## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q4 2015 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 200% | 250% | 253.6% | 210% | 210% | 213.4% | 140% | 130% | 134.1% | 184% | 178% | 227.6% | 196.2%
.x.2 | % of promised (by that time) CPU available | 100% | 542% | 599% | 666.2% | 411% | 411% | 410.5% | 426% | 395% | 395.4% | 560% | 561% | 563.9% | 498.7%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ??
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ??
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 97% | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 100% | 78% | 19.5% | ??
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 24% | 25% | 35.9% | 63% | 63% | 88.89% | 76% | 51% | 80.9% | 33% | 15% | 35.89% | 58.45%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 36% | 26% | 29.22% | 66% | 73% | 83.56% | 70% | 72% | 73.99% | 30% | 31% | 30.45% | 52.05%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | 0
Quarter | 0
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Site | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total |  | Site | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | 0 | 11944036 | 11881879 | 5901085 | 29727000 |  | 0 | 12840966 | 12897936 | 10783127 | 36522029
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | 0 | 9612112 | 11364681 | 11014316 | 31991109 |  | 0 | 10038553 | 11934641 | 12058839 | 34032033
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | 0 | 21248793 | 22911693 | 14502384 | 58662870 |  | 0 | 24055271 | 24805898 | 15286491 | 64147660
[7 empty] | 0 | 3201087 | 3133267 | 2451260 | 8785614 |  | 0 | 3649212 | 3636278 | 3070060 | 10355550
[7 empty] | Total CPU hrs | 42804941 | 46158253 | 31417785 | 120380979 |  | Total | 50584002 | 53274753 | 41198517 | 145057272
Current Resources Available | [6 empty] | Used dev accounting portal. | [6 empty] | http://accounting-devel.egi.eu/tier2.php?Path=1.36.2&query=sum_normelap_nprocessors&startYear=2015&startMonth=10&endYear=2015&endMonth=12&yrange=SITE&xrange=DATE&groupVO=all&chart=GRBAR&scale=LIN&localJobs=onlygridjobs
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
0 | 46080 | 2140 | 6917 | 844 | 666.2% | 253.6% | 41% | 43.43% | 29727000 | 23.01% | 2208 | 101744640 | 29.22% | 35.9%
0 | 17339 | 783 | 4224 | 367 | 410.5% | 213.4% | 15.43% | 15.89% | 31991109 | 24.77% | 2208 | 38284512 | 83.56% | 88.89%
0 | 35910 | 1370 | 9081 | 1022 | 395.4% | 134.1% | 31.95% | 27.8% | 58662870 | 45.42% | 2208 | 79289280 | 73.99% | 80.9%
0 | 13066 | 635 | 2317 | 279 | 563.9% | 227.6% | 11.63% | 12.89% | 8785614 | 6.802% | 2208 | 28849728 | 30.45% | 35.89%
Totals | 112395 | 4928 | 22539 | 2512 | 498.7% | 196.2% | 100% | 100% | 129166593 | 100% | 2208 | 248168160 | 52.05% | 58.45%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
0 | 3200 | 46080 | 2140 | NA | 0
0 | 1383 | 17337 | 784 | NA | 0
0 | 3646 | 35910 | 1370 | NA | 0
0 | 1071 | 13066 | 635 | NA | 0
Totals | 9300 | 112393 | 4929 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | 0
Quarter | 0
Reported by | 0
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | esr | epic | fusion | geant4 | gridpp | hone | ilc | lhcb | LLST | mice | magic | na48 | neiss | ops | pheno | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
0 |  | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 21
0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 31
0 |  | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 17
0 | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  | 1 | 0 | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 18
Total | 2 | 4 | 1 | 4 | 1 | 3 | 2 | 1 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 4 | 3 | 3 | 4 | 1 | 2 | 2 | 1 |  | 4 | 4 | 3 | 1 | 1 | 4 | 2 | 3 | 4 |  | 87
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 930 | 0.13 | 16 | 6 | 952.13 | 1.68% | 2.324%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3100.24 | 0.7 | 178 | 13.47 | 3400.59 | 5.234% | 5.651%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | 0
Quarter | 0
Reported by | 0
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
0 | R. Long | 1 | 1 | 1
| M. Doidge | 1 | 1 | 1
| P. Love |  |  |  | 0.3 | 0.3 | 0.3
0 | S. Jones | 1 | 1 | 1
| R. Fay |  |  |  | 0.5 | 0.5 | 0.5
| J. Bland |  |  |  | 0.5 | 0.5 | 0.5
0 | A. Forti | 1 | 1 | 1
| R. Frank | 1 | 1 | 1
| A. McNab |  |  |  | 0.5 | 0.5 | 0.5
0 | E. Korolkova | 0.5 | 0.5 | 0.5
| M. Robinson |  |  |  | 0.1 | 0.1 | 0.1
Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | 0.5 | 0.5 | 0.5
Manchester | A. Forti |  |  |  | 1 | 1 | 1

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q4
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Infrastructure Move to Vmware Disaster Recovery Deployed New Kit Ansible Management Procurement. | Increased performance Picked ourselves up from floods and power outages. New storage and compute online More efficient site management New kit ordered |  |  | Used unexpected downtime to do move. More downtime then we'd like. None. None (yet). Delivery mid-March.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | glexec has become increasing relevant, but still no solution yet. Still no IPv6. DPM headnode out of warranty. |  |  | Working towards a relocatable solution. IPv6 requires downtime scheduled (March). Plan to try out a virtualised headnode on the Unviersity' Vmware cluster.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Move to new new Infrastructure (central Vmware server). Pulled ourselves up after a natural disaster. |  |  | 12/12/15 12/12/15 |  | Increased stability. Reasonably swift recovery.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Dual Home Perfsonar by Easter (after downtime to enable on switches). Glexec (or a similar solution) on nodes Smooth running |  |  | 31/3/16 31/3/16 31/3/16 |  | IPv6 mesh engagement Finally close that ticket. No natural disasters please!
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes

## Manchester
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q4
Reported by | A Pilkington
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Manchester |  | 1) Integrate DPM in puppet and abandon YAIM: done for data servers 2) Continued development and running of Vac (318 VMs) and GridPP Vcycle service (managing VMs at IC, CERN, CC-IN2P3, Datacentred.co.uk) at Manchester 3) Transition of GridPP website from GridSite to Wordpress plus X.509 plugin written by Andrew 4) Operating GridPP’s site monitoring framework for the Vac and Vcycle managed sites at the request of GridPP 5) Icecube and LHCb are exploiting the prototype GPU service within grid jobs to run their existing GPU dependent code 6) Manchester has continued as one of the UK’s three LHCb T2-D sites with storage 7) Deployed monitoring framework for Vac resources based on ElasticSearch/Kibana |  |  | a few hhd failures (WN, SE), dead motherboards (WN), PSU (SE), and memory (WN) Problem with VOMS server sending service notifications to wrong email address
Note:To get multiple lines per box use Alt-Return |  | 3)
Institute or area specific risks
Site | Risk |  |  | Mitigating Action
Manchester
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/Htcondor on at least 1 cluster, 2) Integrate DPM in puppet and abandon YAIM, 3) Test remaining SE with failed raid array, fix remaining problems, and return it into full service. 4) Extend IPv6 to more hosts 6)Add APEL-Sync records to Vac usage reporting to pass the EGI APEL SAM tests 7) Extend the accounting analysis tool to produce reports automatically as a web page for daily monitoring rather than just as an offline tool 8) Look into foreman deployment 9) Improve local tools to balance data servers 10) Test ATLAS consistency tools |  |  |  |  | 1) stalled 2) in progress 3) in progress 4) stalled 8) in progress
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/Htcondor on at least 1 cluster, 2) Integrate DPM in puppet and abandon YAIM, 3) Test remaining SE with failed raid array, fix remaining problems, and return it into full service. 4) Extend IPv6 to more hosts 5) Increase number of machines managed by Vac in the Tier-2 6) Add APEL-Sync records to Vac usage reporting to pass the EGI APEL SAM tests 7) Extend the accounting analysis tool to produce reports automatically as a web page for daily monitoring rather than just as an offline tool 8) Look into foreman deployment 9) Improve local tools to balance data servers 10) commission new hardware 11) decommission remaining 2005 Dells
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs.
Working with LSST users to adapt their workflow to use grid resources
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Alessandra Forti chaired session on opportunistic resources at the ATLAS TIM https://indico.cern.ch/event/437170/timetable/#all.detailed |  |  | 2015-12-02
Andrew McNab presentations: “Batch and Cloud overview”, UK-T0 kickoff meeting, 20 Oct 2015. “LHCb infosystem plans” and “Publishing GLUE2 in JSON”, WLCG Information System Task Force meeting, 12 Nov 2015. |  |  | 20/10/2015 and 12/11/15
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Alessandra is one of the GridPP representatives and one of the co-chairs of the WLCG Ops Coordination, Atlas monitoring coordinator and member of the atlas distributed computing coordination; Multicore TF co-leader; WLCG workshop 2016 planning committee.
Andrew is the Deputy LHCb Computing Coordinator and LHCb Distributed Computing and Operations Coordinator. He is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group and leading the GridPP Tier-2 Evolution project. He is leader of the WLCG "Machine Features” task force, and a member of the "Cloud Traceability”, “Cloud Resource Reporting”, and “Information Systems Evolution" task forces. He completed serving on the CHEP2015 Programme Committee in December, and is on the HEP Software Foundation interim steering board.
Other outputs and Knowledge |  |  | Date |  | Notes

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q4
Reported by | S Jones
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Security HW Maint SW Maint, upgrades and Dev etc. New cluster type Documentation and test Tickets | New Kernel (2.6.32-573.3.1) Disk recon, PDU exchange,draft for new HW quotes, Centos7 Build system, MCORE slot stickiness, Snaky (rebuild system) for Arc/Condor, New APEL rpms (2.1.5-1 (sslv3) Vac cluster, 120 slots. (monitoring in progress) Usability testing of Tom's new User Guide (small VOs), ARC BDII patch to give VO job breakdown, GLUE Log/Phys CPU definition (for Maria, CERN), Approved VOs (regular updates, new VO (LZ)) 116918 Reduce BDII warnings 117585 Fix ARGUS Config (pilots) 117154, 118233 Flaky BDII 117884 ATLAS Consistency checking. |  | Centos7 very different to SL6. May cause problems. Vac being tested. Will report in due course.
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | IPV6 Centos7 |  | Still waiting - status to be req. today. Quite different to SL6. Will need testing for migration.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | CSD Cluster Share + Explore Cloud Technologies VAC, (VCYCLE?) IPV6 Test System Usability test, report filed. |  | 31/12/2015 31/12/2015 31/12/2015 |  | DONE. Will expand (see below). Still awaiting allocation. Asked for status. Done.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | CSD Cluster Share + Explore Cloud Technologies VAC IPV6 Test System New round of Usability Tests for 'Guest Experiment' documentation Contos7 Tests |  | 31/03/2016 31/03/2016 31/03/2016 31/03/2016 |  | Expanding to hundreds of slots. L'pool to be test site. Status awaited. Will try to prioritise. Report. Get a baseline made, and add some service nodes in Centos7 format.

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q4
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | All servers are now running on sl6. Analysis abailability for ATLAS ( ASAP metric) is 98.3%. Other general sysadmin work (security, new certificates, bad worker nodes etc). Cloud support work. |  |  | Disk servers recently reinstalled as sl6 are overloaded asthey have free space, while others are nearly full. Old 6-cores wn's wn's are removed but we still advertising them . As a result Sheffield has low utilisation of cpu hours. Perfsonar server haven't been fully reconfigured as ipv6 machine.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Moving grid servers to ipv6 configured may cause lots of problem. |  |  | Wait for gaining more experience and proper instructions for ipv6 configuration
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | All machines are now on sl6 |  |  | 24 December 2015
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Finish procurement. Reconfigure perfsonar server as ipv6 machine. Fix cpu publishing. |  |  | 2016-03-31
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes