## Overview
GridPP4 Goal
To provide UK computing in the LHC era
Tier- 1 |  | WPA | Tier-1 |  | WPA | Tier-2 |  | WPB/C |  |  | WPC/D |  |  | WPE/F
Operations |  |  | Experiments |  |  | Experiments and Ops |  |  | Grid and expt support |  |  | Management and Impact
Manager: A. Sansum |  |  | Manager: A.Sansum |  |  | Manager: S. Lloyd |  |  | Manager: J. Coles |  |  | Manager: D. Britton
| Task A1 |  |  | Task A5 |  |  | Task B1 |  |  | Task C2 |  |  | Task E1
|  |  |  | ATLAS |  |  | ATLAS
| Production and grid |  |  | Tier-1 |  |  | Tier-2 |  |  | Data Group |  |  | Planning
| G.Smith |  |  | R.Jones |  |  | R.Jones |  |  | T.Doyle |  |  | P Gronbech
| Task A2 |  |  | Task A6 |  |  | Task B2 |  |  | Task C3 |  |  | Task E2
|  |  |  | CMS |  |  | CMS
| Storage system |  |  | Tier-1 |  |  | Tier-2 |  |  | Security |  |  | Execution
| M. Viljeon |  |  | D, Colling |  |  | D.Colling |  |  | D. Kelsey |  |  | P Gronbech
| Task A3 |  |  | Task A7 |  |  | Task B3 |  |  | Task C4 |  |  | Task F1
| Fabric and |  |  | LHCb |  |  | LHCb
| machine room |  |  | Tier-1 |  |  | Tier-2 |  |  | NGI |  |  | Outreach
| M. Bly |  |  | P. Clarke |  |  | P. Clarke |  |  | J. Gordon |  |  | N. O'Neill
| Task A4 |  |  | Task A8 |  |  | Task B4 |  |  | Task D1
Hardware
| procurement |  |  | Other expts Tier-1 |  |  | Other expts Tier-2 |  |  | Experiment Support
| D. Corney |  |  | P.Gronbech |  |  | P.Gronbech |  |  | P.Gronbech
Task C1
Grid Deployment and
Operational Performance
J.Coles

## Metrics and Milestones
GridPP4+ Goal
To provide UK computing in the LHC era
[30 empty] | Date | 2016-04-21
[30 empty] | 169 |  | Metric OK
Tier- 1 |  |  |  | WPA |  | Tier-1 |  |  |  | WPA |  | Tier-2 |  |  | WPB/C | [5 empty] | WPC/D | [5 empty] | WPE/F |  |  | 7 |  | Metric close to target
Operations | [5 empty] | Experiments | [5 empty] | Experiments and Ops | [5 empty] | Grid and expt support | [5 empty] | Management and Impact | [5 empty] | 1 |  | Metric not OK
[30 empty] | 0 |  | Not able to be measured
[30 empty] | 19 |  | Milestone achieved
| Production and grid | [5 empty] | ATLAS T1 | [5 empty] | ATLAS T2 | [5 empty] | Data Group | [5 empty] | Planning |  |  |  |  | 0 |  | Milestone underway
| A1 | [5 empty] | A5 | [5 empty] | B1 | [5 empty] | C2 | [5 empty] | E1 |  |  |  |  | 1 |  | Milestone overdue
| A1.1 | A1.2 | A1.3 | A1.4 | A1.5 |  | A5.1 | A5.2 | A5.3 | A5.4 | A5.5 |  | B1.1 | B1.2 | B1.3 | B1.4 | B1.5 |  | C2.1 | C2.2 | C2.3 | C2.4 | C2.5 |  | E1.1 | E1.2 | E1.3 | E1.4 | E1.5 | 13 |  | Milestone not due / metric n/a
| A1.6 | A1.7 | A1.8 | A1.9 | A1.10 |  | A5.6 | [5 empty] | B1.6 | B1.7 | B1.8 | B1.9 | B1.10 |  | C2.6 | C2.7 | C2.8 | C2.9 | C2.10 |  | E1.6 | E1.7 | E1.8 | E1.9 | E1.10 | 19 |  | Suspended
| A1.11 | A1.12 | A1.13 | A1.14 | A1.15 | [7 empty] | B1.11 | B1.12 |  |  |  |  | C2.11 | C2.12 | C2.13 | C2.14 | [7 empty] | 0 |  | Awaiting input
| A1.16 | A1.17 | [27 empty] | 229 |  | Total | 229
| Storage system | [5 empty] | CMS T1 | [5 empty] | CMS T2 | [5 empty] | Security | [5 empty] | Execution
| A2 | [5 empty] | A6 | [5 empty] | B2 | [5 empty] | C3 | [5 empty] | E2
| A2.1 | A2.2 | A2.3 | A2.4 | A2.5 |  | A6.1 | A6.2 | A6.3 | A6.4 | A6.5 |  | B2.1 | B2.2 | B2.3 | B2.4 | B2.5 |  | C3.1 | C3.2 | C3.3 | C3.4 |  |  | E2.1 | E2.2 | E2.3 | E2.4 | E2.5
| A2.6 | A2.7 | A2.8 | A2.9 | A2.10 |  | A6.6 | A6.7 | A6.8 | A6.9 | A6.10 |  | B2.6 | B2.7 | B2.8 | B2.9 | B2.10 | [7 empty] | E2.6 | E2.7 | E2.8 | E2.9 | E2.10
| A2.11 | A2.12 |  |  |  |  | A6.11 | [5 empty] | B2.11 | B2.12 | B2.13 | B2.14 | B2.15 | [7 empty] | E2.11 | E2.12
[13 empty] | B2.16 | B2.17 | B2.18 | B2.19 | B2.20
[13 empty] | B2.21 | B2.22 | B2.23 | B2.24 | B2.25
[13 empty] | B2.26 | B2.27 | B2.28
| Fabric | [5 empty] | LHCb T1 | [5 empty] | LHCb T2 | [5 empty] | NGI | [5 empty] | Outreach
| A3 | [5 empty] | A7 | [5 empty] | B3 | [5 empty] | C4 | [5 empty] | F1
| A3.1 | A3.2 | A3.3 | A3.4 | A3.5 |  | A7.1 | A7.2 | A7.3 | A7.4 | A7.5 |  | B3.1 | B3.2 | B3.3 | B3.4 |  |  | C4.1 | C4.2 | C4.3 | C4.4 | C4.5 |  | F1.1 | F1.2 | F1.3 | F1.4 | F1.5
| A3.6 | A3.7 | A3.8 | A3.9 | A3.10 |  | A7.6 | A7.7 | [10 empty] | C4.6 | C4.7 | C4.8 | C4.9 |  |  | F1.6 | F1.7 | F1.8 | F1.9
| A3.11 | A3.12 | A3.13 | A3.14 | A3.15
| Hardware Procurement | [5 empty] | Other expts T1 | [5 empty] | Other expts T2 | [5 empty] | Experiment Support
| A4 | [5 empty] | A8 | [5 empty] | B4 | [5 empty] | D1
| A4.1 | A4.2 | A4.3 | A4.4 | A4.5 |  | A8.1 | A8.2 | A8.3 | A8.4 | A8.5 |  | B4.1 | B4.2 |  |  |  |  | D1.1 | D1.2 | D1.3 | D1.4 | D1.5
[7 empty] | A8.6 | [11 empty] | D1.6 | D1.7 | D1.8 | D1.9 | D1.10
[19 empty] | D1.11 | D1.12 | D1.13 | D1.14
Deployment and Performance
C1
[13 empty] | C1.1 | C1.2 | C1.3 | C1.4 | C1.5
[13 empty] | C1.6 | C1.7 | C1.8 | C1.9 | C1.10
[13 empty] | C1.11 | C1.12 | C1.13 | C1.14 | C1.15
[13 empty] | C1.16 | C1.17 | C1.18 | C1.19 | C1.20
[13 empty] | C1.21 | C1.22 | C1.23 | C1.24 | C1.25
[13 empty] | C1.26 | C1.27 | C1.28 | C1.29 | C1.30
[13 empty] | C1.31 | C1.32

## WPA
WP A: Tier-1
Manager: Andrew Sansum
Task no. | Task | Metric | Milestone | Target/ date | Monthly | Owner | Description | Q415 | Comment
A1 | Production and grid | 1 |  | 100% |  | John Gordon | Fraction of WLCG MoU commitment for CPU 100 % | 117%
A1 | Production and grid | 2 |  | 100% |  | Andrew Sansum | % met of RB allocation for CPU 100 % | 126%
A1 | Production and grid | 3 |  | 99% |  | Andrew Sansum | Availability of LFC service 99% | 100%
A1 | Production and grid | 4 |  | 99% |  | Andrew Sansum | SAM availability of FTS service 99 % |  | No measurement for FTS3.
A1 | Production and grid | 5 |  | 99% |  | Andrew Sansum | SAM availability of MyProxy service 99 % | 100%
A1 | Production and grid | 6 |  | 99% |  | Andrew Sansum | SAM availability of toplevel BDII service 99 % | 100%
A1 | Production and grid | 7 |  | 99% |  | Andrew Sansum | Availability of WMS service 99 % | 100%
A1 | Production and grid | 8 |  | 98% |  | Andrew Sansum | Availability of LHCB VO box 98 % | 100%
A1 | Production and grid | 9 |  | 98% |  | Andrew Sansum | Availability of ALICE VO box 98 % | 100%
A1 | Production and grid | 10 |  | 99% |  | Andrew Sansum | Availability of CMS VO box 99 %
A1 | Production and grid | 11 |  | 99% |  | Andrew Sansum | Availability of CE service 99 % | 100%
A1 | Production and grid | 12 |  | 2 | Yes | Andrew Sansum | Number of Security Incidents 2 per year | 0
A1 | Production and grid | 13 |  | 0 | Yes | Andrew Sansum | # level 3 incidents(newly entered or active) in disaster management system 0 | 0
A1 | Production and grid | 14 |  | 0 | Yes | Andrew Sansum | # level 4 incidents (newly entered or active) in disaster management system 0 | 0
A1 |  | 15 |  | 0.93 |  | Andrew Sansum | Percentage of GRIDPP4 Staff in Post 93 % | 91% | New achievable max staff count reduced to 18.5 during GridPP4+ (owing to overheads changes). As staff count needs to fall to 17.5 in April it is not feasible to hit current target.
A1 | Production and grid |  | 16 | 2015-05-01 |  | Andrew Sansum | External review of operation |  | Anticpate during first half of 2016
A1 | Production and grid |  | 17 | 2015-06-01 |  | Andrew Sansum | Strategic and operations plan agreed |  | Anticpate during first half of 2016
A2 | Storage system | 1 |  | 1 |  | Andrew Sansum | Fraction of WLCG MoU commitment for Disk 100 % | 171%
A2 | Storage system | 2 |  | 1 |  | Andrew Sansum | Fraction of WLCG MoU commitment for Tape 100 % | 100%
A2 | Storage system | 3 |  | 1 |  | Andrew Sansum | % met of RB Allocation for Tape 100 % | 112.3%
A2 | Storage system | 4 |  | 1 |  | Andrew Sansum | % met of RB Allocation for Disk 100 % | 134.3%
A2 | Storage system | 5 |  | 2 |  | Andrew Sansum | # Storage node failures leading to filesystem loss or damage | 0.66667
A2 | Storage system | 6 |  | 1% |  | Andrew Sansum | % Lost disk server hours due to hardware problems over deployed base | 0.2633%
A2 | Storage system | 7 |  | 1 |  | Andrew Sansum | Number of Damaged GRIDPP Tapes, leading to data loss 1 in 500 | 0
A2 | Storage system | 8 |  | 99% |  | Andrew Sansum | CASTOR SAM tests: ATLAS VO | 99%
A2 | Storage system | 9 |  | 99% |  | Andrew Sansum | CASTOR SAM tests: ALICE VO | 100%
A2 | Storage system | 10 |  | 99% |  | Andrew Sansum | CASTOR SAM tests: CMS VO | 99%
A2 | Storage system | 11 |  | 99% |  | Andrew Sansum | CASTOR SAM tests: LHCb VO | 99% | LHCb load (stripping campaign) in January affected LHCb SRMs causing tests to timeout.
A2 | Storage system | 12 |  | 99% |  | Andrew Sansum | Reliability of tape robot 99 % | 100%
A3 | Fabric and machine room | 1 |  | 97% | Yes | Andrew Sansum | WLCG Service Availability Target (set lower by WLCG than MoU, taken from OPS availability) 97 % | 99.67%
A3 | Fabric and machine room | 2 |  | 97% | Yes | Andrew Sansum | WLCG Service Availability for Alice 97 % | 100%
A3 | Fabric and machine room | 3 |  | 97% | Yes | Andrew Sansum | WLCG Service Availability for ATLAS 97 %
A3 | Fabric and machine room | 4 |  | 97% | Yes | Andrew Sansum | WLCG Service Availability for CMS 97 % | 99%
A3 | Fabric and machine room | 5 |  | 97% | Yes | Andrew Sansum | WLCG Service Availability for LHCB 97 %
A3 | Fabric and machine room | 6 |  | 95% |  | Gareth Smith | Respond to pager within 2 hours 95 % | 96% | Q4 availabilities affected by problem with glexec tests over a weekend following updating the final batch of worker nodes with a new configuration.
A3 | Fabric and machine room | 7 |  | 3 per month |  | Gareth Smith | Number of GGUS Tickets not responded to within two hours .
A3 | Fabric and machine room | 8 |  | 70% |  | Gareth Smith | Job Efficiency (CPU/Wall) 70 % | 99% | See comment for A2.11
A3 | Fabric and machine room | 9 |  | 70 |  | Gareth Smith | Farm Occupancy 70 %
A3 | Fabric and machine room | 10 |  | 20% |  | Gareth Smith | Percentage of available T1 Disk 1 used in quarter 20 % | 100%
A3 | Fabric and machine room | 11 |  | 5416 |  | Gareth Smith | Used tape capacity | 0.33333
A3 | Fabric and machine room | 12 |  |  |  | Gareth Smith | WLCG Availability Rank for Alice | 82.33% | During much of December jobs were being restarted by condor due to problems. However, accounting scripts currently use CPU time from only the final job run but wall clock time from all job runs.
A3 | Fabric and machine room | 13 |  | 5.5 |  | Gareth Smith | WLCG Availability Rank for ATLAS | 91.33%
A3 | Fabric and machine room | 14 |  | 4 |  | Gareth Smith | WLCG Availability Rank for CMS | 76%
A3 | Fabric and machine room | 15 |  |  |  | Gareth Smith | WLCG Availability Rank for LHCB | 13589
A4 | Hardware procurement |  | 1 | 2016-03-01 |  | Andrew Sansum | Internal strategic and technology review |  | Will need to take place now GridPP5 resolved. May depend on new Tier1 manager.
A4 | Hardware procurement |  | 2 | 2015-06-01 |  | Andrew Sansum | Produce the purchasing plan |  | Taking this as the purchasing plan for spendind within the 2016/17 FY.
A4 | Hardware procurement |  | 3 | 2015-04-01 |  | Andrew Sansum | Capacity procurements started |  | PG - This has started
A4 | Hardware procurement |  | 4 | 2015-09-01 |  | Andrew Sansum | Capacity order placed |  | Late. (Although not done during the quarter of this report tenders were issued for replies by 18th Dec 2015.)
A4 | Hardware procurement |  | 5 | 2016-03-01 |  | Andrew Sansum | Tier-1 WLCG MoU commitments met

## WPA - Experiments
Delivery to experiments
Manager: Dave Britton
Task no. | Experiment | Metric | Milestone | Target/ date | Monitored monthly? | Owner | Description | Q415 | Comment
A5 | ATLAS | 1 |  |  |  | Roger Jones | T1 Required hardware deployed
A5 | ATLAS | 2 |  | 0.95 | Yes? | Roger Jones | T1 Job success rates from ATLAS dashboard (site-only metrics) | 0.98
A5 | ATLAS | 3 |  | 0.98 | Yes? | Roger Jones | T1 Data availability from the ATLAS dashboard; if we can automate this reliably, we can make it monthly | 0.982
A5 | ATLAS | 4 |  | 0.98 | Yes? | Roger Jones | Data acceptance from Tier 0/Tier 1s/Tier 2s - ATLAS SAM tests
A5 | ATLAS | 5 |  | 0.01 |  | Roger Jones | Data loss - Cedric's page
A5 | ATLAS |  | 6 | 2015-12-01 |  | Roger Jones | Report to PMB on delivery during year
A6 | CMS | 1 |  |  |  | Dave Colling | T0-RAL T1 transfer rate | OK
A6 | CMS | 2 |  |  |  | Dave Colling | T0-RAL T1 transfer quality | OK
A6 | CMS | 3 |  |  |  | Dave Colling | T1-T1 (where Ral is one of T1) transfer rate | OK
A6 | CMS | 4 |  |  |  | Dave Colling | T1-T1 (where Ral is one of T1) transfer quality | OK
A6 | CMS | 5 |  |  |  | Dave Colling | Timely and efficient availability and use of resources at RAL T1 | OK
A6 | CMS | 6 |  | 250MB/s |  | Dave Colling | Tape migration rate | OK
A6 | CMS | 7 |  |  | Yes | Dave Colling | Data Loss at Tier-1 | OK
A6 | CMS | 8 |  | 0.9 |  | Dave Colling | Site availability at the Tier-1 | OK
A6 | CMS | 9 |  | 0.9 |  | Dave Colling | Site readiness at the Tier-1 | OK
A6 | CMS | 10 |  |  |  | Dave Colling | Provide an appropriate level of resources to CMS | OK
A6 | CMS |  | 11 | 2015-12-01 |  | Dave Colling | Report to PMB on delivery during year
A7 | LHCB | 1 |  | 0.15 |  | Raja Nandakumar | Processing: Fraction of jobs executed at UK T1 | 21%
A7 | LHCb | 2 |  | T1>70% | Yes | Raja Nandakumar | Processing: Fraction of jobs that were successful in the RAL Tier-1 | 95.24%
A7 | LHCb | 3 |  | 0.9 |  | Raja Nandakumar | Processing: Overall job efficiency | 96.15%
A7 | LHCb | 4 |  | #lost files/Q=0 #diskservers down over 8 hours < 3 |  | Raja Nandakumar | UK T1 SE Reliability | 5 1 | One disk server failed twice, resulting in the loss of 5 files
A7 | LHCb | 5 |  | 0.5 | Yes | Raja Nandakumar | User analysis: Fraction of jobs that were successful in the RAL Tier-1 | 91.7%
A7 | LHCb | 6 |  | 0.7 |  | Raja Nandakumar | User analysis: Overall job efficiency | 96.94%
A7 | LHCb |  | 7 | 2015-12-01 |  | Raja Nandakumar | Report to PMB on delivery during year
A8 | Other expts | 1 |  | 75% |  | Duncan Rand | UK T1 CPU efficiency for "other" experiments. (non-alice) | 77.3% | Large drop in CPU efficiency for other experiments. Closer inspection indicates drops in biomed, ilc, na62 and t2k CPU efficiencies. Still exceeded target.
A8 | Other expts | 2 |  | 2% | Yes | Duncan Rand | Fraction of CPU time used by other experiments at UK T1.(non Alice) | 6.5% | Exceeded target.
A8 | Other expts | 3 |  | >1 |  | Duncan Rand | Number of new user groups for UK Grid. | 1 | Added EUCLID. So list now includes: DEAP3600, DiRAC, EUCLID, GalDyn, LIGO, LOFAR, LSST, LZ, , PraVDA, SNO+, SuperNemo, GalDyn, UKQCD although not all are running jobs yet. https://www.gridpp.ac.uk/wiki/GridPP_VO_Incubator
A8 | Other expts |  | 4 | 2015-12-01 |  | Duncan Rand | Report to PMB on delivery during year
A8 | Other expts | 5 |  | 75% |  | Duncan Rand | UK T1 CPU efficiency for Alice. | 79.3% | Drop maintained, still above target however.
A8 | Other expts | 6 |  | 10% |  | Duncan Rand | Fraction of CPU time used by Alice at UK T1. | 12.66% | Exceeded target.

## WPB-C
WP B: Tier-2s
Manager: Steve Lloyd
Task no. | Task | Metric | Target/Date | Monthly? | Owner | Description | Q415 | Comments
B1 | ATLAS group analysis | 1 | Requested share dynamic |  | Roger Jones | Slots available to ATLAS for group analysis |  | These are run through production - drop the separate metric. SUSPENDED post PMB 13/9/11
B1 | ATLAS group analysis | 2 | Requested Share dynamic |  | Roger Jones | Group data space deployed in space tokens (Peter Love pages)
B1 | ATLAS group analysis | 3 | 0.95 |  | Roger Jones | Production job success rates (site only metrics) - from PANDA dashboard | 0.976
B1 | ATLAS group analysis | 4 | 0.95 | Yes? | Roger Jones | Data availability from the ATLAS dashboard; if we can automate this reliably, we can make it monthly | 0.956
B1 | ATLAS group analysis | 5 |  |  | Roger Jones | Data acceptance - via the Steve Lloyd page folded with the available storage (Peter Love page) | 0.984
B1 | ATLAS group analysis | 6 | 0.05 |  | Roger Jones | Data loss - Cedric's page
B1 | User analysis and production | 7 | Requested Share dynamic |  | Roger Jones | ATLAS Available simulation and user analysis slots
B1 | User analysis and production | 8 | RRB vs Space token |  | Roger Jones | ATLAS available storage in production space
B1 | User analysis and production | 9 | RRB vs Space token |  | Roger Jones | ATLAS available storage in user space
B1 | User analysis and production | 10 | 0.98 |  | Roger Jones | ATLAS SAM tests uptime T2s
B1 | User analysis and production | 11 | 0.95 |  | Roger Jones | ATLAS job success rates in simulation
B1 | User analysis and production | 12 | 0.95 |  | Roger Jones | ATLAS job success rates in user analysis | 0.938
B2 | CMS group analysis | 1 |  |  | David Colling | Bristol - Transfer rates to the UK Tier 2 | Not OK | Monitoring of Bristol as a T2 suspended
B2 | CMS group analysis | 2 | 80% |  | David Colling | Bristol - Site availability at the Tier-2 | Not OK
B2 | CMS group analysis | 3 | 80% |  | David Colling | Bristol - Site readiness at the Tier-2 | Not OK
B2 | CMS group analysis | 4 |  |  | David Colling | Bristol - Unique data loss at Tier-2s | Not OK
B2 | CMS group analysis | 5 |  |  | David Colling | Bristol - Failed analysis jobs | Not OK
B2 | CMS group analysis | 6 |  |  | David Colling | Bristol - Failed production jobs | Not OK
B3 | CMS group analysis | 7 |  |  | David Colling | Bristol - Provide an appropriate level of resource to CMS | OK
B2 | CMS group analysis | 8 |  |  | David Colling | Brunel - Transfer rates to the UK Tier 2 | OK
B2 | CMS group analysis | 9 | 80% |  | David Colling | Brunel - Site availability at the Tier-2 | OK
B2 | CMS group analysis | 10 | 80% |  | David Colling | Brunel - Site readiness at the Tier-2 | OK
B2 | CMS group analysis | 11 |  |  | David Colling | Brunel - Unique data loss at Tier-2s | OK
B2 | CMS group analysis | 12 |  |  | David Colling | Brunel - Failed analysis jobs | OK
B2 | CMS group analysis | 13 |  |  | David Colling | Brunel - Failed production jobs | OK
B3 | CMS group analysis | 14 |  |  | David Colling | Brunel - Provide an appropriate level of resource to CMS | OK
B2 | CMS group analysis | 15 |  |  | David Colling | Imperial - Transfer rates to the UK Tier 2 | OK
B2 | CMS group analysis | 16 | 80% |  | David Colling | Imperial - Site availability at the Tier-2 | OK
B2 | CMS group analysis | 17 | 80% |  | David Colling | Imperial - Site readiness at the Tier-2 | OK
B2 | CMS group analysis | 18 |  |  | David Colling | Imperial - Unique data loss at Tier-2s | OK
B2 | CMS group analysis | 19 |  |  | David Colling | Imperial - Failed analysis jobs | OK
B2 | CMS group analysis | 20 |  |  | David Colling | Imperial - Failed production jobs | OK
B3 | CMS group analysis | 21 |  |  | David Colling | Imperial - Provide an appropriate level of resource to CMS | OK
B2 | CMS group analysis | 22 |  |  | David Colling | RAL PP - Transfer rates to the UK Tier 2 | OK
B2 | CMS group analysis | 23 | 80% |  | David Colling | RAL PP - Site availability at the Tier-2 | OK
B2 | CMS group analysis | 24 | 80% |  | David Colling | RAL PP - Site readiness at the Tier-2 | OK
B2 | CMS group analysis | 25 |  |  | David Colling | RAL PP - Unique data loss at Tier-2s | OK
B2 | CMS group analysis | 26 |  |  | David Colling | RAL PP - Failed analysis jobs | OK
B2 | CMS group analysis | 27 |  |  | David Colling | RAL PP - Failed production jobs | OK
B2 | CMS group analysis | 28 |  |  | David Colling | RAL PP - Provide an appropriate level of resource to CMS | OK
B3 | LHCb User analysis and production | 1 | 10-15MB/s? |  | Raja Nandakumar | LHCb T2 data transfer upload rate | 23.8
B3 | LHCb User analysis and production | 2 | <2 |  | Raja Nandakumar | LHCb No. of sites below WLCG SAM tests uptime target | 2
B3 | LHCb User analysis and production | 3 | >18% (WLCG MoU) |  | Raja Nandakumar | LHCb Fraction of simulation jobs in the UK | 19.6%
B3 | LHCb User analysis and production | 4 | 85% |  | Raja Nandakumar | LHCb job success rates in simulation | 90.92%
B4 | Other Expts | 1 | 5 |  | Duncan Rand | No of non LHC Vos (including ALICE) active at T2s | 13 | alice, biomed, comet, geant4, gridpp, ilc, lsst, lz, mice, na62, pheno, snoplus, northgrid
B4 | Other Expts | 2 | >5% |  | Duncan Rand | Fraction of CPU used by other expts | 14.96% | alice, biomed, ilc, pheno, lz the largest Vos
C1 | Grid operations | 1 | Number of GridPP sites in certified status. Require 100% |  | Jeremy Coles | Fraction of UK sites in Production | 100%
C1 | Grid operations | 2 | Sum of unique VOs supported across GridPP sites - target 4 LHC + 5 other |  | Jeremy Coles | Number of supported VOs | 55
C1 | Grid operations | 3 | HEPSPEC06 used/ HEPSPEC06 available - 80% |  | Jeremy Coles | Fraction of HEPSPEC used | 63% | 70% based on wall clock.
C1 | Grid operations | 4 | Total GridPP HEPSPEC06 nominally available at the end of the last quarter. Target WLCG pledge |  | Jeremy Coles | GridPP HEPSPEC Available | 576730
C1 | Grid operations | 5 | Total TB of disk storage nominally available from GridPP at the end of the last quarter. Target WLCG pledge |  | Jeremy Coles | GridPP disk storage available | 40474
C1 | Grid operations | 6 | 0.95 |  | Jeremy Coles | Job success rates
C1 | Grid operations | 7 | Percentage of jobs run by LHC V0s processed in UK in last quarter. Target is as pledged shares (11%?) |  | Jeremy Coles | UK contribution to LHC experiments | 14.75% | Now using dev portal: http://accounting-devel.egi.eu/egi.php
C1 | Grid operations | 8 | Number of flagged tickets <3 |  | Jeremy Coles | GridPP site response to tickets | 0
C1 | Site performance | 9 | 1 |  | Jeremy Coles | Scotgrid % of promised (by that time) disk available to GridPP | 319%
C1 | Site performance | 10 | 1 |  | Jeremy Coles | Scotgrid % of promised (by that time) CPU available | 611%
C1 | Site performance | 11 | 0.95 | Yes | Jeremy Coles | Scotgrid Average SAM (SLL page) availability | 99%
C1 | Site performance | 12 | 0.95 | Yes | Jeremy Coles | Scotgrid Average SAM (SLL page) reliability | 1--%
C1 | Site performance | 13 | 0.5 |  | Jeremy Coles | Scotgrid CPU utilisation (wall clock time) | 65%
C1 | Site performance | 14 | 0.5 |  | Jeremy Coles | Scotgrid CPU utilisation (CPU time) | 54% | Q-1 figures in latest report and what I added to the last ops report do not correlate! Need to check further.
C1 | Site performance | 15 | 1 |  | Jeremy Coles | Southgrid % of promised (by that time) disk available to GridPP | 238%
C1 | Site performance | 16 | 1 |  | Jeremy Coles | Southgrid % of promised (by that time) CPU available | 309%
C1 | Site performance | 17 | 0.95 | Yes | Jeremy Coles | Southgrid Average SAM (SLL page) availability | 99%
C1 | Site performance | 18 | 0.95 | Yes | Jeremy Coles | Southgrid Average SAM (SLL page) reliability | 99%
C1 | Site performance | 19 | 0.5 |  | Jeremy Coles | Southgrid CPU utilisation (wall clock time) | 70%
C1 | Site performance | 20 | 0.5 |  | Jeremy Coles | Southgrid CPU utilisation (CPU time) | 59% | Interesting that this drops vs wall clock time efficiency. Multi-core jobs presumably?
C1 | Site performance | 21 | 1 |  | Jeremy Coles | Londongrid % of promised (by that time) disk available | 303%
C1 | Site performance | 22 | 1 |  | Jeremy Coles | Londongrid % of promised (by that time) CPU available | 305%
C1 | Site performance | 23 | 0.95 | Yes | Jeremy Coles | Londongrid Average SAM (SLL page) availability | 100%
C1 | Site performance | 24 | 0.95 | Yes | Jeremy Coles | Londongrid Average SAM (SLL page) reliability | 100%
C1 | Site performance | 25 | 0.5 |  | Jeremy Coles | Londongrid CPU utilisation (wall clock time) | 66%
C1 | Site performance | 26 | 0.5 |  | Jeremy Coles | Londongrid CPU utilisation (CPU time) | 62%
C1 | Site performance | 27 | 1 |  | Jeremy Coles | Northgrid % of promised (by that time) disk available to GridPP | 196%
C1 | Site performance | 28 | 1 |  | Jeremy Coles | Northgrid % of promised (by that time) CPU available | 499%
C1 | Site performance | 29 | 0.95 | Yes | Jeremy Coles | Northgrid Average SAM (SLL page) availability | 100%
C1 | Site performance | 30 | 0.95 | Yes | Jeremy Coles | Northgrid Average SAM (SLL page) reliability | 20% | Missing explanation
C1 | Site performance | 31 | 0.5 |  | Jeremy Coles | Northgrid CPU utilisation (wall clock time) | 58%
C1 | Site performance | 32 | 0.5 |  | Jeremy Coles | Northgrid CPU utilisation (CPU time) | 52%
Note on I18: gronbech: Susspended at PMB F2F April 2012
Note on H48: gronbech: how do we measure this
Note on H49: gronbech: how do we measure this

## WPC-D
WP C: Operations and support
Manager: Jeremy Coles
Task no. | Task | Metric | Milestone | Target/date | Owner | Description | Q415 | Comment
C2 | Data Group | 1 |  | 0 | Jens Jensen | Number of VO requested changes not implemented in a timely fashion across whole infrastructure (1wk for small changes, 3wks for medium size, 6wks for large.) - any GridPP VO |  | ATLAS space token cleanup slowed a bit by introduction of new space tokens (at QMUL) but at ATLAS's request.
C2 | Data Group | 2 |  | 0 | Jens Jensen | Number of experiments whose data transfer rates from/to RAL to/from T2s do not meet their (realistic) requirements | 1 | DiRAC transfer slow due to transferring files individually; needs reimplementing.
C2 | Data Group | 3 |  | 85% | Jens Jensen | FTS data transfer success rate |  | T1->T2s 93%, 146 MB/s T2s->T1 87% 222 MB/s (ATLAS+CMS+LHCb only)
C2 | Data Group | 4 |  | 4/Y | Jens Jensen | Conference paper (CHEP, AHM, or similar (or better)) produced each year describing GridPP developments and innovations in data management and storage area |  | no additional papers. Brian presented work at the E2E workshop. GridPP representation at the "UkT0" workshop. Jens' presentation at EGI community forum included GridPP stuff (data transfer)
C2 | Data Group | 5 |  | 4/Q | Jens Jensen | Engage with storage and data management experts within WLCG/EGI/EMI/NGS or similar, or industry, to reinforce GridPP's recognised competence in this area (talks given, meetings, virtual meetings) |  | DPM user group meeting http://indico.cern.ch/event/319828/
C2 | Data Group | 6 |  | 0 | Jens Jensen | Number of incidents not resolved within 1wk after being reported on list
C2 | Data Group | 7 |  | 8 | Jens Jensen | Number of blog posts | 4 | Jens 1, Sam 1, Brian 2 (we need more people to blog rather than more posts from the Usual Suspects!)
C2 | Data Group |  | 8 | 2011-04-01 | Jens Jensen | Milestone for Q312: DPM planing document. Which is done, but needs post-GridPP29 update before going further. | 2011-04-01 | Need to circulate the post-GridPP29 updated version (=final)
C2 | Data Group |  | 9 | 2016-03-31 | Brian Davies | Great ATLAS space token Arkleseizure |  | Completed for some sites. Still need Lancs, QMUL, RALPP, RALT1, OX | lcg-infosites reporting correct (updated) space tokens for ATLAS
C2 | Data Group |  | 10 |  | Sam Skipsey | Syncat v2 testing completed |  | See http://storage.esc.rl.ac.uk/weekly/20150701-minutes.txt for bkg info (item 2)
C2 | Data Group |  | 11 | 2016-03-31 | Brian Davies | Syncat v2 rolled out to all sites supporting VOs that require it |  | Assumes no serious problems found in testing!
C2 | Data Group |  | 12 | 2015-10-19 | Brian Davies | Present GridPP work at JISC E2E workshop | 2015-10-19 | https://www.jisc.ac.uk/events/janet-end-to-end-performance-initiative-workshop-19-oct-2015 | http://storage.esc.rl.ac.uk/weekly/20151104-minutes.txt
C2 | Data Group |  | 13 | 2015-12-10 | Sam Skipsey | (Re)present GridPP at DPM workshop | 2015-12-07
C2 | Data Group |  | 14 | 2015-11-07 | Jens Jensen | DiRAC data transfer document published to other DiRAC sites |  | Needs revision due to more scalable methods being adopted by Durham (mid Jan '16)
C3 | Security | 1 |  |  | Ian Neilson | Number of Tier 2 security incidents in the last quarter | 0 | no incident reported
C3 | Security | 2 |  |  | Ian Neilson | Number of sites responding poorly to a security incident in last quarter | 0
C3 | Security |  | 3 | 2015-12-01 | Ian Neilson | Security Service Challenge |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson and Ewan Macmahon will run a full test in Q4.
C3 | Security |  | 4 | 2014-06-01 | D.P.Kelsey | Security recommendations for the future. |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Q4 2015 after the results of the GridPP5 bid are known.
C4 | NGI | 1 |  |  | John Gordon | UK NGI quarterly reports submitted on time |  | In EGI PY5 (May-Dec 14) these NGI reports are no longer required
C4 | NGI | 2 |  |  | John Gordon | UK Integration metrics sent to EGI |  | In EGI PY5 (May-Dec 14) these NGI reports are no longer required
C4 | NGI | 3 |  |  | John Gordon | UK CPU and storage delivered to EGI | >100
C4 | NGI | 4 |  |  | John Gordon | Monthly timesheets complete by 10th of each month | 100
C4 | NGI | 5 |  |  | John Gordon | GridPP staff PM delivered as required | 100
C4 | NGI | 6 |  | 95% | John Gordon | GOCDB Availability | >99
C4 | NGI | 7 |  | 95% | John Gordon | APEL Availability | >99
C4 | NGI | 8 |  | 1 | John Gordon | # Sites marked Amber by EGI |  | Only red (<80% avail) and Green possible now, no amber
C4 | NGI | 9 |  | 1 down Amber; >1 red | John Gordon | # Sites marked Red by EGI | 2 | UK Green overall. Individually, UCL failing consistently but >80% Sept (A 33%, 72%, pass)
D1 | Tier-1 expt support | 1 |  |  | Pete Gronbech | ATLAS integrated T1 metric
D1 | Tier-1 expt support | 2 |  |  | Glenn Patrick | ATLAS integrated T1 metric
D1 | Tier-1 expt support | 3 |  |  | Pete Gronbech | CMS integrated T1 metric
D1 | Tier-1 expt support | 4 |  |  | Glenn Patrick | CMS integrated T1 metric
D1 | Tier-1 expt support | 5 |  |  | Pete Gronbech | LHCb reporting to monthly T1 expt liaison Meeting
D1 | Tier-1 expt support | 6 |  |  | Pete Gronbech | LHCb reporting to Quarterly resource meeting |  | meeting 18/9/13
D1 | Tier-1 expt support | 7 |  |  | Glenn Patrick | CMS vice J. Jackson post
D1 | Tier-1 expt support | 8 |  |  | Glenn Patrick | CMS Castor metric
D1 | Ganga and user support | 9 |  |  | Ulrik Egede | LHCb Ganga: Unit testing of code within area of responsibility | OK | Move to Jenkins for continuous testing is in progress.
D1 | Ganga and user support | 10 |  |  | Ulrik Egede | LHCb Ganga: Classification of raised tickets for bugs | OK | Move to Jenkins for continuous testing is in progress.
D1 | Ganga and user support | 11 |  |  | Mark Slater | ATLAS Ganga: Close at least 4 Savannah Tickets (bug reports/feature requests) per quarter | 17 Tickets closed | The restart of the DAST shifts with Run II has improved the follow-up on user issues and reporting them as bugs where appropiate
D1 | Ganga and user support | 12 |  |  | Mark Slater | ATLAS Ganga: Dedicate one week per month to being a support shifter and answer >90% of Ganga related queries |  | Spent significant time cleaning out old JIRA tickets
D1 | Ganga and user support | 13 |  |  | Pete Gronbech | Number of new user groups using the T1/UK Grid | 3
D1 | Ganga and user support | 14 |  |  | Pete Gronbech | Number of issues dealt with by user support posts |  | Full report by Janusz in main report.
Note on H20: gronbech: Green <=1, Amber 2 or 3 and Red >=4
Note on H21: gronbech: Green 0, Amber 1, Red >=2
Note on H26: gronbech: Do we have an MoU with EGI ?
Note on F32: John Gordon: Metric changed to 95% in Q3 2009

## WPE-F
WP E: Management
Manager: Dave Britton
Task no. | Task | Metric | Milestone | Target/date | Owner | Description | Date Complete | Comment
E1 | Planning |  | 1 | 2015-04-01 | Dave Britton | Financial plan for GridPP4+ established | 2015-03-01
E1 | Planning |  | 2 | 2015-05-01 | Pete Gronbech | Draft ProjectMap for GridPP4+. GridPP4+ ProjectMap exists with >80% of areas defined | 2015-05-01
E1 | Planning |  | 3 | 2015-07-01 | Pete Gronbech | Final project map for GridPP4+. More than >95% of areas defined | 2015-08-01 | Completed
E1 | Planning |  | 4 | 2015-06-01 | Pete Gronbech | Quarterly reporting system agreed for Tier-1 | 2015-08-01 | Completed
E1 | Planning |  | 5 | 2015-07-01 | Pete Gronbech | Quarterly reporting system agreed for other areas | 2015-06-01
E1 | Planning | 6 |  |  | Pete Gronbech | Hardware allocation made by T1 resource board for next period |  | T1 resource meeting held
E1 | Planning |  | 7 | 2015-10-01 | Pete Gronbech | T2 staff grants issued for GridPP5 |  | Completed in Jan 2016
E1 | Planning |  | 8 | 2015-09-01 | Pete Gronbech | Allocations calculated for Tier-2 hardware grants | 2015-10-01
E1 | Planning |  | 9 | 2015-12-01 | Pete Gronbech | Grants for Tier-2 hardware issued |  | Completed Dec 2015
E1 | Planning |  | 10 | 2015-01-01 | Dave Britton | Post-GridPP4+ planning initiated | 2015-04-01 | GridPP5 proposal submitted 10/3/15
E2 | Execution | 1 |  | <6 | Pete Gronbech | Number of vacant posts | 0.9 | .47 at T1 and ~.44 at T2 & other
E2 | Execution | 2 |  |  | Pete Gronbech | 100% of quarterly reports received by Project Manager within 2 months of quarter end.
E2 | Execution | 3 |  |  | Pete Gronbech | ProjectMap is updated within 3 months of end of each quarter
E2 | Execution | 4 |  |  | Pete Gronbech | Financial model updated within 1 month of changes
E2 | Execution | 5 |  | 40 per year | Pete Gronbech | Weekly video/phone PMB meetings |  | On track
E2 | Execution | 6 |  | 3 / year | Pete Gronbech | Face to face PMB meetings |  | One at each GridPP collaboration meeting (ie 2/ year) + T1 review
E2 | Execution | 7 |  | 1 per year | Pete Gronbech | CB meetings |  | On track
E2 | Execution | 8 |  | 20 per year | Pete Gronbech | Ops Team meetings |  | On track
E2 | Execution | 9 |  | 2 per year | Pete Gronbech | Collaboration meetings |  | On track
E2 | Execution | 10 |  |  | Pete Gronbech | OC papers submitted 1 week before meeting
E2 | Execution |  | 11 | 2015-09-30 | Pete Gronbech | WLCG pledges updated
E2 | Execution |  | 12 | 2015-12-31 | Pete Gronbech | Year 1 review of service to experiments
F1 | Outreach | 1 |  | 4 per year | Tom Whyntie | Number of events GridPP attends with stand/posters | 1 | Total in last year 2
F1 | Outreach | 2 |  | 1 per month | Tom Whyntie | Number of GridPP talks published on website | 0 | Total over the last year 41
F1 | Outreach | 3 |  | 10 per year | Tom Whyntie | Number of GridPP publications | 9 | Total over last year 12
F1 | Outreach | 4 |  | One per month | Tom Whyntie | Number of news items on GridPP web site | 1 | Low this quarter, total of 8/12 for the year
F1 | Outreach | 5 |  | 1 per year | Tom Whyntie | Number of GridPP press releases | 0 | Total for last year 3
F1 | Outreach | 6 |  | 5 per year | Tom Whyntie | Number of press articles about GridPP | 1 | Total over last year 5
F1 | Outreach | 7 |  | 1 per year | Tom Whyntie | Number of KE exploration meetings held | 2 | Total for over last year 3
F1 | Outreach | 8 |  | 10 | Tom Whyntie | Number of non-GridPP funded Groups who use GridPP hardware | 19
F1 | Outreach |  | 9 | 2015-12-31 | Tom Whyntie | KE sections of GridPP website updated