## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q2 2015 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 200% | 200% | 253.6% | 210% | 210% | 213.4% | 140% | 140% | 134.1% | 184% | 184% | 178.1% | 190.7%
.x.2 | % of promised (by that time) CPU available | 100% | 542% | 542% | 599.6% | 411% | 411% | 410.5% | 426% | 426% | 395.4% | 560% | 561% | 563.9% | 478.2%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 97% | 99% | 97% | NA | NA | 50% | 100% | 97% | 0% | 100% | 33% | 10% | 39.25%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 36% | 24% | 25.34% | 83% | 63% | 66.53% | 80% | 76% | 50.83% | 47% | 33% | 14.66% | 39.16%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 43% | 37% | 26.47% | 81% | 66% | 73.72% | 77% | 70% | 72.18% | 42% | 30% | 30.8% | 49.82%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2015
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Site | 2015-04-01 | 2015-05-01 | 2015-06-01 | Total |  | Site | 2015-04-01 | 2015-05-01 | 2015-06-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 1342170 | 11774552 | 10856124 | 23972846 |  | Lancaster | 12680808 | 6756328 | 3514060 | 22951196
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 9654820 | 8986296 | 9275020 | 27916136 |  | Liverpool | 9020600 | 7755696 | 8419080 | 25195376
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 18186988 | 19154052 | 19268044 | 56609084 |  | Manchester | 17896336 | 14793796 | 7174172 | 39864304
[7 empty] | Sheffield | 3341820 | 2605992 | 2840676 | 8788488 |  | Sheffield | 1841644 | 1225164 | 1115276 | 4182084
[7 empty] | Total CPU hrs | 29183978 | 39914900 | 39399188 | 108498066 |  | Total | 41439388 | 30530984 | 20222588 | 92192960
Current Resources Available | [6 empty] | Everyone has CPU-hours > Wall Clock Hours, multicore work abounds this quarter.
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 41472 | 2140 | 6917 | 844 | 599.6% | 253.6% | 38.48% | 44.68% | 23972846 | 20.44% | 2184 | 90574848 | 26.47% | 25.34%
Liverpool | 17339 | 783 | 4224 | 367 | 410.5% | 213.4% | 16.09% | 16.35% | 27916136 | 23.8% | 2184 | 37868376 | 73.72% | 66.53%
Manchester | 35910 | 1370 | 9081 | 1022 | 395.4% | 134.1% | 33.32% | 28.6% | 56609084 | 48.27% | 2184 | 78427440 | 72.18% | 50.83%
Sheffield | 13066 | 497 | 2317 | 279 | 563.9% | 178.1% | 12.12% | 10.38% | 8788488 | 7.493% | 2184 | 28536144 | 30.8% | 14.66%
Totals | 107787 | 4790 | 22539 | 2512 | 478.2% | 190.7% | 100% | 100% | 117286554 | 100% | 2184 | 235406808 | 49.82% | 39.16%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 2880 | 43905 | 2140 | NA | Lancaster
Liverpool | 1383 | 17337 | 783 | NA | Liverpool
Manchester | 3646 | 35910 | 1370 | NA | Manchester
Sheffield | 1071 | 13066 | 497 | NA | Sheffield
Totals | 8980 | 110218 | 4790 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2015
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | esr | epic | fusion | geant4 | gridpp | hone | ilc | lhcb | LLST | mice | magic | na48 | neiss | ops | pheno | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 21
Liverpool | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 31
Manchester |  | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 17
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  | 1 | 0 | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 18
Total | 2 | 4 | 1 | 4 | 1 | 3 | 2 | 1 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 4 | 3 | 3 | 4 | 1 | 2 | 2 | 1 |  | 4 | 4 | 3 | 1 | 1 | 4 | 2 | 3 | 4 |  | 87
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 930 | 0.13 | 16 | 6 | 952.13 | 1.68% | 2.324%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3100.24 | 0.7 | 178 | 13.47 | 3400.59 | 5.234% | 5.651%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2015
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | 1 | 1 | 1
| M. Doidge | 1 | 1 | 1
| P. Love |  |  |  | 0.3 | 0.3 | 0.3
Liverpool | S. Jones | 1 | 1 | 1
| R. Fay |  |  |  | 0.5 | 0.5 | 0.5
| J. Bland |  |  |  | 0.5 | 0.5 | 0.5
Manchester | A. Forti | 1 | 1 | 1
| R. Frank | 1 | 1 | 1
| A. McNab |  |  |  | 0.5 | 0.5 | 0.5
Sheffield | E. Korolkova | 0.5 | 0.5 | 0.5
| M. Robinson |  |  |  | 0.1 | 0.1 | 0.1
Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | 0.5 | 0.5 | 0.5
Manchester | A. Forti |  |  |  | 1 | 1 | 1

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q2
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Start Infrastructure Overhaul Solve VAC problems Tarball work CHEP Papers submiitted Another Network Overhaul planned | Test cluster being tested, VM infrastructure deployed. VAC install problems understood New tarball made and deployed, system polished. Accepted. We have a plan! |  |  | Testing is only on a small scale Between hardware problems and lack of time not been able to do a large scale deployment yet. Still work to be done. Network work will need to be done at the same time that we impliment the switchover.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Still, still, still, still behind on IPv6 investigation. Some more kit is lined up for retirement Still no ARC CE yet Still down to one CE at the moment. |  |  | Still in talks, keep appraised of the situation. None Will deploy on new infrastructure. CE is seasoned and heavily monitored. Jobs flowing.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | New Tarball – UI and WN. WN tarball tested High Reliability and Availability., high job throughput |  |  | 30/6/15 Ongoing |  | Tickets solved, new tarball functionality. Jobs must flow!
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Dual Home something, hopefully, finally! Up to two Ces on a fresh cluster. VAC cluster up and running fully |  |  | 30/9/15 30/9/15 3/8/15 |  | Finally enaged in testing Resiliance would be nice Squeeze some more use out of some older kit.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q2
Reported by | S Jones
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Multicore Multicore Sysadmin Sysadmin SysAdmin SWDev Conferences Conferences CoreTask | Fallow replace DrainBoss (simpler, better) Jura patches in test New VO Support ( LSST ...) tested, works More migration, CREAM/Torque to ARC/Condor Kernel updates, security Ported Snakey to Condor Attended PreGDB (Batch Systems, Condor) Arrangement for GridPP35 at Liverpool Continued Approved VOs work |  | None - much better Needs to be provided to ARC Developers None Still half nodes on TORQUE None None None Large tasks done. Much detailed planning required. None
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | IPV6 GridPP35 bandwidth |  | Indication that address “soon” available. Planning. Coordinate with IT to measure and improve prior to.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Adding New Vos document (slipped) CSD Cluster Share + Explore Cloud Technologies VAC, (VCYCLE?) More work on “RPMs for site VO Management” (slipped) IPV6 Test System |  | 30/06/2015 30/06/2015 30/06/2015 30/06/2015 |  | Note: Tom tested new simpler method. Delete. Continuing to investigate Vac. Aim for Q3. RPM availability Sliiped due to other work.. Asked central services. Hope for addresses in Q3.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | CSD Cluster Share + Explore Cloud Technologies VAC, (VCYCLE?) More work on “RPMs for site VO Management” (slipped) IPV6 Test System GRIDPP35 readiness and execution |  | 30/09/2015 30/09/2015 30/09/2015 09/09/2015 |  | Still building and testing. RPMs available. Low priority. Test System available once addresses come. Big ticket items ready.

## Manchester
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q2
Reported by | Andrew McNab
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Manchester | operations | 1) IPv6 enabled 2) perfsonar, testbed and new voms slave on IPv6 3) deployed vo.dirac.ac.uk VO and removed trainig.ngs.ac.uk VO 4) Ongoing maintenance / replacement of failures in out of warranty equipment5) Helping local Astrophysicist run DES analysis jobs on the Manchester T2 (as part of 10% non-LHC quota). 6) Continued development and running of Vac (318 VMs) and Vcycle (managing VMs at IC and CERN) at Manchester. 7) Operating the GridPP’s site monitoring framework for the Vac and Vcycle managed sites at the request of GridPP. 8) Icecube and LHCb are exploiting the prototype GPU service within grid jobs to run their existing GPU-dependent code. 9) Manchester has continued as one of the UK’s three LHCb T2-D sites with storage. |  |  | A few hardware failures, limited to disks this quarter (WN and SEs) mysql ssl connection problems between voms master and slaves due to openssl update (replication failed)
Note:To get multiple lines per box use Alt-Return (or Ctrl-Return in LibreOffice)
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Manchester | 4 2012 SEs are out of warranty by the end of March. |  |  | We already have a stock of replacement parts to deal with hardware failures.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/Htcondor on at least 1 cluster, 2) Integrate DPM in puppet and abandon YAIM, 3) make storage more robust. 4) Report usage of Vac VMs directly to the central APEL accounting service using its SSM protocol. 5) Develop a tool to analyse the accounting records made by the Vac service 6) Test SEs with failed raid arrays, fix remaining problems, and return them into full service. 7) Start using IPv6. 8) Upgrade Puppet to latest major version. |  |  |  |  | BDII&quarterly report and experiment monitoring
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/Htcondor on at least 1 cluster, 2) Integrate DPM in puppet and abandon YAIM, 3) Test remaining SE with failed raid array, fix remaining problems, and return it into full service. 4) Extend IPv6 to more hosts 5) Upgrade Puppet to latest major version. 6) Report usage of Vac VMs directly to the central APEL accounting service using its SSM protocol. 7) Extend the accounting analysis tool to produce reports automatically as a web page for daily monitoring rather than just as an offline tool 8) Test remaining SE with failed raid array, fix remaining problems, and return it into full service. 9) Update cvmfs puppet module and configuration 10) Set up and test puppet db 11) Look into foreman deployment |  |  |  |  | Quarterly report, BDII, monitoring Reliability and availability measures vs 95% requirement from WLCG
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Alessandra Forti presentations: 20150411, GDB, WLCG Operational Costs 20150414, CHEP '15, Multicore job scheduling in the Worldwide LHC Computing Grid 20150430, GridPP34, ATLAS monitoring evolution for run2 20150430, Gridpp34, WLCG workshop 2015 summary 20150512, GDB, WLCG workshop 2015 summary 20150629, ATLAS S&C week, Distributed Monitoring and accounting (chair) 20150630, LSST meeting, slides for LSST status report
Andrew McNab presentations: "CPU resource provisioning towards 2022", 12 April 2015, WLCG Collaboration meeting, Okinawa "Managing virtual machines with Vac and Vcycle", 13 April 2015, CHEP2015, Okinawa "LHCb experience running jobs in virtual machines", 14 April 2015, CHEP2015, Okinawa "Summary of Track7: Clouds and VMs", 16 April 2015, CHEP2015, Okinawa "HSF Technical Notes status", 17 April 2015, HSF meeting at CHEP2015, Okinawa "LHCb computing going into Run 2", 29 April 2015, GridPP34, London "Making it simpler to provide CPU at Tier-2", 29 April 2015, GridPP34, London
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Alessandra is one of the GridPP representatives and one of the co-chairs of the WLCG Ops Coordination, Atlas monitoring coordinator and member of the atlas distributed computing coordination; Multicore TF co-leader; WLCG workshop 2015 planning committee.
Andrew is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group, the LHCb T2-D co-ordinator, a Grid Expert On Call member of the LHCb distributed computing team, and a member of the WLCG "Machine Features”, "Cloud Traceability” and “Cloud Resource Reporting” task forces. He is currently serving on the CHEP2015 Programme Committee and the HEP Software Foundation interim steering board.
Other outputs and Knowledge |  |  | Date |  | Notes

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 14Q4
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | 80% of old disk servers on sl5 have been drained and reinstalled as sl6 disk servers. Draining helped to reveal and delete many dark data left after a switch to rucio. Other general sysadmin work ( security, heavy workload issues, new certificates etc). |  |  | There was a replacement of doors in computing room in the department and cluster worked at reduced capacity to prevent overheating. There is currently a major refurbishment at the university computer center, so WN's have been moved to the computing room in the department which has limited cooling power. Part of WNs has been switched off. These resulted in low cpu untilisation number.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Grid servers with ipv6 configured still cause lots of problem. |  |  | Wait for gaining more experience and proper instructions for ipv6 configuration
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | 80% of old disk servers on sl5 have been reinstalled as sl6 disk servers. |  |  | 30 June 2015
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Reinstall remaining sl5 machines (argus and disk servers ) as SL6 servers. |  |  | 2015-09-30
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes