## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q215 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 191% | 191% | 190.8% | 358% | 358% | 358.2% | 112% | 112% | 308.1% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 112% | 200% | 319.2%
.x.2 | % of promised (by that time) CPU available | 100% | 1052% | 1052% | 1052% | 469% | 469% | 469.5% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 559% | 472% | 553.6%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 100% | All sites nominal
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 100% | All sites nominal
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 100% | 100% | 13% | 48% | 100% | 100% | 99% | 99% | 95% | [9 empty] | 49% | 50% | 97.5%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 50% | 54% | 60.78% | 33% | 22% | 19.1% | 41% | 50% | 45.69% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 66% | 40% | 34.16%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 46% | 46% | 63.7% | 28% | 19% | 19.8% | 37% | 48% | 33.02% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 47% | 36% | 42.61% | Low wall times appear to be due to Multicore accounting, with much higher CPU usage times being observed at all sites.
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q215
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2015-04-01 | 2015-05-01 | 2015-06-01 | Total |  | Site | 2015-04-01 | 2015-05-01 | 2015-06-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 4372696 | 4139720 | 4950620 | 13463036 |  | DURHAM | 3931832 | 4901156 | 4011664 | 12844652
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 2007984 | 1964404 | 2052640 | 6025028 |  | ECDF | 3371952 | 1740064 | 1135868 | 6247884
[8 empty] | GLASGOW | 12553140 | 12956008 | 18279544 | 43788692 |  | GLASGOW | 12439220 | 11265608 | 7937040 | 31641868
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 18933820 | 19060132 | 25282804 | 63276756 |  | Total | 19743004 | 17906828 | 13084572 | 50734404
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 9677 | 53.424 | 920 | 28 | 1052% | 190.8% | 14.23% | 1.396% | 13463036 | 21.28% | 2184 | 21134568 | 63.7% | 60.78%
ECDF | 14445.2 | 1185.793 | 3077 | 331 | 469.5% | 358.2% | 21.24% | 30.98% | 6025028 | 9.522% | 2184 | 31548316.8 | 19.1% | 19.8%
GLASGOW | 43878 | 2588 | 8287 | 840 | 529.5% | 308.1% | 64.53% | 67.62% | 43788692 | 69.2% | 2184 | 95829552 | 45.69% | 33.02%
Totals | 68000.2 | 3827.217 | 12284 | 1199 | 553.6% | 319.2% | 100% | 100% | 63276756 | 100% | 2184 | 148512436.8 | 42.61% | 34.16%
Please check the figures in the Yellow
| MoU figures taken from S.Lloyds spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 216 | 9676.8 | 53.424 | 2419200 | DURHAM
ECDF | 568 | 43249.024 | 945.793 | 10812256 | ECDF | NOTE: Above ECDF is a combination of ECDF + ECDF-RDF
ECDF-RDF | 0 | 0 | 240 | 0 | ECDF-RDF
GLASGOW | 573 | 43878 | 2588 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q215
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | lz | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | total | fraction used | Site percentage non LHC
DURHAM | 1.4 | 0.1 |  |  |  | 0 | [15 empty] | 7.67 | [11 empty] | 9.17 | 0.4124% | 84.73%
ECDF | 944 | [14 empty] | 1 |  |  |  |  | 0 | [12 empty] | 945 | 42.5% | 0%
GLASGOW | 1252.73 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 1269.158 | 57.08% | 1.215%
Total | 2198.13 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 1 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 2223.328 | 100% | 1.043%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q215
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Oliver Smith | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Durham | Liam Skinner | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.3 | 0.3 | 0.3
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G Qin | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 1 | 1 | 1 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0 | 0 | 0 | 0.5 | 0.5 | 0.5
Total |  | 4.75 | 4.75 | 4.75 | 1.1 | 1.1 | 1.1
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q215
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Finished procurement of new and additonal HW (576 CPU cores) |  | Shared network connection with DiRAC may lead to connectivity issues for the site.
ECDF | Incorporating new Eddie Mk3 facility in Q315 to bolster CPU resources Inclusion of new VOs (LZ and LSST) and early discussion with other experiments (EUCLID) on using Grid resources |  | Challenges ahead in integrating new shared resource Eddie MK3 facility with existing middleware requirements CPU utilisation has reduced at the site - investigations underway into optimising shared cluster resources in advance of new cluster being commissioned
GLASGOW | 1.2PB of storage commisioned and placed into production. Openstack instance moved to dedicated hardware, initial testing taking place. Finished migration to ARC and HTCondor, tested latest version of ARC 5.0 and discovered issues with LRMS and Infirmation systems. |  | Hardware issues with nodes identified to become part of the cloud has slowed deployment. Power cut lead to unanticipated downtime Issues with ARC publishing reduced overall availability & reliability
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Ongoing reduction in manpower at ECDF, no site coverage available when A. Washbrook is on leave. |  | Role advertised last month and looking to fill the post by start of Q415. Passive coverage of site is occasionally provided by Glasgow
Institute or area specific risks
Risk |  | Mitigating Action
Edinburgh: ECDF is a fully costed general purpose compute facility, which has compatibility risk with specialised WLCG requirements |  | Further liaison with the ECDF computing team.
Durham: Issues with site-wide networking, leading to poor connectivity. |  | Closer relationship with Central IT (Networking)
Glasgow: Infrastructure including power, air con and space. |  | Additional funding secured by GU Scotgrid staff to improve both power and air con.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Durham: Procurment of additional WN hardware |  | 2015-06-30 |  | WN have been purchased.
Glasgow: Add 1.2PB of Storage to DPM Pool |  | 2015-06-30 |  | Storage added and fully functional
Glasgow: Bring online production instance of Openstack |  | 2015-06-30 |  | Online and upgraded to Openstack Kilo, hardware issues mean reduced capacity at present
Edinburgh: Fine tuning of multicore workloads to optimise both single core and multi-core job throughput on a shared resource |  | 2015-06-30 |  | Number of slots requested per multicore job was halved. This step has led to multicore jobs being scheduled much faster than before.
Edinburgh: Working with ECDF on continuing integration of analytics tools for resource monitoring |  | 2015-06-30 |  | Work ongoing. ECDF input into this effort has been placed on hold due to the Eddie Mk3 commissioning
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Edinburgh: Eddie Mk3 workload testing and middleware integration |  | 2015-09-30 |  | Initial tests working on new cluster resources.
Edinburgh: Working with ECDF on continuing integration of analytics tools for resource monitoring |  | 2015-09-30 |  | Initial feedback of results from ECDF
Durham: Install new WN hardware |  | 2015-09-30 |  | Hardware on and active
Durham: Contact Central IT regarding IPv6 reverse DNS |  | 2015-09-30 |  | Obtain plans from Central IT
Glasgow: Contact Central IT regarding IPv6 reverse DNS |  | 2015-09-30 |  | Obtain plans from Central IT
Glasgow: Repair Compute Element HW for cloud deployemt |  | 2015-09-30 |  | Working Kilo Openstack instance
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
CHEP 2015 - Evaluation of containers as a virtualisation alternative for HEP workloads (talk presented by A. Washbrook) |  | 13-17/4/2015 |  | A. Washbrook & G. Roy
CHEP 2015 - Development of site-oriented Analytics for Grid computing centres (poster presented by A. Washbrook) |  | 13-17/4/2015 |  | A. Washbrook & D. Crooks
CHEP 2015 - Acceleration of ensemble machine learning methods using many-core devices (poster presented by A. Washbrook) |  | 13-17/4/2015 |  | A. Washbrook
CHEP 2015 - Extending DIRAC File Management with Erasure-Coding for efficient storage (poster presented by S. Skipsey) |  | 13-17/4/2015 |  | S. Skipsey
CHEP 2015 - Enabling Object Storage via shims for Grid Middleware(talk presented by S. Skipsey) |  | 13-17/4/2015 |  | S. Skipsey
GridPP 34 - Graphite & Grafana |  | 2015-04-30 |  | D. Crooks
GridPP 34 - Experiences with Tier-2 operations on shared university resources |  | 2015-04-30 |  | A. Washbrook
GridPP 34 - "Future" Storage |  | 2015-04-30 |  | S. Skipsey
HEPSYSMAN - Bladeroom [invited] |  | 1-3/6/2015 |  | D. Crooks
HEPSYSMAN - OSSEC and Elasticsearch |  | 1-3/6/2015 |  | D. Crooks
HEPSYSMAN - Glasgow Site Report |  | 1-3/6/2015 |  | D. Crooks
HEPSYSMAN - Applications for a Site-oriented Analytics Platform |  | 1-3/6/2015 |  | A. Washbrook
HEPSYSMAN - Edinburgh Site Report |  | 1-3/6/2015 |  | A. Washbrook
HEPiX 2015 - A recent view of OSSEC and Elasticsearch at Scotgrid Glasgow |  | 2015-03-25 |  | D. Crooks (not reported last quarter)
HEPiX 2015 - Evaluation of Memory and CPU usage via Cgroups of ATLAS workloads running at a Tier-2 |  | 2015-03-25 |  | G. Qin & G. Roy (not reported last quarter)
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Cloud Traceability TF |  | Present |  | David Crooks
Member of SQUID Monitoring TF |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
Active members of Multi-core taskforce (representing Scotgrid distributed Tier 2) |  | Present |  | Attended by S. Skipsey
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Co-chair of ATLAS future software and technology forum, |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A