## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q215 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | EFDA JET |  |  | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 25% | 25% | 25% | 168% | 168% | 168% | 118.2% | 118.2% | 220.2% | 259.3% | 259.3% | 259.3% | 288.2% | 288.2% | 288.2% | 291.9% | 291.9% | 291.9% | 583.3% | 583.3% | 583.3% | 257.8% | 257.8% | 262.9%
.x.2 | % of promised (by that time) CPU available | 100% | 828% | 828% | 828% | 281.3% | 281.3% | 281.3% | 678.2% | 678.2% | 678.2% | 285.7% | 285.7% | 285.7% | 307% | 307% | 307% | 351.7% | 442.3% | 442.3% | 2018% | 2018% | 2018% | 357.2% | 395.2% | 395.2%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 94% | 94% | 94% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 99% | 99% | 82% | 82% | 82% | 96.43% | 96.43% | 96.43%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 94% | 94% | 94% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 99% | 99% | 82% | 82% | 82% | 96.43% | 96.43% | 96.43%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | na | na | na | 67% | 67% | 67% |  |  |  | 98% | 98% | 98% | 72% | 72% | 72% | 100% | 100% | 100% | 97% | 97% | 97% | 84.25% | 84.25% | 84.25% | Steve Lloyds test have been broken this quarter
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 2.469% | 2.599% | 7.727% | 87.02% | 88.38% | 91.7% | 15.97% | 19.16% | 16.8% | 75.23% | 59.24% | 41.39% | 51.8% | 68.86% | 63.95% | 63.19% | 38.6% | 49.64% | 0% | 54.54% | 62.54% | 56.06% | 49.53% | 53.51%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 2.244% | 1.969% | 7.387% | 75.04% | 82.93% | 86.17% | 14% | 17.57% | 12.61% | 72.63% | 72.72% | 77.51% | 50.91% | 67.43% | 74.28% | 47.93% | 36.42% | 66.15% | 0% | 60.12% | 113.1% | 47.33% | 47.96% | 64.57%
bi
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q215
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
EFDA JET | EMI2 | EMI3/SL6 |  | 1Gb/s | 1Gb/s | DPM 1.8.8-4 (EMI3) |  | Site | 2015-04-01 | 2015-05-01 | 2015-06-01 | Total |  | Site | 2015-04-01 | 2015-05-01 | 2015-06-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 |  | EFDA JET | 11764 | 114176 | 159948 | 285888 |  | EFDA JET | 13232 | 117952 | 167840 | 299024
Bristol | EMI-2/EMI-3 | EMI 3 |  | 10Gb/s | 1Gb/s | StoRM v1.11.4(EMI-3) |  | Birmingham | 8051500 | 7795120 | 7657256 | 23503876 |  | Birmingham | 8555284 | 8192704 | 8263936 | 25011924
Cambridge | EMI-3 | EMI-3/SL6 |  | 10Gb/s | 2*10Gb/s | DPM 1.8.8-4 (EMI-3) |  | Bristol | 1195352 | 1047844 | 623696 | 2866892 |  | Bristol | 1466836 | 1426628 | 925556 | 3819020
Oxford | EMI 2 | EMI 3/SL6 |  | 10Gb/s | 3*10Gb/s | DPM 1.8.7 (EMI-2) |  | Cambridge | 2046264 | 2214800 | 2051688 | 6312752 |  | Cambridge | 1317752 | 1184096 | 869156 | 3371004
RALPP | UMD2/3 | UMD2/3 |  | 10Gb/s | 10Gb/s | Dcache 2.2 |  | Oxford | 9378420 | 9187708 | 8636368 | 27202496 |  | Oxford | 8586804 | 8148752 | 6682900 | 23418456
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 19567356 | 20691784 | 20010708 | 60269848 |  | RALPP | 15900372 | 17599924 | 11733020 | 45233316
[8 empty] | Sussex | 1465812 | 1691940 | 1727192 | 4884944 |  | Sussex | 1102396 | 970056 | 628344 | 2700796
[8 empty] | Total CPU hrs | 41716468 | 42743372 | 40866856 | 125326696 |  | Total | 36942676 | 37640112 | 29270752 | 103853540
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
EFDA JET | 1772 | 1.5 | 214 | 6 | 828% | 25% | 1.994% | 0.02902% | 285888 | 0.2281% | 2184 | 3870048 | 7.387% | 7.727%
Birmingham | 12489 | 620 | 4439 | 369 | 281.3% | 168% | 14.05% | 11.99% | 23503876 | 18.75% | 2184 | 27275976 | 86.17% | 91.7%
Bristol | 10410 | 218 | 1535 | 99 | 678.2% | 220.2% | 11.71% | 4.217% | 2866892 | 2.288% | 2184 | 22735440 | 12.61% | 16.8%
Cambridge | 3729 | 350 | 1305 | 135 | 285.7% | 259.3% | 4.196% | 6.77% | 6312752 | 5.037% | 2184 | 8144136 | 77.51% | 41.39%
Oxford | 16768 | 1300 | 5461 | 451 | 307% | 288.2% | 18.87% | 25.15% | 27202496 | 21.71% | 2184 | 36621312 | 74.28% | 63.95%
RALPP | 41719 | 2610 | 9433 | 894 | 442.3% | 291.9% | 46.95% | 50.49% | 60269848 | 48.09% | 2184 | 91114296 | 66.15% | 49.64%
Sussex | 1977.32 | 70 | 98 | 12 | 2018% | 583.3% | 2.225% | 1.354% | 4884944 | 3.898% | 2184 | 4318466.88 | 113.1% | 62.54%
Totals | 88864.32 | 5169.5 | 22485 | 1966 | 395.2% | 262.9% | 100% | 100% | 125326696 | 100% | 2184 | 194079674.88 | 64.57% | 53.51%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the KSI2K from gstat July 15 | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
EFDA JET |  | 1475 | 1.47 | 331776 | EFDA JET
Birmingham |  | 12892.8 | 521 | 3223200 | Birmingham
Bristol |  | 10516.08 | 163 | 2629020 | Bristol
Cambridge |  | 3729.024 | 350 | 932256 | Cambridge
Oxford |  | 16786.848 | 1136 | 4196712 | Oxford
RALPP |  | 39560 | 2686 | 9890000 | RALPP
Sussex |  | 2007.552 | 76 | 501888 | Sussex
Totals |  | 86819.408 | 4933.47 | 21704852
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
(cam and ox hae new sl6 hs06 values)
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on B27: gronbech: Extra CPU added 11/3/14
Note on C27: gronbech: 80TB new added and 8TB old removed 3/7/14
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q215
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
EFDA JET | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 11
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 20
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 |  | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 26
Sussex |  | 1 | [8 empty] | 1 | [19 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[43 empty] | 0 | 0
[43 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 1 | 2 | 1 | 0 | 0 | 2 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 2 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 107
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
EFDA JET | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.03319% | 16.43%
Birmingham | 166 | 241 | 0.12 | 0.6 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0.03 |  | 0.53 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 409.851 | 13.97% | 0.6954%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.009 | 1.057% | 0.02257%
Cambridge | 0 | 278.6 | 0 | 0 | 0.1 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279.2 | 9.514% | 0.05014%
Oxford | 0 | 577 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.06 | 0.891 | 0 | 0.625 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 5.34 | 0.018 | 0.016 | 1.5 | 31 | 0 | 0 | 0.0234 | 617.9124 | 21.06% | 6.39%
RALPP | 0 | 528 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 798 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0.027 |  | 0 | 0 | 255 |  | 2 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1585.427 | 54.03% | 0.2792%
Sussex |  | 9 | [8 empty] | 0.008 | [24 empty] | 1 |  |  | 0.176 |  |  |  |  | 10.184 | 0.347% | 11.63%
Total | 166 | 1634.224 | 0.12 | 1.25 | 0.4 | 0.064 | 0 | 0 | 0 | 830.061 | 1.016 | 0 | 0.735 | 0 | 0.125 | 0 | 0 | 0.092 | 0 | 0.534 | 0 | 256.022 | 0 | 2 | 0.6 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 5.34 | 0.018 | 0.016 | 1.676 | 31 | 0 | 0 | 1.0434 | 2934.5574 | 100% | 1.644%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q215
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater |  |  |  | 0.3 | 0.3 | 0.3
| Matt Williams | 0.5 | 0.5 | 0.5
Bristol | Winnie Lacesso |  |  |  | 0.5 | 0.5 | 0.5
| Luke Kreczko |  |  |  | 0.2 | 0.2 | 0.2
Cambridge
| John Hill | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2
Oxford
| Ewan MacMahon | 1 | 1 | 1 | 0 | 0 | 0
| Kashif Mohammad | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
RALPP | Ian Loader | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
| Chris Brew | 0.4 | 0.4 | 0.4 | 0.35 | 0.35 | 0.35
| FedericoMelaccio | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
Sussex | Emyr James | [6 empty] | red text last quarters figures
| Matt Raso-Barnett |  |  |  | 0.3 | 0.3 | 0.3
Jeremy Maris
Total |  | 4.5 | 4.5 | 4.5 | 1.85 | 1.85 | 1.85
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q215
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
EFDA JET | Cluster has been working normally, albeit with low usage. We have the occasional biomed and fusion jobs in batches. We haven't had any additional hardware and none are planned. |  | None – There are no outstanding GGUS tickets against EFDA-JET
Birmingham
Bristol | - deployed HDFS + DMLite storage element (~218 TB) - deployed two new GridFTP servers with 10 Gbit/s NICs each - decommissioned old StoRM SE |  | The accounting (ARC CE -> JURA -> APEL) is reporting an order of magnitude smaller usage than it should (not yet fixed)
Cambridge | New SL6 squid VM set up. CVMFS=>2.1.20. fetch_crl=>v3 on SL5 hosts. Added pilot role for gridpp VO. |  | Outside the quarter, but flooding after a storm took out the University's JANET connection on 17 July. Currently only have 1x10Gbps (rather than 2x) for JANET connection. We were very lucky - we could have been down for weeks,.
Oxford | Decommissioned the last cream ce. This one falls across the end of the quarter boundary a bit; it stopped accepting jobs from real VOs in June, but didn't actually get turned off until July. Published our new simpler cvmfs puppet module that is easier to use and creates new style configuration. Blog post here: http://southgrid.blogspot.co.uk/2015/04/simple-cvmfs-puppet-module.html Used said puppet module in practice to clean up the cmvfs config on all our worker nodes. Redid VO support configuration to enable the use of pilot roles for all the VO supported or planned to be supported by the GridPP Dirac server Changed the supported VOs list removing some old ones and adding cernatschool, na62, hyperk and lsst for compute but not storage. Ewan created a draft text suggesting a GridPP Tier 2 Future Storage project, this has been discussed at the Grid Storage meeting.
RALPP
Sussex | Returned to a period of stable running with good uptime. Begun storage migration to a new Lustre 2.5 filesystem. Currently Grid storage is remaining on the old 1.8.9 filesystem, but we will begin migrating it over in the coming months. |  | No problems currently, but storage will need to be moved over to the new Lustre filesystem, which will require some downtime, probably no more than a day at most.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Deploy ELK log monitoring |  | 2015-09-30
RALPP:Replace cluster top level router |  | 2015-09-30 |  | ongoing
Bristol - quotas and BDII information for new SE (HDFS + DMLite), waiting on software update |  | 2015-09-30
Bristol- split HTCondor services to improve stability of WLCG & local job submission |  | 2015-09-30
Bristol - upgrade ARC CE from 4.2 to 5.X |  | 2015-09-30
Bristol - IP subnet change for 1//4 of Bristol LCG |  | 2015-09-30
Bristol- Fix ARC CE accounting |  | 2015-09-30
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
Landslides |  |  |  | Bristol
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop