## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q315 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 171.7% | 319% | 319% | 381.2% | 381.2% | 381.2% | 142.8% | 142.8% | 142.8% | 305.3% | 305.3% | 305.3% | 212.4% | 212.4% | 212.4% | 246% | 242.3% | 259.5%
.x.2 | % of promised (by that time) CPU available | 100% | 355.5% | 533.9% | 533.9% | 205.5% | 205.5% | 205.5% | 256.1% | 256.1% | 256.1% | 320.7% | 320.7% | 320.7% | 273.1% | 273.1% | 273.1% | 345.4% | 261.9% | 291.1%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 97.6% | 100% | 100%
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 97.6% | 100% | 100%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 89% | 93% | 22% | 77% | 89% | 0% | 96% | 97% | 44% | 95% | 98% | 11% | 50% |  |  | 89.4% | 81.4% | 19.25% | Unreliable test? What relevance at CMS sites?
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 79% | 50.04% | 61.28% | 56.33% | 61.55% | 85.94% | 57.47% | 47.81% | 72.08% | 77.74% | 56.45% | 87.16% | 30.62% | 0.9985% | 7.522% | 59.04% | 64.92% | 74% | CPU time > wall time for several sites (multicore jobs)
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 63.48% | 41.35% | 51.19% | 53.93% | 61.98% | 75.85% | 52.05% | 47.93% | 74.16% | 82.47% | 81.15% | 97.04% | 27.35% | 0.5545% | 5.789% | 51.42% | 59.98% | 70.22%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q315
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 4 Gb/s | DPM |  | SITE | Jul 15 | Aug 15 | Sep 15 | Total |  | SITE | Jul 15 | Aug 15 | Sep 15 | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 14992388 | 12610784 | 15343972 | 42947144 |  | UKI-LT2-Brunel | 19124404 | 13485616 | 18806716 | 51416736
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | Storm |  | UKI-LT2-IC-HEP | 21148892 | 17859208 | 19719496 | 58727596 |  | UKI-LT2-IC-HEP | 24434984 | 19759632 | 22346304 | 66540920
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 4 Gb/s | DPM |  | UKI-LT2-QMUL | 16180472 | 16826724 | 19546908 | 52554104 |  | UKI-LT2-QMUL | 16669944 | 15239336 | 19173344 | 51082624
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 14946744 | 11745160 | 15581084 | 42272988 |  | UKI-LT2-RHUL | 12211652 | 11684196 | 14074756 | 37970604
[8 empty] | UKI-LT2-UCL-HEP | 4896 | 5188 | 246332 | 256416 |  | UKI-LT2-UCL-HEP | 22192 | 25228 | 285768 | 333188
[8 empty] | Total | 67273392 | 59047064 | 70437792 | 196758248 |  | Total | 72463176 | 60194008 | 74686888 | 207344072
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2014, see URL below) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 38000 | 1100 | 7116.84 | 344.8046 | 533.9% | 319% | 29.94% | 14.39% | 42947144 | 21.83% | 2208 | 83904000 | 51.19% | 61.28% | 83.53%
UKI-LT2-IC-HEP | 35068.4 | 2937 | 17064.9 | 770.4745 | 205.5% | 381.2% | 27.63% | 38.41% | 58727596 | 29.85% | 2208 | 77431027.2 | 75.85% | 85.94% | 88.26%
UKI-LT2-QMUL | 32095.44 | 1680 | 12530.606 | 1176.5461 | 256.1% | 142.8% | 25.29% | 21.97% | 52554104 | 26.71% | 2208 | 70866731.52 | 74.16% | 72.08% | 102.9%
UKI-LT2-RHUL | 19730 | 1770 | 6152.802 | 579.7169 | 320.7% | 305.3% | 15.55% | 23.15% | 42272988 | 21.48% | 2208 | 43563840 | 97.04% | 87.16% | 111.3%
UKI-LT2-UCL-HEP | 2006.088 | 159 | 734.5 | 74.8625 | 273.1% | 212.4% | 1.581% | 2.08% | 256416 | 0.1303% | 2208 | 4429442.304 | 5.789% | 7.522% | 76.96%
Totals | 126899.928 | 7646 | 43599.648 | 2946.4046 | 291.1% | 259.5% | 100% | 100% | 196758248 | 100% | 2208 | 280195041.024 | 70.22% | 74% | 94.89%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 5686 | 66902 | 1051.333
UKI-LT2-IC-HEP | 3980 | 35819 | 2846.141
UKI-LT2-QMUL | 4512 | 40318 | 1461
UKI-LT2-RHUL | 2160 | 19730 | 1768
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 162769 | 7126.474 |  | 0
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
https://www.gridpp.ac.uk/deployment/status/reports/GridPP4-Tier-2%20Pledge%20levels-Jan2015.xlsx
Note on E34: gronbech: Gstat displays SI2000 so this needs converting to HS06

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q315
Reported by | Duncan Rand
VOs Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cedar | cernatschool.org | comet.j-parc.jp | cms | dteam | dzero | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | ilc | ipv6.hepix.org | lhcb | lz | mice | na48 | na62.vo.gridpp.ac.uk | neiss.org.uk | ngs.ac.uk | ops | pheno | snoplus.snolab.ca | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | vo.helio-vo.eu | vo.landslides.mossaic.org | vo.londongrid.ac.uk | zeus | Total
UKI-LT2-Brunel | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 1 | 1 | 21
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 23
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 22
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 15
UKI-LT2-UCL-HEP | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Total | 1 | 5 | 4 | 2 | 3 | 1 | 1 | 1 | 4 | 5 | 2 | 1 | 2 | 1 | 4 | 3 | 2 |  | 1 | 4 | 1 | 4 | 1 | 1 | 1 | 1 | 5 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 3 | 84
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | lz | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.364 |  | 0.24 |  |  |  | 0.052 | 628.504 |  | 39.91 | 0.014 | 0.003 |  |  |  |  | 1.691 | [6 empty] | 0.005 |  |  |  |  | 0.003 | [6 empty] | 0.019 |  |  | 670.805 | 15.05% | 0.3564%
UKI-LT2-IC-HEP |  | 29.84 | 0 |  | 0 |  | 0 | 1125.355 |  | 12.267 |  |  |  |  | 86.471 |  |  |  | 0 | [10 empty] | 7.479 |  |  |  |  | 5.553 |  |  | 17.254 | 1284.219 | 28.82% | 4.682%
UKI-LT2-QMUL |  | 84 | 0.741 |  |  |  |  | 0.843 |  | 1100 | 0.046 | [5 empty] | 0.673 | 0.0068 |  |  |  | 0.016 |  | 0.001 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 5.2 |  |  |  |  | 1191.551 | 26.74% | 7.613%
UKI-LT2-RHUL | 1.323 |  | 0.417 |  |  |  |  | 7.284 |  | 1294.376 | 0.13 | 0.002 |  |  |  |  | 0.431 | [6 empty] | 0.005 | [6 empty] | 0.01 | 1.294 | [6 empty] | 1305.272 | 29.29% | 0.2767%
UKI-LT2-UCL-HEP | 0.735 | [8 empty] | 4 | [28 empty] | 4.735 | 0.1062% | 15.52%
Total | 2.422 | 113.84 | 1.398 | 0 | 0 | 0 | 0.052 | 1761.986 | 0 | 2450.553 | 0.19 | 0.005 | 0 | 0 | 86.471 | 0 | 2.795 | 0.0068 | 0 | 0 | 0 | 0.016 | 0 | 0.011 | 0 | 0 | 0 | 0 | 0.0082 | 7.479 | 0.01 | 1.294 | 0.019 | 5.2 | 5.553 | 0.019 | 0 |  | 4456.582 | 100% | 3.536%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q315
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3
| Ivan Reid | 0.7 | 0.7 | 0.7 | 0.15 | 0.15 | 0.15
| P. Hobson | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
| R. Powell | Unfunded Month 1: 0.25; Unfunded Month 2: 0.25; Unfunded Month 3: 0.25
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Abdulkadir Farah | bar: Unfunded Month 1 to Unfunded Month 3
Duncan Rand | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| David Colling, Ray Beuselinck | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| network team + Alex Owen/Cozmin | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| B.Green/Tom | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 7.4 | 7.4 | 7.4 | 2.25 | 2.25 | 2.25

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q315
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel
UKI-LT2-IC-HEP | Increased support for lz and comet VOs.
UKI-LT2-QMUL | New member of staff, Terry Froy, started on 6th July. He has also provided assistance to the Universities core network team when requested (e.g. during clearing). Completed installation, configuration and tuning of new Lustre, including High Availability for the Meta data server. It is now, in principle, ready to go live once rsync of data has completed. Decommissioned more old Dell 1950 storage (90TB), 90TB left. Started investigation of new batch system (SLURM) as likely replacement of gridengine. Have added a prototype GPU system (~0.6TFLOPS double precision performance) to batch system and intend to make available on the grid once cream software can take advantage. Identified significant configuration issues with IPV6 for CERN pilot factories, discussed in detail in hepix IPV6 working group. Attended gripp35 meeting and we gave talk on how QMUL have implemented IPV6. Terry found bug in RHEL 6 kernel related to "bonding regression when using MACADDR= in ifcfg-bondX'" and has been reported upstream Red Hat Bug 1252524
UKI-LT2-RHUL | - Setting up firewall to use 10GB link
UKI-LT2-UCL-HEP | Being phased out.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insufficient man-power at major sites (i.e. Imperial, Brunel, QMUL and RHUL) |  | Imperial, Brunel and QMUL (but not RHUL) now with at least 2 sys-admins
Insitute or area specific risks
Risk |  | Mitigating Action
Insufficient man-power at UCL |  | Assistance is given where possible.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
UKI-LT2-Brunel: GPU 2014 workshop |  |  |  | https://agenda.infn.it/conferenceDisplay.py?confId=7534
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes