## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q3 2015 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 200% | 250% | 253.6% | 210% | 210% | 213.4% | 140% | 130% | 134.1% | 184% | 178% | 227.6% | 196.2%
.x.2 | % of promised (by that time) CPU available | 100% | 542% | 599% | 666.2% | 411% | 411% | 410.5% | 426% | 395% | 395.4% | 560% | 561% | 563.9% | 498.7%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ??
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ??
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 99% | 97% | 6% | NA | 0.5% | 0% | 97% | 0% | 0% | 100% | 33% | 10% | 4% | ??
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 24% | 25% | 20.35% | 63% | 63% | 64.83% | 76% | 51% | 61.49% | 33% | 15% | 23.43% | 40.71%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 36% | 26% | 33.21% | 66% | 73% | 71.88% | 70% | 72% | 71.07% | 30% | 31% | 32.8% | 51.22%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2015
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Site | 2015-07-01 | 2015-08-01 | 2015-09-01 | Total |  | Site | 2015-07-01 | 2015-08-01 | 2015-09-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 13209344 | 14991052 | 5584036 | 33784432 |  | Lancaster | 6618400 | 10214624 | 3873148 | 20706172
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 11346708 | 7830804 | 8341244 | 27518756 |  | Liverpool | 9877120 | 7155260 | 7787844 | 24820224
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 24808092 | 13889784 | 17653488 | 56351364 |  | Manchester | 11945456 | 15912444 | 20893736 | 48751636
[7 empty] | Sheffield | 3136112 | 2697844 | 3629068 | 9463024 |  | Sheffield | 1764816 | 2046096 | 2948024 | 6758936
[7 empty] | Total CPU hrs | 49364144 | 36711640 | 31578768 | 117654552 |  | Total | 30205792 | 35328424 | 35502752 | 101036968
Current Resources Available | [6 empty] | Everyone has CPU-hours > Wall Clock Hours again. Numbers from the “normal” accounting portal.
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 46080 | 2140 | 6917 | 844 | 666.2% | 253.6% | 41% | 43.43% | 33784432 | 26.58% | 2208 | 101744640 | 33.21% | 20.35%
Liverpool | 17339 | 783 | 4224 | 367 | 410.5% | 213.4% | 15.43% | 15.89% | 27518756 | 21.65% | 2208 | 38284512 | 71.88% | 64.83%
Manchester | 35910 | 1370 | 9081 | 1022 | 395.4% | 134.1% | 31.95% | 27.8% | 56351364 | 44.33% | 2208 | 79289280 | 71.07% | 61.49%
Sheffield | 13066 | 635 | 2317 | 279 | 563.9% | 227.6% | 11.63% | 12.89% | 9463024 | 7.444% | 2208 | 28849728 | 32.8% | 23.43%
Totals | 112395 | 4928 | 22539 | 2512 | 498.7% | 196.2% | 100% | 100% | 127117576 | 100% | 2208 | 248168160 | 51.22% | 40.71%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 46080 | 2140 | NA | Lancaster
Liverpool | 1383 | 17337 | 784 | NA | Liverpool
Manchester | 3646 | 35910 | 1370 | NA | Manchester
Sheffield | 1071 | 13066 | 635 | NA | Sheffield
Totals | 9300 | 112393 | 4929 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2015
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | esr | epic | fusion | geant4 | gridpp | hone | ilc | lhcb | LLST | mice | magic | na48 | neiss | ops | pheno | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 21
Liverpool | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 31
Manchester |  | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 17
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  | 1 | 0 | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 18
Total | 2 | 4 | 1 | 4 | 1 | 3 | 2 | 1 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 4 | 3 | 3 | 4 | 1 | 2 | 2 | 1 |  | 4 | 4 | 3 | 1 | 1 | 4 | 2 | 3 | 4 |  | 87
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 930 | 0.13 | 16 | 6 | 952.13 | 1.68% | 2.324%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3100.24 | 0.7 | 178 | 13.47 | 3400.59 | 5.234% | 5.651%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2015
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | 1 | 1 | 1
| M. Doidge | 1 | 1 | 1
| P. Love |  |  |  | 0.3 | 0.3 | 0.3
Liverpool | S. Jones | 1 | 1 | 1
| R. Fay |  |  |  | 0.5 | 0.5 | 0.5
| J. Bland |  |  |  | 0.5 | 0.5 | 0.5
Manchester | A. Forti | 1 | 1 | 1
| R. Frank | 1 | 1 | 1
| A. McNab |  |  |  | 0.5 | 0.5 | 0.5
Sheffield | E. Korolkova | 0.5 | 0.5 | 0.5
| M. Robinson |  |  |  | 0.1 | 0.1 | 0.1
Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | 0.5 | 0.5 | 0.5
Manchester | A. Forti |  |  |  | 1 | 1 | 1

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q3
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Network “Polishing” New VM Infrastructure Cluster reinstall University hardware purchase | “Something” fixed the perfsonar problems. New Vms in production, some old Vms migrated. Cluster refreshed. Extra compute online, extra storage for us in the rack. |  |  | We're not sure what actually fixed it. Our CE migration wasn't so smooth. A few days downtime to get rid of teething problems. None.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | glexec has become increasing relevant, but no solution yet. Complications during our infrastructure refresh has delayed bringing online new Ces. Still no IPv6. |  |  | Working towards a relocatable solution. Almost ready to be commissioned. IPv6 movement means that we should be able to have dual-stacked by Christmas.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Move to new Infrastructure. Solved one long-standing site-issue (perfsonar). Overcame several large scale failures in September. Good metrics for July/August. |  |  | 1/9/2015 1/9/2015 30/9/2015 31/8/2015 |  | Increased reliability as kit goes out of warranty. Sensible perfsonar outputs. Overcame a complete network failure. Jobs flowed for 2/3 of the quarter.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Dual Home Perfsonar by Christmas Increase CE resiliance. Glexec (or a similar solution) on nodes LSST enabled and operating, other VO dirac jobs too. |  |  | 30/9/15 30/9/15 3/8/15 |  | IPv6 mesh engagement Restore our metrics. “proper” pilot jobs, dirac using VO support Always fun to have more Vos.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q3
Reported by | S Jones
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Security HM Maint SW Maint Operations Tickets... (cont) Conference User Support and docs New monitoring tech Power | Kernel updates, CVE-2615-3245/6 (libuser) PSUs, PDUs, Disk (badblocks), Arc/BDII/Openladap2.4.40..., new badblocks proc. SRM Cleanup, 116918 (stale bdii), 116507 (VOMS dzero), 116783 (bdii), 115449(lcg-tags) GRID35 (venue, food, dinner. accom, NW, power ...) VO docs, NA62 help, LSST, LZ (new VOs) Sensu trial, Maui monitor Several outages for power upgrades |  | None None Rollback is always risky Some TBs reclaimed but still much dark data remains Routine Routine Much risk, but worked out OK in the end None None Overruns required replanning.
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | IPV6 Centos7/SL7 |  | Reminder requested on status (21/10/2015) Make a build baseline for a simple server (BDII?)
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | CSD Cluster Share + Explore Cloud Technologies VAC, (VCYCLE?) IPV6 Test System Successful host of GRIDPP35 |  | 30/09/2015 30/09/2015 12/09/2015 |  | VAC jobs (slipped). Will progress. Still awaiting allocation. Nudge sent. Completed.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | CSD Cluster Share + Explore Cloud Technologies VAC, (VCYCLE?) IPV6 Test System Start of Usability Tests for 'Guest Experiment' documentation SL7 Tests |  | 31/12/2015 31/12/2015 31/12/2015 31/12/2015 |  | Get some VAC jobs running. Allocation with Test System up. Report to be filed. Get a SL7 baseline made.

## Manchester
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q3
Reported by | A. Forti
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Manchester | VAC development Storage maintainance Storage operations LSST grid integration | - Continued development and running of Vac (318 VMs) and Vcycle (managing VMs at IC and CERN) at Manchester - Began reporting all Vac usage information directly via APEL SSM protocol - Deployed Vac-in-a-Box on a production testbed at Manchester, before helping with conversion of UCL to a Vac-in-a-Box based site - Operating GridPP’s site monitoring framework for the Vac and Vcycle managed sites at the request of GridPP - Icecube and LHCb are exploiting the prototype GPU service within grid jobs to run their existing GPU-dependent code - Manchester has continued as one of the UK’s three LHCb T2-D sites with storage - LSST/DESC jobs running on 3 sites in the UK analysing data imported on Manchester storage - Adapt backup to external storage - Automatize DPM DB and storage comparison to allow for more frequent problem spotting |  |  | - A few hdd failures - Raid failure in one SE due to raid controller loosing connection to enclosure - Uneven distribution of data caused high load on data servers and caused job failures and DB-disk records out of sync.
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  |  | Mitigating Action
Manchester | - 2012 SEs are out of warranty by the end of March. |  |  | Stocked replacement parts
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/Htcondor on at least 1 cluster, 2) Integrate DPM in puppet and abandon YAIM, 3) Test remaining SE with failed raid array, fix remaining problems, and return it into full service. 4) Extend IPv6 to more hosts 5) Upgrade Puppet to latest major version. 6)Add APEL-Sync records to Vac usage reporting to pass the EGI APEL SAM tests 7) Extend the accounting analysis tool to produce reports automatically as a web page for daily monitoring rather than just as an offline tool 8) Update cvmfs puppet module and configuration 9) Set up and test puppet db 10) Look into foreman deployment |  |  |  |  | 1) In progress 2) In progress 3) In progress 4) Not done 5) Done 6) In progress 7) In progress 8) Done 9) Done 10) In progress
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/Htcondor on at least 1 cluster, 2) Integrate DPM in puppet and abandon YAIM, 3) Test remaining SE with failed raid array, fix remaining problems, and return it into full service. 4) Extend IPv6 to more hosts 6)Add APEL-Sync records to Vac usage reporting to pass the EGI APEL SAM tests 7) Extend the accounting analysis tool to produce reports automatically as a web page for daily monitoring rather than just as an offline tool 8) Look into foreman deployment 9) Improve local tools to balance data servers 10) Test ATLAS consistency tools |  |  | 31/12/2015 31/12/2015 31/12/2015 31/12/2015 |  | Get some VAC jobs running. Allocation with Test System up. Report to be filed. Get a SL7 baseline made.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs.
Working with LSST users to adapt their workflow to use grid resources
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Alessandra Forti presentations LSST status report, GridPP35 Infrastructure consolidation session co-chair, ATLAS S&C |  |  | 10/09/2015, 22/09/2015
Andrew McNab presentations “Vac, Vcycle, VMs status”, LHCb Computing Workshop, CERN, “HSF Technical Notes”, HEP Software Foundation Interim Foundation Board, “Processing CERN data on OpenStack”, Manchester OpenStack meeting, SpacePortX Manchester, “Vac, Vcycle, and Vac-in-a-Box”, GridPP35 Conference, Liverpool, “Batch and Cloud overview”, UK T0 Meeting, RAL, |  |  | 20/5/2015 24/6/2015 8/9/2015 11/9/2015 20/10/2015
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Alessandra is one of the GridPP representatives and one of the co-chairs of the WLCG Ops Coordination, Atlas monitoring coordinator and member of the atlas distributed computing coordination; Multicore TF co-leader; WLCG workshop 2016 planning committee.
Andrew is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group, the LHCb T2-D co-ordinator, a Grid Expert On Call member of the LHCb distributed computing team, and a member of the WLCG "Machine Features”, "Cloud Traceability”, “Cloud Resource Reporting”, and “Information Systems Evolution" task forces. He is currently serving during the final stages of the CHEP2015 Programme Committee, and on the HEP Software Foundation interim steering board. During this quarter he began leading GridPP’s Tier-2 Evolution Task Force to implement the plan of GridPP5 to radically simplify the operation of Tier-2 sites.
Other outputs and Knowledge |  |  | Date |  | Notes

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 15Q3
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | All remaining sl5 machines but one big disk server have been reinstalled as sl6 servers. Site abailability for ATLAS in Q3 is 98%, ASAP metric is 96% .Other general sysadmin work (security, new certificates, bad worker nodes etc). Cloud support work. |  |  | Draining disk servers takes long time, so one big disk servers is left to drain and reinstall. This also tricky as we need to find space for draining. We have old worker nodes (8 of them are 6 core machines) which are currently not used. This is causing low utilisation of cpu hours.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Moving gris servers toipv6 configured may cause lots of problem. |  |  | Wait for gaining more experience and proper instructions for ipv6 configuration
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | All sl5 machines but one big disk server have been reinstalled as sl6 disk servers. |  |  | 30 September 2015
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Reinstall remaining one sl5 machines disk servers as SL6 servers. Reconfigure perfsonar server as ipv6 machine. |  |  | 2015-12-30
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes