## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q315 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | EFDA JET |  |  | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 25% | 25% | 21.43% | 168% | 168% | 140.3% | 118.2% | 220.2% | 205.7% | 259.3% | 259.3% | 239.7% | 288.2% | 288.2% | 266.4% | 291.9% | 291.9% | 278% | 583.3% | 583.3% | 538.5% | 257.8% | 262.9% | 241.5%
.x.2 | % of promised (by that time) CPU available | 100% | 828% | 828% | 630.6% | 281.3% | 281.3% | 248.5% | 678.2% | 678.2% | 526.8% | 285.7% | 285.7% | 212.4% | 307% | 307% | 234.1% | 442.3% | 442.3% | 334.6% | 2018% | 2018% | 1521% | 395.2% | 395.2% | 308.6%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 94% | 94% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 99% | 99% | 100% | 82% | 82% | 96% | 96.43% | 96.43% | 99.29%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 94% | 94% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 99% | 99% | 100% | 82% | 82% | 96% | 96.43% | 96.43% | 99.29%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | na | na | na | 67% | 67% |  |  |  |  | 98% | 98% |  | 72% | 72% |  | 100% | 100% |  | 97% | 97% |  | 84.25% | 84.25% |  | Steve Lloyds test have been broken this quarter
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 2.599% | 7.727% | 7.323% | 88.38% | 91.7% | 89.53% | 19.16% | 16.8% | 19.3% | 59.24% | 41.39% | 48.53% | 68.86% | 63.95% | 66.01% | 38.6% | 49.64% | 68.44% | 54.54% | 62.54% | 65.6% | 49.53% | 53.51% | 63.07%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 1.969% | 7.387% | 4.793% | 82.93% | 86.17% | 82.26% | 17.57% | 12.61% | 17.06% | 72.72% | 77.51% | 70.4% | 67.43% | 74.28% | 68.94% | 36.42% | 66.15% | 72.51% | 60.12% | 113.1% | 114.4% | 47.96% | 64.57% | 66.2%
bi
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q315
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
EFDA JET | EMI2 | EMI3/SL6 |  | 1Gb/s | 1Gb/s | DPM 1.8.8-4 (EMI3) |  | Site | 2015-07-01 | 2015-08-01 | 2015-09-01 | Total |  | Site | 2015-07-01 | 2015-08-01 | 2015-09-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 |  | EFDA JET | 48328 | 4940 | 134248 | 187516 |  | EFDA JET | 88096 | 17804 | 180600 | 286500
Bristol | EMI-2/EMI-3 | EMI 3 |  | 10Gb/s | 1Gb/s | StoRM v1.11.4(EMI-3) |  | Birmingham | 7445500 | 7649832 | 7587552 | 22682884 |  | Birmingham | 7842248 | 8535696 | 8310404 | 24688348
Cambridge | EMI-3 | EMI-3/SL6 |  | 10Gb/s | 2*10Gb/s | DPM 1.8.8-4 (EMI-3) |  | Bristol | 968088 | 1324520 | 1628380 | 3920988 |  | Bristol | 1202552 | 1516344 | 1717732 | 4436628
Oxford | EMI 2 | EMI 3/SL6 |  | 10Gb/s | 3*10Gb/s | DPM 1.8.7 (EMI-2) |  | Cambridge | 2143012 | 1455264 | 2198292 | 5796568 |  | Cambridge | 1110620 | 1110812 | 1774044 | 3995476
RALPP | UMD2/3 | UMD2/3 |  | 10Gb/s | 10Gb/s | Dcache 2.2 |  | Oxford | 9550924 | 8080116 | 7891512 | 25522552 |  | Oxford | 8559332 | 8429792 | 7450552 | 24439676
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 24920892 | 17795440 | 24077788 | 66794120 |  | RALPP | 23106916 | 16526856 | 23411060 | 63044832
[8 empty] | Sussex | 1896512 | 1722248 | 1375296 | 4994056 |  | Sussex | 651036 | 828404 | 1384784 | 2864224
[8 empty] | Total CPU hrs | 46973256 | 38032360 | 44893068 | 129898684 |  | Total | 42560800 | 36965708 | 44229176 | 123755684
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
EFDA JET | 1772 | 1.5 | 281 | 7 | 630.6% | 21.43% | 1.994% | 0.02902% | 187516 | 0.1444% | 2208 | 3912576 | 4.793% | 7.323%
Birmingham | 12489 | 620 | 5026 | 442 | 248.5% | 140.3% | 14.05% | 11.99% | 22682884 | 17.46% | 2208 | 27575712 | 82.26% | 89.53%
Bristol | 10410 | 218 | 1976 | 106 | 526.8% | 205.7% | 11.71% | 4.217% | 3920988 | 3.018% | 2208 | 22985280 | 17.06% | 19.3%
Cambridge | 3729 | 350 | 1756 | 146 | 212.4% | 239.7% | 4.196% | 6.77% | 5796568 | 4.462% | 2208 | 8233632 | 70.4% | 48.53%
Oxford | 16768 | 1300 | 7163 | 488 | 234.1% | 266.4% | 18.87% | 25.15% | 25522552 | 19.65% | 2208 | 37023744 | 68.94% | 66.01%
RALPP | 41719 | 2610 | 12468 | 939 | 334.6% | 278% | 46.95% | 50.49% | 66794120 | 51.42% | 2208 | 92115552 | 72.51% | 68.44%
Sussex | 1977.32 | 70 | 130 | 13 | 1521% | 538.5% | 2.225% | 1.354% | 4994056 | 3.845% | 2208 | 4365922.56 | 114.4% | 65.6%
Totals | 88864.32 | 5169.5 | 28800 | 2141 | 308.6% | 241.5% | 100% | 100% | 129898684 | 100% | 2208 | 196212418.56 | 66.2% | 63.07%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the KSI2K from gstat July 15 | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
EFDA JET |  | 1475 | 1.47 | 331776 | EFDA JET
Birmingham |  | 12892.8 | 521 | 3223200 | Birmingham
Bristol |  | 10516.08 | 163 | 2629020 | Bristol
Cambridge |  | 3729.024 | 350 | 932256 | Cambridge
Oxford |  | 16786.848 | 1136 | 4196712 | Oxford
RALPP |  | 39560 | 2686 | 9890000 | RALPP
Sussex |  | 2007.552 | 76 | 501888 | Sussex
Totals |  | 86819.408 | 4933.47 | 21704852
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
(cam and ox hae new sl6 hs06 values)
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q315
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
EFDA JET | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 11
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 20
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 |  | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 26
Sussex |  | 1 | [8 empty] | 1 | [19 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[43 empty] | 0 | 0
[43 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 1 | 2 | 1 | 0 | 0 | 2 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 2 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 107
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
EFDA JET | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.03613% | 16.43%
Birmingham | 127 | 240 | 0.12 | 0.44 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0.13 | 0.02 |  | 0.53 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 369.871 | 13.72% | 0.7759%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.009 | 1.15% | 0.02257%
Cambridge | 0 | 262.9 | 0 | 0 | 0.1 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 |  | 0 | 0 | 0.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263.63 | 9.778% | 0.1024%
Oxford | 0 | 577 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.06 | 0.891 | 0 | 0.625 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 5.34 | 0.018 | 0.016 | 1.5 | 31 | 0 | 0 | 0.0234 | 617.9124 | 22.92% | 6.39%
RALPP | 0 | 429 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 719 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 250 |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1402.6 | 52.02% | 0.328%
Sussex |  | 9 | [8 empty] | 0.008 | [24 empty] | 1 |  |  | 0.176 |  |  |  |  | 10.184 | 0.3777% | 11.63%
Total | 127 | 1518.524 | 0.12 | 1.09 | 0.4 | 0.064 | 0 | 0 | 0 | 751.061 | 1.016 | 0 | 0.635 | 0 | 0.025 | 0 | 0.26 | 0.055 | 0 | 0.534 | 0 | 251.022 | 0 | 2 | 1 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 5.34 | 0.018 | 0.016 | 1.676 | 31 | 0 | 0 | 1.0434 | 2696.1804 | 100% | 1.802%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q315
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater |  |  |  | 0.3 | 0.3 | 0.3
| Matt Williams | 0.5 | 0.5 | 0.5
Bristol | Winnie Lacesso |  |  |  | 0.5 | 0.5 | 0.5
| Luke Kreczko |  |  |  | 0.2 | 0.2 | 0.2
Cambridge
| John Hill | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2
Oxford
| Ewan MacMahon | 1 | 1 | 1 | 0 | 0 | 0
| Kashif Mohammad | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
RALPP | Ian Loader | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
| Chris Brew | 0.4 | 0.4 | 0.4 | 0.35 | 0.35 | 0.35
| FedericoMelaccio | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
Sussex | Emyr James | [6 empty] | red text last quarters figures
| Matt Raso-Barnett |  |  |  | 0.3 | 0.3 | 0.3
Jeremy Maris
Total |  | 4.5 | 4.5 | 4.5 | 1.85 | 1.85 | 1.85
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q315
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
EFDA JET | Cluster has been working OK. Generally usage has been very low with mostly only biomed jobs. Now that the fusion VO is disbanded, there are no fusion jobs. |  | There is one outstanding ticket, raised by a user in the biomed VO. The problem seems to be on the user's side (DNS issues), as tests from other uesrs' from the same site seems to be OK.
Birmingham
Bristol | The Bristol IP subnet change for 1/4 of site was done successfully. |  | The accounting (ARC CE -> JURA -> APEL) is reporting an order of magnitude smaller usage than it should (not yet fixed)
Cambridge | Site moved to new Data Centre. UI upgraded to SL6/EMI-3. perSonar updated to 3.5 |  | Few teething problems after move to Data Centre: two power events, network connection flaky on occasions.
Oxford | Oxford suffered from three ~hour long outages of the A/C. Unfortunately this reulted in down timeof a few days and reduced capacity for several weeks. Also, we started developing the future Tier 2 storage plan with the storage group, we went to the GridPP 34 meeting and presented on IPv6 and led a discussion of multi-Vo pilots, and joined the Tier 2 Evolution Working Group at Andy's invitation. We continued to contribute to the Hepix IPv6 working group, including the diagnosis of the problems with CERN's ATLAS pilot factories, and making our test ARC CE dual stack. We carried out some cross site support when Cambridge had their flooding incident (which mainly means that I marked the site in downtime in the gocdb and sent John friendly emails). We finally retired our last Cream CE and torque server (we got most of it done in June, but it got finally turned off just into July). We had a meeting with Matthew Mottram about moving SNO+ to the Imperial Dirac We rationalised our supported VO list, including adding support for LSST, HyperK, NA62 and CernAtSchool, and rolled out full support for glExec for all VOs to support the move to the Dirac WMS (what was it Daniela called us? 'An exemplar site'?)
RALPP | Deplyed a couple of dCache Security updates Started deploying ELK Added pilot role for gridpp (all) VOs Decommisioned the RALPP VO
Sussex | Working on setting up new Storm SE to work with new Lustre 2.5.3 filesystem |  | Matt leaving Sussex in December, so replacement will need to be brought up to speed. Matt is working on finishing off ongoing projects to site is stable before leaving.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol - IP subnet change for 1//4 of Bristol LCG |  | 2015-09-30 |  | Done
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Deploy ELK log monitoring |  | 2015-09-30 |  | Started
RALPP:Replace cluster top level router |  | 2015-09-30 |  | Awaiting deployment by RAL networking
RALPP:Support more minor VOs (inc snoplus) |  | 2015-11-30
RALPP:Update HyperVisor cluster to Windows 2012RC2 |  | 2015-11-30
Bristol - quotas and BDII information for new SE (HDFS + DMLite), waiting on software update |  | 03/31/2016
Bristol- split HTCondor services to improve stability of WLCG & local job submission |  | 03/31/2016
Bristol - upgrade ARC CE from 4.2 to 5.X |  | 03/31/2016
Bristol- Fix ARC CE accounting |  | 03/31/2016
Bristol- Consolidation of Puppet infrastructure to synchronise with local IT team. |  | 03/31/2016
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
Landslides |  |  |  | Bristol
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop