## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q415 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 319% | 319% | 319% | 381.2% | 381.2% | 381.2% | 142.8% | 142.8% | 246.5% | 305.3% | 305.3% | 305.3% | 212.4% | 212.4% |  | 259.5% | 259.5% | 303.2%
.x.2 | % of promised (by that time) CPU available | 100% | 533.9% | 533.9% | 533.9% | 205.5% | 205.5% | 205.5% | 256.1% | 256.1% | 302.4% | 320.7% | 320.7% | 320.7% | 273.1% | 273.1% |  | 291.1% | 291.1% | 304.9%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 99% | 100% |  | 99.8% | 99.8% | 99.75%
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 99% | 100% |  | 99.8% | 99.8% | 99.75%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 93% | 22% |  | 89% | 0% |  | 97% | 44% |  | 98% | 11% |  |  |  |  | 94.25% | 19%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 50.04% | 61% | 64.67% | 61.55% | 86% | 91.92% | 47.81% | 72% | 41.89% | 56.45% | 87% | 71.12% | 0.9985% | 8% |  | 52.88% | 74% | 66.35% | CPU time > wall time for several sites (multicore jobs)
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 41.35% | 51% | 50.16% | 61.98% | 76% | 83.62% | 47.93% | 74% | 40.86% | 81.15% | 97% | 85.74% | 0.5545% | 6% |  | 54.26% | 70% | 61.82%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q415
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 4 Gb/s | DPM |  | SITE | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total |  | SITE | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 16308684 | 15993612 | 9786020 | 42088316 |  | UKI-LT2-Brunel | 20034788 | 21491108 | 12732504 | 54258400
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | Storm |  | UKI-LT2-IC-HEP | 21285484 | 22902348 | 20562836 | 64750668 |  | UKI-LT2-IC-HEP | 23075376 | 24999704 | 23101620 | 71176700
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 4 Gb/s | DPM |  | UKI-LT2-QMUL | 13951120 | 10385528 | 9851560 | 34188208 |  | UKI-LT2-QMUL | 13901736 | 11098432 | 10046764 | 35046932
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 13423096 | 14315456 | 9614656 | 37353208 |  | UKI-LT2-RHUL | 8781156 | 10871280 | 11329792 | 30982228
[8 empty] | Total | 64968384 | 63596944 | 49815072 | 178380400 |  | Total | 65793056 | 68460524 | 57210680 | 191464260
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 38000 | 1100 | 7116.84 | 344.8046 | 533.9% | 319% | 29.08% | 12.63% | 42088316 | 23.59% | 2208 | 83904000 | 50.16% | 64.67% | 77.57%
UKI-LT2-IC-HEP | 35068.4 | 2937 | 17064.9 | 770.4745 | 205.5% | 381.2% | 26.83% | 33.73% | 64750668 | 36.3% | 2208 | 77431027.2 | 83.62% | 91.92% | 90.97%
UKI-LT2-QMUL | 37890.25 | 2900 | 12530.606 | 1176.5461 | 302.4% | 246.5% | 28.99% | 33.31% | 34188208 | 19.17% | 2208 | 83661672 | 40.86% | 41.89% | 97.55%
UKI-LT2-RHUL | 19730 | 1770 | 6152.802 | 579.7169 | 320.7% | 305.3% | 15.1% | 20.33% | 37353208 | 20.94% | 2208 | 43563840 | 85.74% | 71.12% | 120.6%
UKI-LT2-UCL-HEP
Totals | 130688.65 | 8707 | 42865.148 | 2871.5421 | 304.9% | 303.2% | 100% | 100% | 178380400 | 100% | 2208 | 288560539.2 | 61.82% | 66.35% | 93.17%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 4886 | 58056 | 1051.333
UKI-LT2-IC-HEP | 3980 | 35819 | 2846.599
UKI-LT2-QMUL | 4512 | 40318 | 2768.5
UKI-LT2-RHUL | 2160 | 19730 | 1746
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 153923 | 8412.432
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
Note on E34: gronbech: Gstat displays SI2000 so this needs converting to HS06

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q415
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cedar | cernatschool.org | comet.j-parc.jp | cms | dteam | dzero | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | ilc | ipv6.hepix.org | lhcb | lz | mice | na48 | na62.vo.gridpp.ac.uk | neiss.org.uk | ngs.ac.uk | ops | pheno | snoplus.snolab.ca | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | vo.helio-vo.eu | vo.landslides.mossaic.org | vo.londongrid.ac.uk | zeus | Total
UKI-LT2-Brunel | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 1 | 1 | 21
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 23
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 22
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 15
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 1 | 4 | 4 | 2 | 3 | 1 | 1 | 1 | 4 | 4 | 2 | 1 | 2 | 1 | 4 | 3 | 2 |  | 1 | 4 | 1 | 4 | 1 | 1 | 1 | 1 | 4 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 3 | 81
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.364 |  | 0.286 |  |  |  | 0.053 | 651.431 |  | 39.098 | 0.014 | 0.003 |  |  |  |  | 1.691 | [6 empty] | 0.005 |  |  |  |  | 0.003 | [6 empty] | 0.019 |  | 0 |  | 692.967 | 15.26% | 0.3518%
UKI-LT2-IC-HEP |  | 30.294 | 0 |  | 0 |  | 0 | 1171.6645 |  | 9.939 |  |  |  |  | 123.69 |  |  |  | 0 | [15 empty] | 8.262 |  |  | 58.275 | 17.685 | 1419.8095 | 31.26% | 8.066%
UKI-LT2-QMUL |  | 71 | 0.827 |  |  |  |  | 0.843 |  | 1100 | 0.46 | [5 empty] | 0.673 | 0.0068 |  |  |  | 0.016 | 0.012 | 0.001 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 5.3 |  |  |  | 0 |  | 1179.163 | 25.96% | 6.642%
UKI-LT2-RHUL | 1.205 |  | 0.472 |  |  |  |  | 7.271 |  | 1239 | 0.15 | 0.002 |  |  |  |  | 0.19 | [6 empty] | 0.0015 | [6 empty] | 0.01 | 1.182 | [5 empty] | 0 |  | 1249.4835 | 27.51% | 0.2571%
Total | 1.569 | 101.294 | 1.585 | 0 | 0 | 0 | 0.053 | 1831.2095 | 0 | 2388.037 | 0.624 | 0.005 | 0 | 0 | 123.69 | 0 | 2.554 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.012 | 0.0075 | 0 | 0 | 0 | 0 | 0.0082 | 0 | 0.01 | 1.182 | 0.019 | 5.3 | 8.262 | 0.019 | 0 | 58.275 | 17.685 | 4541.423 | 100% | 4.371%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q415
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3
| Ivan Reid | 0.7 | 0.7 | 0.7 | 0.15 | 0.15 | 0.15
| P. Hobson | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
| R. Powell | Unfunded Month 1: 0.07; Unfunded Month 2: 0.07; Unfunded Month 3: 0.07
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Abdulkadir Farah | bar: Unfunded Month 1 to Unfunded Month 3
Duncan Rand | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| David Colling, Ray Beuselinck | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| network team + Alex Owen/Cozmin | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| B.Green/Tom | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 7.4 | 7.4 | 7.4 | 2.07 | 2.07 | 2.07

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q415
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel
UKI-LT2-IC-HEP
UKI-LT2-QMUL | Attended Janet networking meeting on: End to end performance, actually Chris W gave talk here, and IPV6, Terry gave talk here, (had chat with Lancaster network team and persuaded them on case for IPv6) Major work on commissioning, optimising and migrating over to new Lustre storage system. Now complete including commissioning new production SE. Continued development on new batch system, SLURM, and have now got a CE in front of it now. Planing major internal network upgrade for separation of out-of-band traffics from production traffic, use of jumbo frames, and adding IPV6 to worker nodes. Have now moved all external IP addresses to IPV6 enabled VLAN. All services are IPV6 dual stack enabled (apart from squids) all have IPV6 in DNS apart from squids and production CEs (due to cern bug). Organised procurement procedure, documents and timetable.
UKI-LT2-RHUL |  |  | Slow storage drain, storage upgrade, storage hardware fails, firewall setup
UKI-LT2-UCL-HEP | Site being phased out.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes