## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q415 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | EFDA JET |  |  | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 25% | 21.43% | 21.43% | 168% | 140.3% | 140.3% | 220.2% | 205.7% | 205.7% | 259.3% | 239.7% | 239.7% | 288.2% | 266.4% | 250% | 291.9% | 278% | 278% | 583.3% | 538.5% | 538.5% | 262.9% | 241.5% | 237.7%
.x.2 | % of promised (by that time) CPU available | 100% | 828% | 630.6% | 630.6% | 281.3% | 248.5% | 248.5% | 678.2% | 526.8% | 526.8% | 285.7% | 212.4% | 212.4% | 307% | 234.1% | 234.1% | 442.3% | 334.6% | 334.6% | 2018% | 1521% | 1521% | 395.2% | 308.6% | 308.6%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 94% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 99% | 100% | 100% | 82% | 96% | 93% | 96.43% | 99.29% | 99%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 94% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 99% | 100% | 100% | 82% | 96% | 93% | 96.43% | 99.29% | 99%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | na | na | na | 67% | [5 empty] | 98% |  |  | 72% |  |  | 100% |  |  | 97% |  |  | 84.25% |  |  | Steve Lloyds test have been broken this quarter
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 7.727% | 7.323% | 2.476% | 91.7% | 89.53% | 78.1% | 16.8% | 19.3% | 21.83% | 41.39% | 48.53% | 88.08% | 63.95% | 66.01% | 70.59% | 49.64% | 68.44% | 78.85% | 62.54% | 65.6% | 88.17% | 53.51% | 63.07% | 69.58%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 7.387% | 4.793% | 1.499% | 86.17% | 82.26% | 70.95% | 12.61% | 17.06% | 19.99% | 77.51% | 70.4% | 75.71% | 74.28% | 68.94% | 63.61% | 66.15% | 72.51% | 64.04% | 113.1% | 114.4% | 82.98% | 64.57% | 66.2% | 59.44%
bi
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q415
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
EFDA JET | EMI2 | EMI3/SL6 |  | 1Gb/s | 1Gb/s | DPM 1.8.8-4 (EMI3) |  | Site | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total |  | Site | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 |  | EFDA JET | 34376 | 1672 | 22584 | 58632 |  | EFDA JET | 64935 | 8403 | 23549 | 96887
Bristol | EMI-2/EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 7176476 | 6981424 | 5407048 | 19564948 |  | Birmingham | 7597840 | 7734000 | 6205436 | 21537276
Cambridge | EMI-3 | EMI-3/SL6 |  | 10Gb/s | 2*10Gb/s | DPM 1.8.8-4 (EMI-3) |  | Bristol | 1605240 | 1384896 | 1603932 | 4594068 |  | Bristol | 1728763 | 1562638 | 1727153 | 5018554
Oxford | EMI 2 | EMI 3/SL6 |  | 10Gb/s | 3*10Gb/s | DPM 1.8.7 (EMI-2) |  | Cambridge | 2256524 | 2142748 | 1834108 | 6233380 |  | Cambridge | 2575138 | 2412241 | 2264421 | 7251800
RALPP | UMD2/3 | UMD2/3 |  | 10Gb/s | 10Gb/s | Dcache 2.2 |  | Oxford | 6635588 | 8910604 | 8005736 | 23551928 |  | Oxford | 7335521 | 9773615 | 9024879 | 26134015
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 18905272 | 22176860 | 17912476 | 58994608 |  | RALPP | 22880228 | 25964025 | 23788460 | 72632713
[8 empty] | Sussex | 1523664 | 1660008 | 438984 | 3622656 |  | Sussex | 1645346 | 1718605 | 485448 | 3849399
[8 empty] | Total CPU hrs | 38137140 | 43258212 | 35224868 | 116620220 |  | Total | 43827771 | 49173527 | 43519346 | 136520644
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
EFDA JET | 1772 | 1.5 | 281 | 7 | 630.6% | 21.43% | 1.994% | 0.02947% | 58632 | 0.05028% | 2208 | 3912576 | 1.499% | 2.476%
Birmingham | 12489 | 620 | 5026 | 442 | 248.5% | 140.3% | 14.05% | 12.18% | 19564948 | 16.78% | 2208 | 27575712 | 70.95% | 78.1%
Bristol | 10410 | 218 | 1976 | 106 | 526.8% | 205.7% | 11.71% | 4.283% | 4594068 | 3.939% | 2208 | 22985280 | 19.99% | 21.83%
Cambridge | 3729 | 350 | 1756 | 146 | 212.4% | 239.7% | 4.196% | 6.877% | 6233380 | 5.345% | 2208 | 8233632 | 75.71% | 88.08%
Oxford | 16768 | 1220 | 7163 | 488 | 234.1% | 250% | 18.87% | 23.97% | 23551928 | 20.2% | 2208 | 37023744 | 63.61% | 70.59%
RALPP | 41719 | 2610 | 12468 | 939 | 334.6% | 278% | 46.95% | 51.28% | 58994608 | 50.59% | 2208 | 92115552 | 64.04% | 78.85%
Sussex | 1977.32 | 70 | 130 | 13 | 1521% | 538.5% | 2.225% | 1.375% | 3622656 | 3.106% | 2208 | 4365922.56 | 82.98% | 88.17%
Totals | 88864.32 | 5089.5 | 28800 | 2141 | 308.6% | 237.7% | 100% | 100% | 116620220 | 100% | 2208 | 196212418.56 | 59.44% | 69.58%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
EFDA JET |  | 0 |  |  | EFDA JET
Birmingham |  | 0 |  |  | Birmingham
Bristol |  | 0 |  |  | Bristol
Cambridge |  | 0 |  |  | Cambridge
Oxford |  | 0 |  |  | Oxford
RALPP |  | 0 |  |  | RALPP
Sussex |  | 0 |  |  | Sussex
Totals |  | 0 | 0 | 0
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
(cam and ox hae new sl6 hs06 values)
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q415
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
EFDA JET | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 11
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [20 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[44 empty] | 0 | 0
[44 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 2 | 2 | 2 | 1 | 0 | 0 | 3 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 3 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 112
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
EFDA JET | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.02597% | 16.43%
Birmingham | 127 | 211.9 | 0.12 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0.2 | 0.02 |  | 0.53 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 341.901 | 9.116% | 0.8774%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.4 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.409 | 9.876% | 0.00189%
Cambridge | 0 | 238.9 | 0 | 0 | 0.1 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 |  | 0 | 0 | 0.45 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.57 | 6.388% | 0.09183%
Oxford | 0 | 577 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.06 | 0.891 | 0 | 0.625 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.37 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 5.34 | 0.018 | 0.016 | 1.5 | 31 | 0 | 0 | 0.0234 | 617.9124 | 16.48% | 6.39%
RALPP | 0 | 675 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1130 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 360 |  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2169.6 | 57.85% | 0.212%
Sussex |  | 9 | [8 empty] | 0.008 | [25 empty] | 1 |  |  | 0.176 |  |  |  |  | 10.184 | 0.2715% | 11.63%
Total | 127 | 1712.424 | 0.12 | 1.15 | 0.4 | 0.064 | 0 | 0 | 0 | 1501.461 | 1.016 | 0 | 0.635 | 0 | 0.025 | 0 | 0.28 | 0.055 | 0 | 0.534 | 0 | 361.012 | 0 | 0 | 2 | 1 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 6.34 | 0.018 | 0.016 | 1.676 | 31 | 0 | 0 | 1.0434 | 3750.5504 | 100% | 1.297%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q415
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater |  |  |  | 0.3 | 0.3 | 0.3
| Matt Williams | 0.5 | 0.5 | 0.5
Bristol | Winnie Lacesso |  |  |  | 0.5 | 0.5 | 0.5
| Luke Kreczko |  |  |  | 0.2 | 0.2 | 0.2
Cambridge
| John Hill | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2
Oxford
| Ewan MacMahon | 1 | 1 | 1 | 0 | 0 | 0
| Kashif Mohammad | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
RALPP | Ian Loader | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
| Chris Brew | 0.4 | 0.4 | 0.4 | 0.35 | 0.35 | 0.35
| FedericoMelaccio | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
Sussex | Emyr James | [6 empty] | red text last quarters figures
| Matt Raso-Barnett |  |  |  | 0.3 | 0.3 | 0.15
Jeremy Maris
Total |  | 4.5 | 4.5 | 4.5 | 1.85 | 1.85 | 1.7
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q415
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
EFDA JET
Birmingham
Bristol | Got CMS user stageout working! Split HTCondor services to improve stability of WLCG & local job submission |  | "Despite a catastrophic failure of HDFS due to NameNode badness, recovered with no loss of data."
Cambridge | ATLAS disk dump implemented (and working!). Occasional networking problems to Data Centre now believed understood. Pilot roles added for all supported VOs. |  | Moving storage to DPM 1.8.10/SL6 a major concern for the next quarter.
Oxford | Latter stages of the Begbroke AC issues - we got fully back up and running by the middle of October Added VAC resource to the gocdb using he newly added service type: https://goc.egi.eu/portal/index.php?Page_Type=Service&id=7549 Planning for T2C testing with ATLAS and CMS Ewan attended Janet End-to-end performance Initiative meeting Ewan diagnosed and reported IPv6 bug in CMVFS 2.1.20 Decommissioned ATLASPRODDISK spacetoken Removed ~80TB of 2007 generation storage physically from the racks. Updated VAC to newly released 0.19.0 |  | Ewan resigned to take another rpost within the University of Oxford. Last day 18.3.16
RALPP | Added support for the lz, lsst, na62 and sno+ VOs All VOs have pilot accounts enabled. Certain CMS workflows can overload the storage, They have stopped those workflows at the Tier 2 now, awaiting two developments from CMS to help with this issue. Deployed ELK monitoring of dCache logs.
Sussex | We (mainly Matt RB) have migrated all data from our Lustre 1.8.9 system to a new system running Lustre 2.5.3 - using parallel rsync to move around 280TB of data Matt RB patched Lustre 2.5.3 such that the extended attributes required by StoRM work Matt RB has migrated Grid services that were running on old hardware to VM, including the SRM We’ve recruited a replacement for Matt RB who should be starting with us on 1st April (Tier 2 Visa permitting…) |  | Matt RB left on 14th December and limited cover is being provided by Sussex IT Services. Unfortunately, we (ITS) didn’t notice the problems associated with the renaming of our SRM from grid-storm to grid-storm-02, partly because of other workload. Ticket processing also suffered as some acknowledgement were made late. ITS are more up to speed with covering this now! Atlas knew about the plans which were discussed them a couple of times at the support cloud meeting. It was intended that AGIS would be updated with the new SRM but this didn’t happen; ATLAS production jobs stopped, along with problems with SNO+ and the LFC We lost about 8 weeks of production jobs (Most in Q116) before the problem was understood and AGIS was updated. We have another 7 nodes (112 physical cores) of 2650 v2 and 2640 v3 that we are about to add to our Grid queue so we should be able to catch up with lost production work. It also seems that we may have not copied some files from atlaslocalgroupdisk in the lustre migration. We are attempting to reconcile what ATLAS thinks we have with what we actually have so that we can declare missing files lost.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol- split HTCondor services to improve stability of WLCG & local job submission |  | 2015-12-31 |  | Done
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Deploy ELK log monitoring |  | 2015-09-30 |  | Started
RALPP:Replace cluster top level router |  | 2015-09-30 |  | Awaiting deployment by RAL networking
RALPP:Support more minor VOs (inc snoplus) |  | 2015-11-30
RALPP:Update HyperVisor cluster to Windows 2012RC2 |  | 2015-11-30
Bristol - quotas and BDII information for new SE (HDFS + DMLite), waiting on software update |  | 03/31/2016
Bristol - upgrade ARC CE from 4.2 to 5.X |  | 03/31/2016
Bristol- Fix ARC CE accounting |  | 03/31/2016
Bristol- Consolidation of Puppet infrastructure to synchronise with local IT team. |  | 03/31/2016
Bristol - Deploy HTCondor CE on lcgce02 |  | 03/31/2016
Bristol- Add new hardware: 280 more cores, 256 TB (after replication) |  | 03/31/2016
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
Landslides |  |  |  | Bristol
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop