## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q116 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 319% | 319% | 319% | 381.2% | 381.2% | 381.2% | 142.8% | 246.5% | 246.5% | 305.3% | 305.3% | 248.4% | 212.4% |  |  | 259.5% | 303.2% | 291.7%
.x.2 | % of promised (by that time) CPU available | 100% | 533.9% | 533.9% | 646.4% | 205.5% | 205.5% | 205.5% | 256.1% | 302.4% | 302.4% | 320.7% | 320.7% | 320.7% | 273.1% |  |  | 291.1% | 304.9% | 323.5%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% |  |  | 99.8% | 99.75% | 100%
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% |  |  | 99.8% | 99.75% | 100%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 22% |  |  | 0% |  |  | 44% |  |  | 11% | [5 empty] | 19%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 61% | 64.67% | 44.79% | 86% | 91.92% | 76.12% | 72% | 41.89% | 71.13% | 87% | 71.12% | 70.82% | 8% |  |  | 74% | 66.35% | 64.15% | Brunel low
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 51% | 50.16% | 26.6% | 76% | 83.62% | 68.09% | 74% | 40.86% | 57.41% | 97% | 85.74% | 54.83% | 6% |  |  | 70% | 61.82% | 49.52% | Brunel low
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q116
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  | SITE | 2016-01-01 | 2016-02-01 | 2016-03-01 | Total |  | SITE | 2016-01-01 | 2016-02-01 | 2016-03-01 | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 6858498.9328 | 11498666.989 | 8662852.3178 | 27020018.2396 |  | UKI-LT2-Brunel | 12101616.4171 | 18607125.6125 | 14785602.6706 | 45494344.7002
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | Storm |  | UKI-LT2-IC-HEP | 19740126.1717 | 19382351.855 | 13598199.3675 | 52720677.3942 |  | UKI-LT2-IC-HEP | 22332390.2814 | 21323542.6225 | 15281981.5325 | 58937914.4364
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 15163670.965 | 18533276.936 | 14329197.8225 | 48026145.7235 |  | UKI-LT2-QMUL | 19946734.1611 | 21863853.2863 | 17698838.668 | 59509426.1154
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 5617411.3904 | 8593952.6139 | 9673078.1662 | 23884442.1705 |  | UKI-LT2-RHUL | 8008725.5037 | 10674043.4763 | 12167784.2946 | 30850553.2746
[8 empty] | UKI-LT2-UCL-HEP | 351503.6214 | 232867.705 | 712188.8645 | 1296560.1909 |  | UKI-LT2-UCL-HEP | 381646.3207 | 380003.5666 | 888143.3638 | 1649793.2511
[8 empty] | Total | 47731211.0813 | 58241116.0989 | 46975516.5385 | 152947843.7187 |  | Total | 62771112.684 | 72848568.5642 | 60822350.5295 | 196442031.7777
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 46000 | 1100 | 7116.84 | 344.8046 | 646.4% | 319% | 33.17% | 13.13% | 27020018.2396 | 17.82% | 2208 | 101568000 | 26.6% | 44.79% | 59.39%
UKI-LT2-IC-HEP | 35068.4 | 2937 | 17064.9 | 770.4745 | 205.5% | 381.2% | 25.29% | 35.06% | 52720677.3942 | 34.76% | 2208 | 77431027.2 | 68.09% | 76.12% | 89.45%
UKI-LT2-QMUL | 37890.25 | 2900 | 12530.606 | 1176.5461 | 302.4% | 246.5% | 27.32% | 34.62% | 48026145.7235 | 31.67% | 2208 | 83661672 | 57.41% | 71.13% | 80.7%
UKI-LT2-RHUL | 19730 | 1440 | 6152.802 | 579.7169 | 320.7% | 248.4% | 14.23% | 17.19% | 23884442.1705 | 15.75% | 2208 | 43563840 | 54.83% | 70.82% | 77.42%
UKI-LT2-UCL-HEP
Totals | 138688.65 | 8377 | 42865.148 | 2871.5421 | 323.5% | 291.7% | 100% | 100% | 151651283.5278 | 100% | 2208 | 306224539.2 | 49.52% | 64.15% | 77.86%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 4886 | 46247 | 1387
UKI-LT2-IC-HEP | 3980 | 35819 | 2845
UKI-LT2-QMUL | 4512 | 45482 | 2896
UKI-LT2-RHUL | 2160 | 19921 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 147469 | 8588
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
Note on E34: gronbech: Gstat displays SI2000 so this needs converting to HS06

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q116
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cedar | cernatschool.org | comet.j-parc.jp | cms | dteam | dzero | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | ilc | ipv6.hepix.org | lhcb | lz | mice | na48 | na62.vo.gridpp.ac.uk | neiss.org.uk | ngs.ac.uk | ops | pheno | snoplus.snolab.ca | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | vo.helio-vo.eu | vo.landslides.mossaic.org | vo.londongrid.ac.uk | zeus | Total
UKI-LT2-Brunel | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 1 | 1 | 21
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 23
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 22
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 15
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 1 | 4 | 4 | 2 | 3 | 1 | 1 | 1 | 4 | 4 | 2 | 1 | 2 | 1 | 4 | 3 | 2 |  | 1 | 4 | 1 | 4 | 1 | 1 | 1 | 1 | 4 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 3 | 81
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.364 |  | 0.286 |  |  |  | 0.053 | 562 |  | 39.098 | 0.017 | 0.003 |  |  |  |  | 1.691 | [6 empty] | 0.045 |  |  |  |  | 0.202 | [6 empty] | 0.019 |  | 0 |  | 603.778 | 12.86% | 0.4439%
UKI-LT2-IC-HEP |  | 30.291 | 0 |  | 0 |  | 0 | 1352.2615 |  | 12.362 |  |  |  |  | 188.797 |  |  |  | 0 | [15 empty] | 24.901 |  |  | 62.48 | 18.444 | 1689.5365 | 35.97% | 8.056%
UKI-LT2-QMUL |  | 71 | 0.814 |  |  | 0 |  | 2 |  | 1500 | 0.047 | [5 empty] | 0.673 | 0.0068 |  |  |  | 0.016 | 0.013 | 0.142 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 5.3 |  |  |  | 0 |  | 1580.036 | 33.64% | 4.939%
UKI-LT2-RHUL | 1.205 |  | 0.377 |  |  |  |  | 1.058 |  | 819 | 0.14 | 0.002 |  |  |  |  | 0.19 | [5 empty] | 0.004 | 0.123 | [6 empty] | 0.01 | 1.182 | [5 empty] | 0 |  | 823.291 | 17.53% | 0.3927%
Total | 1.569 | 101.291 | 1.477 | 0 | 0 | 0 | 0.053 | 1917.3195 | 0 | 2370.46 | 0.204 | 0.005 | 0 | 0 | 188.797 | 0 | 2.554 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.017 | 0.31 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.01 | 1.182 | 0.019 | 5.3 | 24.901 | 0.019 | 0 | 62.48 | 18.444 | 4696.6415 | 100% | 4.686%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q116
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3
| Ivan Reid | 0.7 | 0.7 | 0.7 | 0.15 | 0.15 | 0.15
| P. Hobson | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
| R. Powell | Unfunded Month 1: 0.07; Unfunded Month 2: 0.07; Unfunded Month 3: 0.07
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Abdulkadir Farah | bar: Unfunded Month 1 to Unfunded Month 3
Duncan Rand | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| David Colling, Ray Beuselinck | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| network team + Alex Owen/Cozmin | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| B.Green/Tom | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 7.4 | 7.4 | 7.4 | 2.07 | 2.07 | 2.07

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q116
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | - Network . new faster firewall delivered to the site; not deployed yet. - CPU . hardware from Gridpp4+ delivered. . Not online yet. . Depending on deployment of new copper fabric.
UKI-LT2-IC-HEP | IPv6 added to our LHCONE link. CMS job overflow set up. Attended IPv6 F2F meeting at CERN.
UKI-LT2-QMUL | Attended Alan Turing Institute meeting on Big Data in the Physical Sciences at the Royal society. Attended Face2Face hepix IPV6 meeting at cern. Wrote blog post on standalone xrootd with multiple VOs (http://gridpp-storage.blogspot.co.uk/2016/01/xrootd-for-all.html) Recommissioned old storage as part of new Lustre storage system, which now provides a of total 3 PB of storage. Brought installed and commissioned an additional 10K hepspec of compute and 300TB of storage. Stated work on deploying test GPU compute with availability via cream CE using test CE with development code from egi. Continued development of new batch system, deployment system and network upgrade. Started work on understanding power efficiency vs performance, have obtained a dedicated PDU with accurate power per socket measurements.
UKI-LT2-RHUL | No change in hepspec, 330TB storage decommissioned Site issues :- 10GB link, firewall setup New kit installed but not added to grid |  | DPM drain issue
UKI-LT2-UCL-HEP | VAC now working for ATLAS.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes