## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q1 2016 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 200% | 250% | 272.5% | 210% | 210% | 207.6% | 140% | 130% | 210.3% | 184% | 178% | 190.3% | 228.6%
.x.2 | % of promised (by that time) CPU available | 100% | 542% | 599% | 666.2% | 411% | 411% | 325.5% | 426% | 395% | 486.7% | 560% | 561% | 563.9% | 519.5%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | I've not updated this row -although the figures are still accurate
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Same here.
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 97% | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 100% | 78% | 19.5% | Not done this row either.
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 25% | 36% | 52.25% | 63% | 90% | 109.1% | 51% | 82% | 75.28% | 15% | 36% | 34.69% | 65.66%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 36% | 30% | 44.35% | 73% | 84% | 98.72% | 72% | 75% | 63.74% | 31% | 31% | 28.61% | 56.3%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2016
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Site | 2016-01-01 | 2016-02-01 | 2016-03-01 | Total |  | Site | 2016-01-01 | 2016-02-01 | 2016-03-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 16677725 | 18302998 | 9657295 | 44638018 |  | Lancaster | 20278798 | 20260030 | 12047013 | 52585841
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 10636689 | 9324138 | 9682580 | 29643407 |  | Liverpool | 11506048 | 10371151 | 10889506 | 32766705
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 18710303 | 22253205 | 20565388 | 61528896 |  | Manchester | 21646456 | 25791458 | 25223232 | 72661146
[7 empty] | Sheffield | 2883122 | 2810989 | 2471321 | 8165432 |  | Sheffield | 3399762 | 3248189 | 3250105 | 9898056
[7 empty] | Total CPU hrs | 46024717 | 49880341 | 39905263 | 135810321 |  | Total | 56831064 | 59670828 | 51409856 | 167911748
Current Resources Available | [6 empty] | Used dev accounting portal. | [6 empty] | http://accounting-devel.egi.eu/tier2.php?Path=1.36.2&query=sum_normcpu&startYear=2016&startMonth=1&endYear=2016&endMonth=3&yrange=SITE&xrange=DATE&groupVO=all&chart=GRBAR&scale=LIN&localJobs=onlygridjobs
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 46080 | 2300 | 6917 | 844 | 666.2% | 272.5% | 39.35% | 40.06% | 44638018 | 31% | 2184 | 100638720 | 44.35% | 52.25%
Liverpool | 13749 | 762 | 4224 | 367 | 325.5% | 207.6% | 11.74% | 13.27% | 29643407 | 20.59% | 2184 | 30027816 | 98.72% | 109.1%
Manchester | 44197 | 2149 | 9081 | 1022 | 486.7% | 210.3% | 37.75% | 37.43% | 61528896 | 42.74% | 2184 | 96526248 | 63.74% | 75.28%
Sheffield | 13066 | 531 | 2317 | 279 | 563.9% | 190.3% | 11.16% | 9.248% | 8165432 | 5.671% | 2184 | 28536144 | 28.61% | 34.69%
Totals | 117092 | 5742 | 22539 | 2512 | 519.5% | 228.6% | 100% | 100% | 143975753 | 100% | 2184 | 255728928 | 56.3% | 65.66%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 46080 | 2300 | NA | Lancaster
Liverpool | 1085 | 13749 | 762 | NA | Liverpool
Manchester | 4494 | 44197 | 2149 | NA | Manchester
Sheffield | 1071 | 13066 | 531 | NA | Sheffield
Totals | 9850 | 117092 | 5742 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2016
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | na48 | neiss | ops | pheno | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1 | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 24
Liverpool | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 31
Manchester |  | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 19
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 0 | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 19
Total | 2 | 4 | 1 | 4 | 1 | 3 | 2 | 1 | 4 | 4 | 3 | 2 | 2 | 2 |  | 2 | 4 | 3 |  | 3 | 4 | 1 |  | 2 | 2 | 1 |  | 4 | 4 | 3 | 1 | 1 | 4 | 2 | 3 | 4 |  | 93
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1450 | 0 | 16 | 6 | 1472 | 1.087% | 1.495%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3620.24 | 0.57 | 178 | 13.47 | 3920.46 | 4.54% | 4.898%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2016
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | 1 | 1 | 1
| M. Doidge | 1 | 1 | 1
| P. Love |  |  |  | 0.3 | 0.3 | 0.3
Liverpool | S. Jones | 1 | 1 | 1
| R. Fay |  |  |  | 0.5 | 0.5 | 0.5
| J. Bland |  |  |  | 0.5 | 0.5 | 0.5
Manchester | A. Forti | 1 | 1 | 1
| R. Frank | 1 | 1 | 1
| A. McNab |  |  |  | 0.5 | 0.5 | 0.5
Sheffield | E. Korolkova | 0.5 | 0.5 | 0.5
| M. Robinson |  |  |  | 0.1 | 0.1 | 0.1
Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | 0.5 | 0.5 | 0.5
Manchester | A. Forti |  |  |  | 1 | 1 | 1

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q1
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Procured New Kit Identified ATLAS SAM test problem NFS tuning for shared area New VO rollout Old KIT decommissioned | New Kit delivered and paid for on time Fixed (technically start of Q2) Soothed job problems LSST rolled out, LZ and uboone almost there More space is racks, fewer SL5 nodes |  |  | None None Problems soothed, not solved LSST having teetching problems Slightly down in capacity until new kit comes online.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | IPv6 downtime didn't happen, so still no IPv6 for a few months |  |  | None can be taken,downtime to roll out IPv6 won't be until end of Q2/start of Q3.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Continued tuning of resources More Vos supported. |  |  | 30/03/16 30/3/16 |  | Increased stability. The more the merrier.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Bring online new kit Formulate SL5 migration plan, test something7 Smooth running |  |  | 30/4/16 31/5/16 30/6/16 |  | More capacity. Started cleaning up the last few Sl5 holdouts Make maximum use of that extra capacity.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q1
Reported by | S Jones
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Security HW OS and infrastructure Docs, training, talks Middleware | CVE-2015-7313 (Kernel 2.6.32-573.12.1) CVE-2016-1950 (nss) CVE-2016-0728 (glibc) GPP4+ HW Procurement (cpu, disk, spares) HW Maint (disk, raid, MB, NW...) Centos7 tests Move to Puppet 3 underway Condor MCORE talk for GridPP, ALBA, Barcelona VAC Test Site (~ 426 slots, 800 coming weeks) VO work - LSST, Pilots ... |  | Older kit starting to breakdown Centos7 very different to SL6 Continues to evolve, but successfully
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | IPV6 Centos7 VAC not yet used by many VOs |  | Still waiting - Need firmware update. Not in our control. Quite different to SL6. Will need testing for migration. Needs VM process to be automatic, easy and well defined.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | IPV6 Test System CSD Cluster Share + Explore Cloud Technologies VAC New round of Usability Tests for 'Guest Experiment' documentation Centos7 Tests |  | 31/03/2016 31/03/2016 31/03/2016 31/03/2016 |  | Still awaiting allocation. Asked for status. Done, but continue to expand to 800 slots. Deprioritised On going
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | IPV6 Test System CSD Cluster Share + Explore Cloud Technologies VAC Centos7 Tests Accounting system Data Flow Diagram VAC Talk at Pitlochry VAC Monitoring system (Data collection, Elastic search, Kibana, Grafana and similar) |  | 30/06/2016 30/06/2016 30/06/2016 30/06/2016 12/06/2016 30/06/2016 |  | Waiting for firmware to allow this. 800 slots Ongoing. Will try to get service nodes on. Possible option. Will clarify operation of subsystem. Slides. Prototype plotting system.

## Manchester
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q1
Reported by | R Frank
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Manchester |  | 1) Completed procurement and installed hardware 2) Decommissioned remaining 2005 Dells 3) Moved Squid proxies from SL5 to CentOS7 4) Continued development of and running of Vac and GridPP Vcycle service (managing VMs at IC, CERN, and CC-IN2P3) at Manchester 5) Vac increased to 616 VMs at Manchester 6) Finalised transition of GridPP website from GridSite to Wordpress + X.509 plugin written by Andrew 7) Operating GridPP’s DIRAC monitoring framework 8) Icecube and LHCb are exploiting the prototype GPU service within grid jobs to run their existing GPU-dependent code 9) Manchester has continued as one of the UK’s four LHCb T2-D sites with storage 10) Andrew prototyped and Manchester has deployed the second version of the WLCG Machine/Job Features scripts 11) Following Jamboree completed the deployment of ATLAS brokering using RAM values for production jobs. 12) Enabled microboone for both single core and multicore 13) Run LSST first production on the grid using ganga/dirac and incorporated dirac catalogue to handle files in the scripts 14) Worked on ATLAS Event Service usage in Manchester |  |  | a few hhd failures (WN, SE), PSU (SE), and memory (WN) Problem with VOMS server disk filling up due to logging issues with jetty server (voms admin)
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  |  | Mitigating Action
Manchester
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/Htcondor on at least 1 cluster, 2) Integrate DPM in puppet and abandon YAIM, 3) Test remaining SE with failed raid array, fix remaining problems, and return it into full service. 4) Extend IPv6 to more hosts 5) Increase number of machines managed by Vac in the Tier-2 6) Add APEL-Sync records to Vac usage reporting to pass the EGI APEL SAM tests 7) Extend the accounting analysis tool to produce reports automatically as a web page for daily monitoring rather than just as an offline tool 8) Look into foreman deployment 9) Improve local tools to balance data servers 10) commission new hardware 11) decommission remaining 2005 Dells |  |  |  |  | 1) stalled 2) in progress 3) stalled (delayed by lack of PSUs) 4) stalled 5) done 6) done 8) in progress 10) done 11) done
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/Htcondor on at least 1 cluster, 2) Integrate DPM in puppet and abandon YAIM, 3) Test remaining SE with failed raid array, fix remaining problems, and return it into full service. 4) Extend IPv6 to more hosts 7) Extend the accounting analysis tool to produce reports automatically as a web page for daily monitoring rather than just as an offline tool 8) Look into foreman deployment 9) Improve local tools to balance data servers 10) Review next old SE (disk tests, raid array rebuild)
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs.
Working with LSST users to adapt their workflow to use grid resources
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Alessandra Forti: - Organised Ganga Tutorial and HEPsysman in Manchester 14-15/1/2016 - HEPsysman, WLCG workshop: Info sys, accounting, benchmarking 15/1/2016 - ATLAS Jamboree, chair of the Infrastructure and sites recommendation 27-29/1/2016 - ATLAS Jamboree, "On memory and batch systems", 27/1/2016 - WLCG workshop, chair of the Info sys, accounting, benchmarking session, 1/2/2016 - WLCG workshop, session introduction, 1/2/2016 - WLCG workshop, session Summary, 3/2/2016 - ATLAS S&C week, "WLCG workshop and jamboree summaries", 1/3/2016 |  |  | 14-15/01/2016 27-29/01/2016 01/02/2016 03/02/2016 01/03/2016
Andrew McNab presentations: “Cloud use by LHCb”, CC-IN2P3 Annual Meeting, Lyon, 9 Feb 2016. “Vacuum platform”, EGI Operations Management Board, 25 Feb 2016. “LHCb Operations Report”, LHCb National Computing Board, 7 Mar 2016. |  |  | 09/02/2016 25/02/2016 07/03/2016
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Alessandra is one of the GridPP representatives and one of the co-chairs of the WLCG Ops Coordination, Atlas monitoring coordinator and member of the atlas distributed computing coordination; Multicore TF co-leader; WLCG workshop 2016 planning committee.
Andrew is the Deputy LHCb Computing Coordinator and LHCb Distributed Computing and Operations Coordinator. He is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group and leading the GridPP Tier-2 Evolution project. He is leader of the WLCG "Machine Features” task force, and a member of the "Cloud Traceability”, “Cloud Resource Reporting”, and “Information Systems Evolution" task forces.
Other outputs and Knowledge |  |  | Date |  | Notes

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q1
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | Procurement has been done. 240 new job slots were added to the cluster. 40 jobs slots have been retired (the remaining old 6 cores machines). Publishing is fixed. The head node and all disk servers have been updated to 1.8.10. The cron job creating storage dumps requested by Atlas is in place. http support issue ihas been solved. Analysis abailability for ATLAS ( ASAP metric) is 98.3%. |  |  | Setting a cron job creating storage dumps was time taking as we found a bug in rfcp command. This was fixed locally and dpm developers will fix this ain the next dpm release. Publishing was fixed after new wn's have been installed and the old 6-cores wn's retired. The results should be seen in the next quarter.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Moving grid servers to ipv6 configured may cause lots of problem. |  |  | Wait for gaining more experience and proper instructions for ipv6 configuration
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Procurement has been done. 240 new job (200 additional) slots were added to the cluster. Publishing is fixed. The head node and all disk servers have been updated to 1.8.10. The cron job creating storage dumps requested by Atlas is in place. http support issue has been solved. |  |  | 31 March 2016
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Fix perfsonar server problem. |  |  | 2016-06-30
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes