## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q116 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | EFDA JET |  |  | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 21.43% | 21.43% | 21.43% | 140.3% | 140.3% | 140.3% | 205.7% | 205.7% | 445.3% | 239.7% | 239.7% | 226% | 266.4% | 250% | 250% | 278% | 278% | 278% | 538.5% | 538.5% | 538.5% | 241.5% | 237.7% | 248.6%
.x.2 | % of promised (by that time) CPU available | 100% | 630.6% | 630.6% | 630.6% | 248.5% | 248.5% | 248.5% | 526.8% | 526.8% | 802% | 212.4% | 212.4% | 212.4% | 234.1% | 234.1% | 234.1% | 334.6% | 334.6% | 334.6% | 1521% | 1521% | 1521% | 308.6% | 308.6% | 327.4%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 96% | 93% | 86% | 99.29% | 99% | 98%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 96% | 93% | 86% | 99.29% | 99% | 98%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | na | na | na | [21 empty] | Steve Lloyds test have been broken this quarter
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 7.323% | 2.476% | 4.899% | 89.53% | 78.1% | 67.05% | 19.3% | 21.83% | 11.99% | 48.53% | 88.08% | 87.02% | 66.01% | 70.59% | 75.92% | 68.44% | 78.85% | 78.46% | 65.6% | 88.17% | 62.33% | 63.07% | 69.58% | 63.95%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 4.793% | 1.499% | 4.658% | 82.26% | 70.95% | 58.31% | 17.06% | 19.99% | 9.724% | 70.4% | 75.71% | 70.8% | 68.94% | 63.61% | 65.53% | 72.51% | 64.04% | 69.29% | 114.4% | 82.98% | 52.48% | 66.2% | 59.44% | 55.65%
bi
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q116
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
EFDA JET | EMI2 | EMI3/SL6 |  | 1Gb/s | 1Gb/s | DPM 1.8.8-4 (EMI3) |  | Site | 2016-01-01 | 2016-02-01 | 2016-03-01 | Total |  | Site | 2016-01-01 | 2016-02-01 | 2016-03-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 |  | EFDA JET | 99491.2631 | 13714.3928 | 67045.592 | 180251.2479 |  | EFDA JET | 104271.9975 | 14583.8918 | 70756.4556 | 189612.3449
Bristol | EMI-2/EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 5050139.5887 | 6220393.3253 | 4632876.4445 | 15903409.3585 |  | Birmingham | 5634644.0638 | 6897180.0389 | 5755657.0111 | 18287481.1138
Cambridge | EMI-3 | EMI-3/SL6 |  | 10Gb/s | 2*10Gb/s | DPM 1.8.10 |  | Bristol | 951838.2301 | 1221140.411 | 1192456.2459 | 3365434.887 |  | Bristol | 1366531.3727 | 1479265.2619 | 1302736.4798 | 4148533.1144
Oxford | EMI 3 | EMI 3/SL6 |  | 10Gb/s | 2*20Gb/s | DPM 1.8.10 |  | Cambridge | 2100180.7812 | 1944638.9395 | 1721253.8103 | 5766073.531 |  | Cambridge | 2627498.1856 | 2421193.5238 | 2038047.7355 | 7086739.4449
RALPP | UMD2/3 | UMD2/3 |  | 10Gb/s | 10Gb/s | Dcache 2.2 |  | Oxford | 9036177.0595 | 7189212.4839 | 7771104.9346 | 23996494.478 |  | Oxford | 10024019.6536 | 8595653.0216 | 9184088.6212 | 27803761.2964
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 21955587.5848 | 22203942.7282 | 18973475.8261 | 63133006.1391 |  | RALPP | 25668507.0468 | 24605660.3513 | 21215814.2057 | 71489981.6038
[8 empty] | Sussex | 19205.0575 | 955386.8111 | 1291921.121 | 2266512.9896 |  | Sussex | 151095.5865 | 1195643.1617 | 1345071.9194 | 2691810.6676
[8 empty] | Total CPU hrs | 39212619.5649 | 39748429.0918 | 35650133.9744 | 114611182.6311 |  | Total | 45576567.9065 | 45209179.251 | 40912172.4283 | 131697919.5858
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
EFDA JET | 1772 | 1.5 | 281 | 7 | 630.6% | 21.43% | 1.879% | 0.02818% | 180251.2479 | 0.1573% | 2184 | 3870048 | 4.658% | 4.899%
Birmingham | 12489 | 620 | 5026 | 442 | 248.5% | 140.3% | 13.24% | 11.65% | 15903409.3585 | 13.88% | 2184 | 27275976 | 58.31% | 67.05%
Bristol | 15847 | 472 | 1976 | 106 | 802% | 445.3% | 16.8% | 8.866% | 3365434.887 | 2.936% | 2184 | 34609848 | 9.724% | 11.99%
Cambridge | 3729 | 330 | 1756 | 146 | 212.4% | 226% | 3.954% | 6.199% | 5766073.531 | 5.031% | 2184 | 8144136 | 70.8% | 87.02%
Oxford | 16768 | 1220 | 7163 | 488 | 234.1% | 250% | 17.78% | 22.92% | 23996494.478 | 20.94% | 2184 | 36621312 | 65.53% | 75.92%
RALPP | 41719 | 2610 | 12468 | 939 | 334.6% | 278% | 44.24% | 49.03% | 63133006.1391 | 55.08% | 2184 | 91114296 | 69.29% | 78.46%
Sussex | 1977.32 | 70 | 130 | 13 | 1521% | 538.5% | 2.097% | 1.315% | 2266512.9896 | 1.978% | 2184 | 4318466.88 | 52.48% | 62.33%
Totals | 94301.32 | 5323.5 | 28800 | 2141 | 327.4% | 248.6% | 100% | 100% | 114611182.6311 | 100% | 2184 | 205954082.88 | 55.65% | 63.95%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
EFDA JET |  | 0 |  |  | EFDA JET
Birmingham |  | 0 |  |  | Birmingham
Bristol |  | 0 |  |  | Bristol
Cambridge |  | 0 |  |  | Cambridge
Oxford |  | 0 |  |  | Oxford
RALPP |  | 0 |  |  | RALPP
Sussex |  | 0 |  |  | Sussex
Totals |  | 0 | 0 | 0
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
(cam and ox hae new sl6 hs06 values)
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on B27: hill: 2283 extra HS06 waiting to be installed. Some of existing CPU will be turned off.
Note on C27: hill: 20TB old storage decommissioned.
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q116
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
EFDA JET | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 11
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [20 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[44 empty] | 0 | 0
[44 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 2 | 2 | 2 | 1 | 0 | 0 | 3 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 3 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 112
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
EFDA JET | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.02554% | 16.43%
Birmingham | 163 | 225 | 0.12 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0.2 | 0.02 |  | 0.53 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 390.501 | 10.24% | 0.6402%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.4 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.409 | 9.714% | 0.00189%
Cambridge | 0 | 246.2 | 0 | 0 | 0.1 | 0.02 | 0 | 0 | 0 | 0 | 0.004 | 0 | 0 | 0 | 0 | 0 | 0.07 | 0 |  | 0 | 0 | 0.43 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246.824 | 6.473% | 0.0786%
Oxford | 0 | 577 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 | 0.049 | 0.625 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 6.48 | 0.018 | 0.016 | 1.5 | 31.98 | 0 | 0 | 0.0234 | 618.8404 | 16.23% | 6.593%
RALPP | 1 | 658 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1130 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 378 |  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2175.6 | 57.05% | 0.3953%
Sussex |  | 9 | [8 empty] | 0.008 | [25 empty] | 1 |  |  | 0.176 |  |  |  |  | 10.184 | 0.2671% | 11.63%
Total | 164 | 1715.824 | 2.12 | 0.65 | 0.4 | 0.044 | 0 | 0 | 0 | 1501.411 | 0.169 | 0.049 | 0.635 | 0 | 0.025 | 0 | 0.27 | 0.055 | 0 | 2.534 | 0 | 378.652 | 0 | 0 | 2 | 1 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 7.48 | 0.018 | 0.016 | 1.676 | 31.98 | 0 | 0 | 1.0434 | 3813.3324 | 100% | 1.402%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q116
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater |  |  |  | 0.3 | 0.3 | 0.3
| Matt Williams | 0.5 | 0.5 | 0.5
Bristol | Winnie Lacesso |  |  |  | 0.5 | 0.5 | 0.5
| Luke Kreczko |  |  |  | 0.25 | 0.25 | 0.25
Cambridge
| John Hill | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2
Oxford
| Ewan MacMahon | 1 | 1 | 1 | 0 | 0 | 0
| Kashif Mohammad | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
RALPP | Ian Loader | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
| Chris Brew | 0.4 | 0.4 | 0.4 | 0.35 | 0.35 | 0.35
| FedericoMelaccio | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
Sussex | Emyr James | [6 empty] | red text last quarters figures
| Matt Raso-Barnett |  |  |  | 0.3 | 0.3 | 0.15
Jeremy Maris
Total |  | 4.5 | 4.5 | 4.5 | 1.9 | 1.9 | 1.75
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q116
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
EFDA JET | The EFDA-JET has been working OK, without much changes. Usage is quite low, with mainly biomed jobs, now that there are no fusion jobs being run. |  | None
Birmingham
Bristol | deployed new service: HTCondor CE - 2nd site outside OSG (1st is CERN). Added 320 cores (HT) and 512 TB of disk, new VM server and new IO server. The 50% of HT core recommendation from http://southgrid.blogspot.co.uk/2012/03/following-recent-discussion-on.html does not work for us. We had to lower it to 4 additional cores (out of 28) such that the time of the benchmark does increase if we use more cores. Provided access to our SE & GridFTP servers to one of the DPM developers to improve the stability & performance of our installation. Most WNs are now migrated to the new Puppet master (SL 7.2, Puppet 4). Started to migrate WNs from CREAM CEs to the ARC & HTCondor CEs. |  | HDFS namenode failover not yet in DPM, caused SE failure over night - HA feature now exists, waiting on puppet master migration to deploy. Space in HPC room is getting rare, new hardware had to wait for a while.
Cambridge | All pool nodes upgraded to SL6/DPM 1.8.10/puppet. Decommissioned 20TB of old storage. Machine job features implemented on all WNs. |  | Still have to upgrade head node. New CPU resources (2283 HS06) to be installed, and some of existing old CPU to be decommissioned. More old disk servers likely to be turned off (and not replaced).
Oxford | Completed major update of the DPM SE. All nodes updated to SL6, with the latest DPM version (1.8.10) installed using puppet. Several teething problems resolved along the way with the help of Sam Skipsey. Migrated the VAC setup to viab. |  | Ewan left on 18.3.16. Time to resolve tickets has extended due to overloaded staff.
RALPP | All CMS work now coming in with Multicore Pilots Purchased 3 new disk servers (216TB Raw each) and 5 Quad WNs (HS score to be determined), delivered and underging vendor proving. Cleared up lots of Atlas Dark Data. Purchased new faster (SSD) SRM node for dCache Admin Started testing CentOS7 nodes. ELK Deployed and providing useful dCache statistics, need to add more metrics and build dashboards. Atlas FAX set up on the xroot proxy nodes |  | Federico Leaves in Early April Some CMS workflows overload the storage: - New headnode to improve SRM performance - Write dynamic queuing tool to adjust queue depth on disk servers depending on IO load.
Sussex | We (mainly Matt RB) have migrated all data from our Lustre 1.8.9 system to a new system running Lustre 2.5.3 - using parallel rsync to move around 280TB of data Matt RB patched Lustre 2.5.3 such that the extended attributes required by StoRM work Matt RB has migrated Grid services that were running on old hardware to VM, including the SRM We’ve recruited a replacement for Matt RB who should be starting with us on 1st April (Tier 2 Visa permitting…) |  | Matt RB left on 14th December and limited cover is being provided by Sussex IT Services. Unfortunately, we (ITS) didn’t notice the problems associated with the renaming of our SRM from grid-storm to grid-storm-02, partly because of other workload. Ticket processing also suffered as some acknowledgement were made late. ITS are more up to speed with covering this now! Atlas knew about the plans which were discussed them a couple of times at the support cloud meeting. It was intended that AGIS would be updated with the new SRM but this didn’t happen; ATLAS production jobs stopped, along with problems with SNO+ and the LFC We lost about 8 weeks of production jobs (Most in Q116) before the problem was understood and AGIS was updated. We have another 7 nodes (112 physical cores) of 2650 v2 and 2640 v3 that we are about to add to our Grid queue so we should be able to catch up with lost production work. It also seems that we may have not copied some files from atlaslocalgroupdisk in the lustre migration. We are attempting to reconcile what ATLAS thinks we have with what we actually have so that we can declare missing files lost.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol- split HTCondor services to improve stability of WLCG & local job submission |  | 2015-12-31 |  | Done
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Replace SL5 Frontier/CVMFS Squids with CentOS7 ones. |  | 2016-04-15
RALPP:Replace cluster top level router |  | 2016-06-30 |  | Awaiting deployment by RAL networking - Is installed in networking racks next to the Site Access Router. Configuration has started.
RALPP: Deploy new dCache Head Node |  | 2016-05-01
RALPP: Deploy Test CentOS7/UMD4 ArcCE |  | 2016-06-01
Bristol - quotas and BDII information for new SE (HDFS + DMLite), waiting on software update |  | 03/31/2016
Bristol - upgrade ARC CE from 4.2 to 5.X |  | 03/31/2016
Bristol- Fix ARC CE accounting |  | 03/31/2016
Bristol- Consolidation of Puppet infrastructure to synchronise with local IT team. |  | 03/31/2016
Bristol - Deploy HTCondor CE on lcgce02 |  | 03/31/2016
Bristol- Add new hardware: 280 more cores, 256 TB (after replication) |  | 03/31/2016
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
Landslides |  |  |  | Bristol
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop