## Metrics
GridPP Quarterly Report | [9 empty] | OK
Area | Data Group | [8 empty] | Close to target
Year | 2015 | [8 empty] | Not OK
Reported by | Jens Jensen | [8 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q213 | Q313 | Q413 | Q114 | Q214 | Q314 | Q414 | Q115 | Q215 | Comment Q114 | Comment Q214 | Comment Q314 | Comment Q414 | Comment Q115 | Comment Q215
C2.1 | Number of VO requested changes not implemented in a timely fashion across whole infrastructure (1wk for small changes, 3wks for medium size, 6wks for large.) - any GridPP VO |  | Jens Jensen | 0 | [9 empty] | OK. No major changes requested except a few bits associated with Rucio renaming for ATLAS. Removing files in PRODDISK | No major changes requested | OK; no major changes requested | OK: no major changes requested. | OK, no major changes requested. | OK, no major changes requested
C2.2 | Number of experiments whose data transfer rates from/to RAL to/from T2s do not meet their (realistic) requirements |  | Jens Jensen | 0 | [9 empty] | OK | There were problems but not to/from RAL. Some T2s had problems with transfers to/from sites like BNL (such as Cambridge, Oxford) but the problem could be at the BNL end. | (WLCG only) 579 MB/s avg over all countries with RAL as a source.. Some countries like China have low "efficiency" RAL as destination is 468MB/s avg, with avg success of 94%: again some countries like Israel and China perform poorly | Avg 150 MB/s overall (between all UK sites), so about 1192 TB. | WLCG transfer rates were low but seems to be lack of activity rather than performance problems: RAL to UK T2s was 634TB, or 82 MB/s, and the other way was 28 MB/s. | Avg into RAL (WLCG only) 115 MB/s for the whole quarter; out of RAL 130 MB/s.
C2.3 | FTS data transfer success rate |  | Jens Jensen | 85% |  | LHC: 92% RAL LHC: >88% UK | 96% |  |  |  |  | >90% but see text) | 94% (but see text) | OK | This number would be easier to assess if they didn';t delete data so zealously in the FTS database | Problems with ATLAS in particular, as they seem to be attempting to write to a disabled pool. It's hard to get numbers when both the RAL and the CERN FTS do not keep logs | 86% success rate (FTS). Matrix is quite consistently green except UCL as destination shows very low rates (0-3%) to other T2s. | All T2s are 91%-100%, but RAL-Bris is low (53%) and RAL-Susx (44%) - the other way (Bris-RAL and Susx-RAL) is OK. Also RAL-RAL is quite low (68%); Brian investigated and found ATLAS file-not-found. Most failures isolated to ~1wk | UK to RAL: 94% RAL to UK: 83% Some T2s have low success rates (and a small number of transfers) - SUSX, UCL, DURHAM
C2.4 | Conference paper (CHEP, AHM, or similar (or better)) produced each year describing GridPP developments and innovations in data management and storage area |  | Jens Jensen | 4/Y |  |  |  | 1 | [5 empty] | Submission to SLAC workshop, OSG/XSEDE all-hands: fedeared storage in GridPP (Wahid presented) Wahid produced a deliverable (or rather his wife did), Kieran, weighing in at 10lb 10oz | Papers prepared for WLCG workshop: | HEPiX preparations: a few GridPP presentations | hepsysman presentations.. Big data day at Wellcome, D Colling attended and we sent him (some) slides | Papers submitted to CHEP (in April 2015). Also HEPIX in Oxford. | CHEP2015 Stoeage/data papers from gridPP: Object storage via Shims in Grid m'ware (CHEP2015) Comparison of overheads of federation tech (Shaun, Wahid, CHEP2015), Filesize distribution at RAL (Brian, Shaun), perfSonar for non-HEP (Brian), DIRAC file mgmt with EC storage (Sam, et al);
C2.5 | Engage with storage and data management experts within WLCG/EGI/EMI/NGS or similar, or industry, to reinforce GridPP's recognised competence in this area (talks given, meetings, virtual meetings) |  | Jens Jensen | 4/Q | [10 empty] | Wahid chaired the pre-GDB at CERN on data access: http://indico.cern.ch/event/272787/ and presented with Dirk Duellmann a summary at the following GDB. "Federation" workshop at SLAC: again, Wahid travelled to it and presented. Many people atrended remotely at the DPM workshop https://indico.cern.ch/event/265334/ Hepsysman: http://hepwww.rl.ac.uk/SYSMAN/June2014/main.html | WLCG workshop in July: http://indico.cern.ch/event/305362/. GridPP meeting at Ambleside - "will stuff scale for run 2?" GDB with UK input: http://indico.cern.ch/event/272777/ | 1. DPM workshop (Oct) 2. Brunel working with DPM on CMS stress tests for DPM. 3. ATLAS Jamboree (Dec.) | Wahid attended the Jan pre-GDB on data preservation, the GDB on "the protocol zoo" | WLCG meeting co-located with CHEP2015.
C2.6 | Number of incidents not resolved within 1wk after being reported on list |  | Jens Jensen | 0 | [9 empty] | No major incidents. | Mainly RUCIO again - removing empty directories.. Also a few WebDAV issues (eg at QMUL) |  | Mostly the ShellShock incidents at the beginning of the quarter. | Some problems with DPM 1.8.9 upgrades were reported but were debugged and resolved fairly quickly. | Incidents are mostly with the new VOs (DiRAC, LIGO) and those reported tend to get solved quickly (turnaround may depend on the VO end)
C2.7 | Number of blog posts |  | Jens Jensen | 8 | 3 | 0 | 3 | 8 | 5 | 6 | 6 | 7 | 5 | Brian 2, Ewan 1, Jens 5 (not really how it's supposed to work, but we got there…) | Five: Ewan 1, Brian 2, Jens 2 | Chris 1, Ewan 1, Sam 1, Jens 3 (but shorter ones) | Brian 3, Jens 3 | A yellowish green for seven: Sam 2 Brian 2 Jens 3 | Five: Jens 4, Brian 1. (At Jens and Brian were not allowed to blog during the Purdah!)
Note on G11: Jensen, Jens (STFC,RAL,SC): Ukraine appears in the "UK" plot, skewing the result slightly.

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Data Group |  |  | Overdue
Year | 2015 |  |  | Not yet due
Reported by | Jens Jensen |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
C2.8 | Cloud storage plan - feasibility of interoperation, or using clouds as scratch, or temporary storage for (cloud) analysis. Standards and interoperation. | Jens Jensen | 2011-04-01 |  | http://www.gridpp.ac.uk/wiki/Cloud_Storage_Plan
C2.9 | FTS - plan for improved monitoring (and reporting) | Jens Jensen | 2011-05-01 |  |  | 1.We now have a plan! Raul Lopez from CERN is interested in working with us on resurrecting the monitoring if we can find the code Gidon wrote for us. We also have a better understanding of the FTS table and have created a read-only account to be able to extract more precise data than the high level summaries. 2. Brian working with SLAC re new xfer testing
C2.10 | Transfer failure study (doc) | Jens Jensen | 2011-07-01 |  | http://www.gridpp.ac.uk/wiki/FTS_transfer_failure_study
C2.11 | NFS4 functional test/initial performance study | Jens Jensen | 2011-07-01 |  | https://svnweb.cern.ch/trac/lcgdm/wiki/Dpm/NFS41/Client/Install | Meant to update this: we have a few studies now.
C2.12 | Collaboration roadmap - EGI, EMI, WLCG, | Jens Jensen | 2011-08-01 |  |  | Thanks to the EGI TF and related we now know more about how we will contribute to EMI (DPM testing) and what we can expect from them. Eg integration of DPM toolkit
C2.13 | Dave's family - extended Dave-the-dataset study | Jens Jensen | 2011-08-01 |  |  | Brian has chased "Dave" and "Georgina" but hasn't completed the blog post(s) that publishes the work.
C2.14 | Argus deployment and integration with Storage | Jens Jensen | 2011-12-01 |  |  | Still can't do this, as sites are not yet running Argus
| Milestone for Q312: DPM planing document. Which is done, but needs post-GridPP29 update before going further. |  |  |  |  | Need to circulate the post-GridPP29 updated version (=final)

## Manpower Q212 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q312 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q412 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q113 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q213 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q114
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q214
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q314
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q414
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q115
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 0.5
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 2.5 | 0 | 0 | 0

## Manpower Q215
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 0 | 0 | 0
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 2 | 2 | 2 | 0 | 0 | 0

## Narrative Q114
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | For once, we have lots (well, enough) blog posts |  | Not enough effort or interest to fully exploit/explore the opportunities
Data Management | ATLAS Rucio renaming and emtpy directory cleanup went well, at least regarding our services for ATLAS. As far as we know no GridPP site uses N2N any more
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
certificate related issues causing transfers to fail - SHA2, "short" proxies |  | Ongoing testing. Delay changes till others have tried it (ie not being the first to switch)?
Support for IPv6 - not an easy one to solve |  | Still a risk: more experience, but problem still rumbling on
Insitute or area specific risks
Risk |  | Mitigating Action
Small VOs:use of shared storage resources causing problems for other users of the same space (or other members of the VO) |  | Token "small" VOs by default? Education? What's their incentive for using tokens when it works without
Small VOs: need sustainable metadata solution to support non-LHC Vos |  | Not sure - investigate existing options further. LFC, AMGA.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Get more "small" VOs to talk to us more frequently |  | 2014-03-31 |  | Ongoing reports from meetings; revision of "small" VO advice
Proposal for data interoperation with DiRAC - aim to meet DiRAC techies |  | 2014-03-31 |  | Proposal to PMB? Work with Jeremy
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
WebFTS evaluation, feedback to developers |  | 2014-06-30 |  | Report. Eventually offer as alternative to GlobusOnline for "small" VOs? (Features expected to suit grid better)
Plan for HTTP contribution/testing of DPM. In particular how to support space tokens via HTTP (Wahid, others) |  | 2014-05-31 |  | Plan to be agreed with DPM collaboration

## Narrative Q214
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | GridPP well represented at numerous events. DPM upgrades went well (1.8.8); only a few sites below baseline. |  | Support for small VOs was highlighted again: it generall works but (a) they can grow, (b) may need space tokens and use space tokens, and (c) sites have no strong incentive to support them
Data Management | Mopping up the remains (such as empty directories) after the Great ATLAS RUCIO Arkleseizure seems to have gone well. |  | We haven't actually completed last quarters' metrics due to the delays with WebFTS deployment at RAL. We only have the CERN one to work with.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Like others have highlighted, much of the wiki is now woefully out of date. People do not check or update they own stuff - at least rarely - and even keydocs get out of date |  | Identify most important storage pages and action people to update them.
Not taking opportunities with the "tangential" stuff - preservation (DPHEP), iRODS (HyperK), European projects (EUDAT, EGI,) |  | Accept the risk?
Insitute or area specific risks
Risk |  | Mitigating Action
DPM 1.8.9 is DMLite, so significantly bigger step than the 1.8.8 most sites currently running |  | Careful testing needed
Insufficient support for data managemnet in DIRAC? DIRAC is being used by more Vos |  | Assess first with VOs whether it is a problem?
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
WebFTS evaluation, feedback to developers |  | 2014-06-30 |  | Delayed due to WebFTS deployment by RAL late (was not given high enough priority by T1, and the stable release was late as well)
Plan for HTTP contribution/testing of DPM. In particular how to support space tokens via HTTP (Wahid, others) |  | 2014-05-31 |  | Plan to be agreed with DPM collaboration (now to be presented in October: http://indico.cern.ch/event/324705/)
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Policy defined for "small" VOs, both existing and new ones (focus on new ones) |  | 2014-09-30 |  | Policy; to be accepted by PMB?
Most important storage pages identified and updated in the wiki |  | 2014-09-30 |  | Tom and/or Jeremy happy with wiki

## Narrative Q314
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Finally, progress/experiences with Ceph seems to hit critical mass? Ceph could be the "future T2". Ewan's success with Argus |  | Getting all upgrades and changes in before beam commissioning for run 2 (ie ~Feb '15). Support for space tokens in non-SRM protocols, particularly for DPM which relies on space tokens to honour reservations. High load in xroot (seen at Liverpool and RAL), cannot reliably throttle connections
Data Management | WebFTS at RAL beginning to be used by (some) small VOs |  | Short term memory of FTS and other transfer databases making it harder to produce consistent logs?
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Need to upgrade to IPv6 before run 2: there are gotchas with dual homing, IPv6 is not supported in xroot till v4 (which is not in DPM). GridFTP 3rd party transfer. |  | Testing DPM with IPv6 (Oxford) Testing GridFTP with IPv6 (QMUL)
Loss of opportunity due to info in wiki being out of date |  | Retry getting KeyDocs updated?
Insitute or area specific risks
Risk |  | Mitigating Action
xroot4 overloaded at L'pool and RAL: Glasgow experiments with cgroup throttling valiant but mostly unsuccessful |  | Raise with DPM developers; raise with xroot
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Policy defined for "small" VOs, both existing and new ones (focus on new ones) |  | 2014-09-30 |  | We have suggested a few items to the "standard" VO policy: also we have a handholding process for small Vos
Most important storage pages identified and updated in the wiki |  | 2014-09-30 |  | Some progress - probably not complete. Suggested focusing on keydocs, plus three other toplevel docs which should maybe become keydocs?
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
DPM workshop in Naples, Italy: prepare UK input and report back |  | 2014-10-15 |  | Slides (for workshop) and report
Run 2 preparations: plan for all remaining todos before Run 2 (such as DPM upgrades,. Xroot throttling, IPv6) |  | 2014-11-30 |  | Plan

## Narrative Q414
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Continuing successful work with WebDAV, CEPH, and cloud things |  | robots: http access (no authentication) leaves SEs vulnerable to robots attack since they cannot always serve a robots.txt from the / location. Hard to persuade people to blog about the work they do (except Brian).
Data Management | FTS transferred almost three times more data in a year than globusonline has done in its lifetime. (Brian found that FTS numbers were about 220 PB; GO is on 77PB at the time of writing.) |  | Continued use of lcg-utils despite their being deprecated and no longer supported.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Again, responses from non-LHC VOs and their representation to the storage group is variable - from excellent to non-existent. |  | Prod absent VOs more vigorously. Need updated contacts list.
File deletion needs revisiting: deletion rates are reported too slow, and are slower still with some of the newer non-SRM protocols. Our earlier metric said 1Hz but we now need >= 10Hz |  | Needs investigation
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DPM workshop in Naples, Italy: prepare UK input and report back |  | 2014-10-15 |  | https://indico.cern.ch/event/324705/session/0/contribution/4 http://storage.esc.rl.ac.uk/weekly/20141015-minutes.txt
Run 2 preparations: plan for all remaining todos before Run 2 (such as DPM upgrades,. Xroot throttling, IPv6) |  | 2014-11-30 |  | See minutes of storage meetings. IPv6 is delayed; xroot throttling raised at workshop (but fix is not in 1.8.9). DPM upgrade to 1.8.9 needed improvement, and migration to EPEL; and upgrade had some minor issues (http://storage.esc.rl.ac.uk/weekly/20141119-minutes.txt) and failed SAM tests at Lancaster. This is the only remaining problem (that we know of).
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
We somehow need more experience with DIRAC's data model |  | 2015-03-31
Report on file deletion rate |  | 2015-02-28 |  | wiki entry

## Narrative Q115
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Managed to engage a few more "small" Vos in discussion (cf risk raised previous Q): LIGO, ILC |  | Some middleware issues: DPM 1.8.9 site config; StoRM issue with checksums on Lustre; LHCb problem with dCache open files.
Data Management | Ready for run 2! |  | Wahid leaving!
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Experiences with DIRAC (non-LHCb) data tools (cf last quarter's objective) found them flakey? |  | Work with new VOs? More debugging/testing?
Middleware: Couple of issues associated with DPM 1.8.9 upgrade (in addition to the ones reported in December) but seemed to be a site config issue and resolved. Also a StoRM bug with recent versions of Lustre, particularly affecting checksumming. |  | Not much else we can do: keep testing, report bugs
Insitute or area specific risks
Risk |  | Mitigating Action
Wahid leaving leads to loss of expertise in DPM or reduces our ability to support T2s |  | Replace Wahid? Retrain someone already part of GridPP storage and data management?
Some sites had poor performance for a ~week, leading to significant drops in their success rates |  | If probelsm recur, work more closely with sites where poor performance is a site problem (as opposed to timeout, experiments reading non-existing files)
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
We somehow need more experience with DIRAC's data model |  | 2015-03-31 |  | Preliminary reports in the storage meetings (see eg 25 Feb). Suggestion is that we follow up with new VOs which will be using DIRAC.
Report on file deletion rate |  | 2015-02-28 |  | Further experience/report available, e.g.: http://gridpp-storage.blogspot.co.uk/2015/02/so-atlas-have-just-finished-deletion.html Deletion rates are a tradeoff between submitting them individually (slowest), scheduled in bulk but executed individually, and executed in bulk (fastest but dangerous)
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Need to back up 5PB of DiRAC data - while it goes to T1 tape, it is an area where GridPP storage and data management should contribute expertise. Some DiRAC sites also host GridPP sites |  | 2015-06-30 |  | 1. Plan 2. Transfers started 3. Experiences from first transfers
New "small" VO feedback on DIRAC data management (e.g. LIGO) |  | 2015-06-30 |  | Presentation or report

## Narrative Q215
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | This time successes and weaknesses are related. Getting DiRAC started and moving was a success: an important customer and they are happyish |  | The surprising amount of effort/time required and gotchas found to get DiRAC set up and running (particularly the RAL end but in general). Same for users of DIRAC.
Data Management | FTS is proving useful in moving data for users |  | Some weaknesses found in FTS3 - need for long term VOMS proxies, need to check holdings against expectation
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Data support for small VOs: shared storage can be filled up (Liverpool) or tools can be hard to use (DiRAC, LIGO) |  | We are now doing (usually) weekly updates on the small or new VOs in the storage meeting (www.storage.esc.rl.ac.uk/weekly)
Recent and emerging changes in experiment data models lead to problems at T2s (or require changes in T2 software) |  | More testing is needed: particularly the T2C model
FTS3 has done well moving files for DiRAC (and others!) |  | Need for extra tools around FTS (which ATLAS and CMS already have) for "small" VOs: checking data holdings, accounting, scheduling FTS transfers
Insitute or area specific risks
Risk |  | Mitigating Action
Some technical risks have resurfaced: (a) deletion rates, particularly at RAL. Old target was 1Hz, we now need 10Hz? (b) delay in deploying bugfixes (eg GFAL) causing problems (c) difficulty in setting up or using new VOs lead to shareed VOs (eg SouthGrid) or 'NIL' VOs (which are not good for accounting) |  | (a) Improve documentation for users (b) more testing (c) write scripts/tools to make process friendlier for users? (d) make better use of existing tools to plug gaps for new VOs?
Problems in setting up new VOs lead to GridPP getting a bad reputation…? |  | (a) We now strongly recommend that members of GridPP join the new VOs to aid debugging. (b) We now have the GRIDPP-SUPPORT mailing list recommended for (technical) contacts in VOs
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Need to back up 5PB of DiRAC data - while it goes to T1 tape, it is an area where GridPP storage and data management should contribute expertise. Some DiRAC sites also host GridPP sites |  | 2015-06-30 |  | 1. Plan 2. Transfers started 3. Experiences from first transfers DONE: DIRAC-USERS mailing list records the experiences in detail See also http://gridpp-storage.blogspot.co.uk/2015/06/the-firewall-did-it.html
New "small" VO feedback on DIRAC data management (e.g. LIGO) |  | 2015-06-30 |  | So we got feedback from LIGO which we can summarise as follows: experiences with DIRAC are frustrating because (a) neither tools nor instructions work well, and (b) lack of progress due to lack of time on their side. It is known some problems were outside GridPP, too, such as networks at user location.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Proposal/plan for feasibility testing of future Tier 2 (aka T2D) based on cheaper erasure coded storage (with no SRM interface?) |  | 2015-08-15 |  | Proposal/plan
T2C experiences: rely on data from other T2s. Experience with either T2C (eg UCL or Oxford as a volunteer) or stress testing Bristol with data from other GridPP sites |  | 2015-09-30 |  | Tests run: results
(Objective for Q4) The "syncat" problem will need revisiting: checking SE contents against catalogues - CMS and ATLAS are both making "plans" requiring full namespace dumps and DiRAC highlighted issues |  | Q4

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes