## Metrics
GridPP Quarterly Report | [6 empty] | OK
Area | Security | [5 empty] | Close to target
Year | 2015 | [5 empty] | Not OK
Reported by | Dave Kelsey | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q313 | Q413 | Q114 | Q214 | Q314 | Q414 | Q115 | Q215 | Comment Q313 | Comment Q413 | Comment Q114 | Comment Q214 | Comment Q314 | Comment Q414 | Comment Q115 | Comment Q215
C3.1 | Number of Tier 2 security incidents in the last quarter |  | ? | Green <=1, Amber 2 or 3 and Red >=4 | 0 | 0 | 1 | 1 | 3 | 0 | 0 | 2 | no incident reported | no incident reported | 1 incident at Durham reported to UK NGI Security on 20 Jan and EGI CSIRT on 21 Jan (EGI RT #6626) | 1 incident at Glasgow reported to UK NGI Security and EGI CSIRT on 25 April (EGI RT #6949, 6951, 6954, 6957) | 1 incident at Manchester - reported to UK NGI Sec and EGI CSIRT on 15 Aug (EGI RT #7344). 1 incident at Glasgow and 1 at Liverpool all reported (UK and EGI) on 29 Sep (EGI RT #7480 and 7484) | no incident reported | no incident reported | 1 incident at Glasgow reported to UK NGI Sec and EGI CSIRT on 11 June [EGI-20150611] and related incident at ECDF/Edinburgh on 12 June [EGI-20150612].
C3.2 | Number of sites responding poorly to a security incident in last quarter |  | ? | Green 0, Amber 1 Red >=2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Well handled | Well handled | Well handled |  |  | Very well handled by both sites.
Note on B10: gronbech: Green 0, Amber 1, Red >=2

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Security |  |  | Overdue
Year | 2015 |  |  | Not yet due
Reported by | Dave Kelsey |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
C3.3 | Operational Security Procedures Update (related to EGI milestones MS412, MS419 and MS426) | John Green | 2011-08-01 | 2011-08-01 | https://documents.egi.eu/document/649
C3.4 | Operational Security Procedures Update (related to EGI milestones MS412, MS419 and MS426) | John Green | 2012-08-01 | 2012-08-16 | https://www.gridpp.ac.uk/wiki/Security_Information | EGI milestone MS419 has gone. This update was completed during Q3 and just considered GridPP security procedures
C3.5 | Operational Security Procedures Update (related to EGI milestones MS412, MS419 and MS426) | John Green | 2013-08-01 | 2012-08-16 | https://www.gridpp.ac.uk/wiki/Security_Information | EGI milestone MS426 was removed after the 1st EU review of EGI-InSPIRE. This update was completed during Q3 of 2013 and just considered GridPP security procedures
C3.6 | Security Service Challenge | John Green | 2011-12-01 | 2013-03-20 | Final report completed and distributed. Not stored on web to keep from other NGIs still needing to run the SSC. | This was delayed for 15 months because of required upgrades to the EGI SSC framework. 11 GridPP sites were challenged in this SSC. All did well.
C3.7 | Security Workshop | John Green | 2012-12-01 | 1st July 2011 | http://indico.cern.ch/conferenceDisplay.py?confId=145475 | A half day security workshop was organized on the second day of HEPSYSMAN at RAL on 1st July 2011
C3.8 | Security Service Challenge | Ian Neilson | 31/12/2013 (new date 31/12/2015) |  |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson and Ewan Macmahon will run a full test in Q4.
C3.9 | Security Workshop | John Green | 2014-12-01 | 2014-06-05 | https://indico.cern.ch/event/318354/ | We decided to run this even early in collaboration with the summer UK HEP SYSMAN meeting.
C3.10 | V1.0 of IGTF profile on Attribute Authority Operations prepared. | D.P.Kelsey | 2011-11-30 | 2012-01-18 | http://www.eugridpma.org/guidelines/aaops/ | Worked on this during this quarter, but was not able to finalise it until the EUGridPMA meeting in Jan 2012. V1.0 now complete.
C3.11 | Review GridPP Security Risk Assessment(related to EGI-Inspire Deliverable D4.4) | D.P.Kelsey | 2012-08-01 | 2012-08-01 | https://documents.egi.eu/secure/ShowDocument?docid=969 | After EGI D4.4 was completed a full Grid risk assessment was performed. Done in the scpe of EGI but fully applicable to GridPP
C3.12 | Review procedures to produce and agree security policies. (related to EGI milestone MS241) | D.P.Kelsey | 2013-08-01 | 2013-08-01 | https://documents.egi.eu/document/210 | This EGI milestone was removed. The previous mechansims for EGI SPG were found to be still fit for purpose
C3.13 | Security recommendations for the future. | D.P.Kelsey | 30/06/2014 (new date 31/12/2015) |  |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Q4 2015 after the results of the GridPP5 bid are known.

## Manpower Q114
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.5 | 0.5 | 0.5
RAL | Deployment | Dave Kelsey | 0.33 | 0.33 | 0.33
RAL | Vulnerabilities | Linda Cornwall |  |  |  | 0.5 | 0.5 | 0.5
RAL | Policy | Dave Kelsey | 0.33 | 0.33 | 0.33
Total |  |  | 1.16 | 1.16 | 1.16 | 0.5 | 0.5 | 0.5

## Manpower Q214
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.5 | 0.5 | 0.5
RAL | Deployment | Dave Kelsey | 0.33 | 0.3 | 0.3 |  | 0.15 | 0.15
RAL | Vulnerabilities | Linda Cornwall |  |  |  | 0.5 | 0.5 | 0.5
RAL | Policy | Dave Kelsey | 0.33 | 0.3 | 0.3
Total |  |  | 1.16 | 1.1 | 1.1 | 0.5 | 0.65 | 0.65

## Manpower Q314
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.3 | 0.3 | 0.3
RAL | Deployment | Dave Kelsey | 0.2 | 0.2 | 0.2
RAL | Vulnerabilities | Linda Cornwall | 0.2 | 0.2 | 0.2 | 0.5 | 0.5 | 0.5
RAL | Policy | Dave Kelsey | 0.47 | 0.49 | 0.42 | 0.09 | 0.08 | 0.16
Total |  |  | 1.17 | 1.19 | 1.12 | 0.59 | 0.58 | 0.66

## Manpower Q414
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.5 | 0.5 | 0.5
RAL | Deployment | Dave Kelsey | 0.2 | 0.2 | 0.2
RAL | Vulnerabilities | Linda Cornwall |  |  |  | 0.5 | 0.5 | 0.5
RAL | Policy | Dave Kelsey | 0.43 | 0.44 | 0.43 | 0.15 | 0.14 | 0.13
Total |  |  | 1.13 | 1.14 | 1.13 | 0.65 | 0.64 | 0.63

## Manpower Q115
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.5 | 0.4 | 0.44
RAL | Deployment | Dave Kelsey | 0.2 | 0.2 | 0.1
RAL | Deployment | Ian Neilson |  | 0.1 | 1
RAL | Vulnerabilities | Linda Cornwall |  |  |  | 0.5 | 0.6 | 0.56
RAL | Policy | Dave Kelsey | 0.58 | 0.24 | 0.6 |  | 0.33 | 0.07
Total |  |  | 1.28 | 0.94 | 2.14 | 0.5 | 0.93 | 0.63

## Manpower Q215
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.56 | 0.5 | 0.5
RAL | Deployment | Dave Kelsey | 0.1 | 0.1 | 0.1
RAL | Deployment | Ian Neilson | 1 | 1 | 1
RAL | Vulnerabilities | Linda Cornwall |  |  |  | 0.44 | 0.5 | 0.5
RAL | Policy | Dave Kelsey | 0.47 | 0.33 | 0.22 | 0.13 | 0.29 | 0.5
Total |  |  | 2.13 | 1.93 | 1.82 | 0.57 | 0.79 | 1

## Narrative Q114
GridPP Quarterly Report
Area | Security
Year | 2013
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Also lead UK NGI security team with fortnightly meetings. Ongoing routine security operations including tracking required updates to software for security reasons and handling vulnerabilities. The UK security team still covering with a weekly rota of duty and regular phone meetings. Draft questionnaires for Cloud technlogy and Cloud service providers have been produced. |  | John Green left in June 2013. The first attempt to replace via recruitment resulted in an offer to the preferred candidate but this was refused. This post will be re-advertised.
Vulnerabilities
Policy | Chair and lead EGI SPG. Regular weekly/monthly meetings. Hosted EUGridPMA and SCI meetings in Cosenres House Abingdon (Jan 2014). Led Security training workshop at ISGC2014 Taipei March 2014. Spoke at German AAI meeting in DESY (Jan 2014). Pushing forward with planning for EGI security in H2020 era.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 2013-12-31 |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK NGI Argus server is fully in service. Still waiting for Argus delpoyment and appointment of replacement GridPP Security Officer
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2014-06-30 |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This may be delayed as funding is not yet certain anywhere.

## Narrative Q214
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Hosted/Chaired EGI CSIRT F2F meeting at Coseners House in April. Also lead UK NGI security team with fortnightly meetings. Ongoing routine security operations including tracking required updates to software for security reasons and handling vulnerabilities. Attended EGI Community Forum (Helsinki, May) - Security for Clouds and plans for H2020 sessions. The UK security team still covering with a weekly rota of duty and regular phone meetings. Ongoing work on EGI Cloud Security issues. Planning for Horizon 2020 security bids. |  | John Green left in June 2013. The first attempt to replace via recruitment resulted in an offer to the preferred candidate but this was refused. This post has now been re-advertised.
Vulnerabilities
Policy | Chair and lead EGI SPG. Participated in FIM4R meeting at ESRIN (April),gave talk on Authentication for P2P networking at LHCONE meeting in Rome, attended EUGridPMA meeting Estonia (May), REFEDS meeting in Dublin (May). Led AAI/FIM workshop at TNC2014 in Dublin in May. Attended TAGPMA meeting Salt Lake City (June) and first meeting of FIM and REFEDS community on security trust in operations for FIM (called SIRTFI building on my SCI work) in June. Planning for EGI security in H2020 era.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 2013-12-31 |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK NGI Argus server is fully in service. Still waiting for Argus delpoyment and appointment of replacement GridPP Security Officer
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2014-06-30 |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Spring/Summer 2015.

## Narrative Q314
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Chaired EGI CSIRT F2F meeting in Wroclaw, PL in August. Also lead UK NGI security team with fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. Attended EGI Big Data & Clouds meeting (Amsterdam, September) - Security for Clouds and AAI sessions. Ongoing work on EGI Cloud Security issues. Submitted several Horizon 2020 security bids. |  | John Green left in June 2013. The first attempt to replace via recruitment resulted in an offer to the preferred candidate but this was refused. A second attempt in the summer also failed. This post is now being re-advertised with a different thrust and requirements. Note that between DPK and LAC we are covering about two-thirds of the activities with strong support from the UK NGI security team.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. GridPP provides matching funding for the EGI.eu funded. Much work on vulnerability handling this quarter including Shellshock. Also handling data protection violations re xrootd and its monitoring. Attended EGI-InSPIRE EU Review (July).
Policy | Chair and lead EGI SPG. Participated in FIM4R meeting at RDA Amsterdam (Sep), attended EUGridPMA meeting Poland (Sep). Attend TAGPMA monthly meetings. Lead new SIRTFI activity to define Trust Framework for operational security in Federated Identity. Part of submitted AARC (Fed IdM) proposal to EU H2020. Attended EGI-InSPIRE EU review. Participated (remotely) in OGF working group meetings (12 Sep).
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 2013-12-31 |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus
C3.9: Security Workshop |  | 31/12/2014 (but held on 05/06/2014) |  | We decided to run this even early in collaboration with the summer UK HEP SYSMAN meeting.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2014-06-30 |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Spring/Summer 2015.

## Narrative Q414
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Chaired EGI CSIRT F2F meeting in Prague in December. Also lead the UK NGI security team with fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. Ongoing discussions and development work for EGI Cloud Security issues. |  | John Green left in June 2013. The first attempt to replace via recruitment resulted in an offer to the preferred candidate but this was refused. A second attempt in the summer also failed. This post was re-advertised before Christmas with a different thrust and requirements. A person has been appointed and is due to start on March 1st 2015. Note that between DPK and LAC we are covering about two-thirds of the activities with strong support from the UK NGI security team.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. An essential component of EGI/WLCG security operations. GridPP provides matching funding for the EGI.eu funded work. Much work on vulnerability handling this quarter.
Policy | Continue to lead EGI SPG and WLCG security policy. Chaired WLCG security annual meeting at FNAL in November discussing main issues and plans for the future. Attended TAGPMA monthly meetings. Lead Sirtfi activity to define Trust Framework for operational security in Federated Identity. Gave talks on this at REFEDS and ACAMP as part of Internet2/ESnet TechX meeting in Indianapolis (Oct). Member of RCUK/JISC eInfrastructure Security and AAI working group. One meeting held this quarter.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 2013-12-31 |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. A task for the new security officer once in post and up to speed.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2014-06-30 |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Spring/Summer 2015.

## Narrative Q115
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Also lead the UK NGI security team with fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. Ongoing discussions and development work for EGI Cloud Security issues. Successful security training workshop at ISGC2015 Taipei in March. New UK NGI Security Officer (Ian Neilson) started at the end of February.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. An essential component of EGI/WLCG security operations. GridPP provides matching funding for the EGI.eu core funded work. Much work on vulnerability handling this quarter.
Policy | Continue to lead EGI SPG and WLCG security policy. Chaired SCI meeting in Berlin (January) Attended TAGPMA monthly meetings. Lead Sirtfi activity to define Trust Framework for operational security in Federated Identity. Member of RCUK/JISC eInfrastructure Security and AAI working group. One meeting held this quarter. Preparing for start of EGI-Engage and AARC H2020 projects.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 2013-12-31 |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. A task for the new security officer once in post and up to speed.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2014-06-30 |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Autumn 2015 after the results of the GridPP5 bid are known.

## Narrative Q215
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Ian Neilson now established in post and has taken over leadership of the UK NGI security team with fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. Improving and documenting EGI procedures and ticket handling has been an important success of this quarter. Ongoing discussions and development work for EGI Cloud Security issues. Successful security training workshop at the UK HEP SYSMAN meeting. |  | The total effort booked for Security in Q2 2015 is larger than the 1.5 FTE allocated. Work on the related EU H2020 projects will increase during the remaining 3 quarters of the FY so less effort will be charged to GridPP in future. The integrated spend over the year will fit the allocation.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group, 14 new vulnerabilities were reported during the quarter. This work is an essential component of EGI/WLCG security operations and GridPP provides matching funding for this EGI.eu core funded work. New SVG procedures have been drafted to take account of greater usage of VMs and Cloud Technology and the greater diversity of software deployed on the infrastructure (much of this done with EGI-Engage funding). New members with expertise in Cloud technology have joined SVG. Plans were presented at the EGI Conference and UK HEP SYSMAN.
Policy | Continue to lead EGI SPG and WLCG security policy. Produced new draft policy documents (4 of them) and much activity on a new Data Protection policy for WLCG/EGI. Attended EUGridPMA and TAGPMA meetings. Leadership of the Sirtfi activity now being done by CERN to define Trust Framework for operational security in Federated Identity. Work on EGI-Engage and AARC H2020 projects (the unfunded work from GridPP point of view) has started with good planning sessions at the EGI Conference in Lisbon, the AARC kickoff meetings and TNC2015. Planning for a joint EGI/EUDAT/GEANT/PRACE security workshop in October.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 31/12/2013 (new date 31/12/2015) |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson and Ewan Macmahon will run a full test in Q4.
C3.13 Security Plans for the future |  | 30/06/2014 (new date 31/12/2015) |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Q4 2015 after the results of the GridPP5 bid are known.

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes