## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q315 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 191% | 191% | 190.8% | 358% | 358% | 358.2% | 112% | 308% | 308.1% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 112% | 200% | 319.2%
.x.2 | % of promised (by that time) CPU available | 100% | 1052% | 1052% | 1052% | 469% | 469% | 469.5% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 559% | 472% | 553.6%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 98% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 99%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 98% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 99%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 100% | 13% | 0% | 100% | 100% | 0% | 99% | 95% | 0% | [9 empty] | 49% | 50% | 0% | Issues with Steve Lloyd metrics running at many sites.
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 54% | 61% | 84.36% | 22% | 19% | 13.53% | 50% | 46% | 44.21% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 66% | 40% | 43.4%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 46% | 64% | 83.93% | 19% | 20% | 21.73% | 48% | 33% | 58.13% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 47% | 36% | 54.07%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q315
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2015-07-01 | 2015-08-01 | 2015-09-01 | Total |  | Site | 2015-07-01 | 2015-08-01 | 2015-09-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 3314624 | 6677968 | 7940276 | 17932868 |  | DURHAM | 3588264 | 6634868 | 7802432 | 18025564
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 1628160 | 3185076 | 2116592 | 6929828 |  | ECDF | 944356 | 1820668 | 1550720 | 4315744
[8 empty] | GLASGOW | 22621700 | 14247916 | 19446884 | 56316500 |  | GLASGOW | 15336432 | 14141312 | 13349680 | 42827424
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 27564484 | 24110960 | 29503752 | 81179196 |  | Total | 19869052 | 22596848 | 22702832 | 65168732
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 9677 | 53.424 | 920 | 28 | 1052% | 190.8% | 14.23% | 1.396% | 17932868 | 22.09% | 2208 | 21366816 | 83.93% | 84.36%
ECDF | 14445.2 | 1185.793 | 3077 | 331 | 469.5% | 358.2% | 21.24% | 30.98% | 6929828 | 8.536% | 2208 | 31895001.6 | 21.73% | 13.53%
GLASGOW | 43878 | 2588 | 8287 | 840 | 529.5% | 308.1% | 64.53% | 67.62% | 56316500 | 69.37% | 2208 | 96882624 | 58.13% | 44.21%
Totals | 68000.2 | 3827.217 | 12284 | 1199 | 553.6% | 319.2% | 100% | 100% | 81179196 | 100% | 2208 | 150144441.6 | 54.07% | 43.4%
Please check the figures in the Yellow
| MoU figures taken from S.Lloyds spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 216 | 9676.8 | 53.424 | 2419200 | DURHAM
ECDF | 568 | 43249.024 | 945.793 | 10812256 | ECDF | NOTE: Above ECDF is a combination of ECDF + ECDF-RDF
ECDF-RDF | 0 | 0 | 240 | 0 | ECDF-RDF
GLASGOW | 573 | 43878 | 2588 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q315
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | total | fraction used | Site percentage non LHC
DURHAM | 1.4 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [11 empty] | 9.17 | 0.2694% | 84.73%
ECDF | 896 | [14 empty] | 2 | 50 |  |  |  |  | 0 | [12 empty] | 948 | 27.85% | 0%
GLASGOW | 2430 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 2446.428 | 71.88% | 0.6302%
Total | 3327.4 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 2 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 3403.598 | 100% | 2.15%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q315
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Oliver Smith | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Durham | Liam Skinner | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.3 | 0.3 | 0.3
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G Qin | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 1 | 1 | 1 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0 | 0 | 0 | 0.5 | 0.5 | 0.5
Total |  | 4.75 | 4.75 | 4.75 | 1.1 | 1.1 | 1.1
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q315
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Installed new WN hardware, increasing our compute capacity by 35%. Deployed clustered storage using new WN hardware, added additional 24tb storage to cluster |  | Contacted central IT for IPV6 reverse DNS support, on hold until new network core is rolled out later this year. Hope to revisit this before the end of the year. Manpower reduction due to long term sick leave.
ECDF | Dialog opened with university network team to work on IPv6 testing and deployment. Currently testing dual-stack perfsonar services and will continue testing with middleware as part of wider rollout plans across the university. HPC resource demonstrator: standalone full simulation of 1 million ATLAS events on Archer supercomputer completed successfully, production integration with VO (ATLAS) distributed computing frameworks now underway. |  | Reduction in staff, awaiting position to be filled.
GLASGOW | Initial install of ViaB was successful, next steps are to create experiment queues and potentially try Vcycle. Hardware repaired for OpenStack instance, new neutron hardware located. Test Centos7 DPM tested and reported to DPM collaboration. |  | Severed fibre connection between server room and main campus router led to lowered availability,
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Ongoing reduction in manpower at ECDF, no site coverage available when A. Washbrook is on leave. |  | Role advertised last month and looking to fill the post by start of Q415. Passive coverage of site is occasionally provided by Glasgow
Institute or area specific risks
Risk |  | Mitigating Action
Edinburgh: New shared cluster will exclusively run on Scientific Linux 7 which is currently unsupported by all the VOs supported by the site |  | Working with LHC VOs on compatibility testing to allow SL6-based software to be run on SL7 platform. The ECDF systems team have suggested partitioning small section of cluster resources for SL6 use if a solution cannot be found before the existing SL6 cluster retirement at the end of the year.
Edinburgh: Critical systems (e.g storage head node) have recently fallen out of warranty |  | Replace systems using GridPP4+ equipment funding
Glasgow: Infrastructure including power, air con and space. |  | Additional funding secured by GU Scotgrid staff to improve both power and air con by procuring a small data facility to host equipment.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Edinburgh: Eddie Mk3 workload testing and middleware integration |  | 2015-09-30 |  | Work ongoing work with ECDF support team
Edinburgh: Working with ECDF on continuing integration of analytics tools for resource monitoring |  | 2015-09-30 |  | Work stalled in last quarter but will revisit effort with new ECDF computing resources
Durham: Install new WN hardware |  | 2015-09-30 |  | Completed
Durham: Contact Central IT regarding IPv6 reverse DNS |  | 2015-09-30 |  | Contacted, on hold awaiting install of new network core.
Glasgow: Contact Central IT regarding IPv6 reverse DNS |  | 2015-09-30 |  | Contacted, Central IT ongoing deployment of production DNS
Glasgow: Repair Compute Element HW for cloud deployemt |  | 2015-09-30 |  | Hardware installed and test Openstack underway
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Duhram: Further purchase and installation of WN hardware, switching capacity upgrades and additional disk server |  | 2015-01-01 |  | Installed and configured Hardware
Durham: Negotiate new bandwidth limit with central IT once new 10gbit Janet connection is installed |  | 2015-01-01 |  | Agreement with Central IT
Edinburgh: Eddie Mk3 workload testing and middleware integration |  | 2015-01-01 |  | Jobs from supported VOs running on the new cluster by the end of the year pending a full switch over from existing resource.
Glasgow: Complete Openstack deployment, along with object store |  | 2015-01-01 |  | Working Openstack instance
Glasgow: Allocate more resources to VAC testing and request Experimental Queues. |  | 2015-01-01 |  | Queue instances set up and hardware available.
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
GridPP Storage post based at Edinburgh has been filled. The successful candidate will start early November |  | Ongoing
Dissemmination events |  | Date |  | Notes
Dealing with Data conference (University of Edinburgh) From raw data to new fundamental particles: The data management lifecycle at the Large Hadron Collider |  | 2015-08-31 |  | Andrew Washbrook
GridPP 35 - Processing LHC Workloads on Archer |  | 2015-09-11 |  | Andrew Washbrook
ATLAS software development tutorial: Performance and Monitoring Tools |  | 2015-09-14 |  | Andrew Washbrook
GridPP 35 - Security and Traceability |  | 2015-09-11 |  | David Crooks
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Cloud Traceability TF |  | Present |  | David Crooks
Member of SQUID Monitoring TF |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
Active members of Multi-core taskforce (representing Scotgrid distributed Tier 2) |  | Present |  | Attended by S. Skipsey
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
Co-chair of ATLAS future software and technology forum, |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A