## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q415 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 191% | 191% | 190.8% | 358% | 358% | 358.2% | 308% | 308% | 308.1% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 112% | 200% | 319.2%
.x.2 | % of promised (by that time) CPU available | 100% | 1052% | 1052% | 1818% | 469% | 469% | 469.5% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 559% | 472% | 610.9%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 98% | 98% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 99%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 98% | 100% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 100%
.x.5 | Average SLL untargeted ATLAS test performance (UK test) | 95% averaged over sites in Tier-2 | 100% | 13% | 0% | 100% | 100% | 0% | 99% | 95% | 0% | [9 empty] | 49% | 50% | 0% | Issues with Steve Lloyd metrics running at sites (c.f. Hammercloud)
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 61% | 84% | 71.12% | 19% | 14% | 33.14% | 46% | 44% | 72.66% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 66% | 40% | 64.71%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 64% | 84% | 58.33% | 20% | 22% | 26.77% | 33% | 58% | 60.65% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 47% | 36% | 53.61%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q415
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total |  | Site | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 7995273 | 8517116 | 5025202 | 21537591 |  | DURHAM | 9953703 | 9486328 | 6821028 | 26261059
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 2321572 | 2725404 | 3490200 | 8537176 |  | ECDF | 2893642 | 3157139 | 4518450 | 10569231
[8 empty] | GLASGOW | 20446070 | 22583647 | 15731932 | 58761649 |  | GLASGOW | 23162296 | 24765308 | 22470380 | 70397984
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 30762915 | 33826167 | 24247334 | 88836416 |  | Total | 36009641 | 37408775 | 33809858 | 107228274
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 16724 | 53.424 | 920 | 28 | 1818% | 190.8% | 22.28% | 1.396% | 21537591 | 24.24% | 2208 | 36926592 | 58.33% | 71.12%
ECDF | 14445.2 | 1185.793 | 3077 | 331 | 469.5% | 358.2% | 19.25% | 30.98% | 8537176 | 9.61% | 2208 | 31895001.6 | 26.77% | 33.14%
GLASGOW | 43878 | 2588 | 8287 | 840 | 529.5% | 308.1% | 58.47% | 67.62% | 58761649 | 66.15% | 2208 | 96882624 | 60.65% | 72.66%
Totals | 75047.2 | 3827.217 | 12284 | 1199 | 610.9% | 319.2% | 100% | 100% | 88836416 | 100% | 2208 | 165704217.6 | 53.61% | 64.71%
Please check the figures in the Yellow
| MoU figures taken from S.Lloyds spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 216 | 16724 | 53.424 | 2419200 | DURHAM
ECDF | 568 | 43249.024 | 945.793 | 10812256 | ECDF | NOTE: Above ECDF is a combination of ECDF + ECDF-RDF
ECDF-RDF | 0 | 0 | 240 | 0 | ECDF-RDF
GLASGOW | 573 | 43878 | 2588 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q415
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | total | fraction used | Site percentage non LHC
DURHAM | 1.4 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [11 empty] | 9.17 | 0.2694% | 84.73%
ECDF | 896 | [14 empty] | 2 | 50 |  |  |  |  | 0 | [12 empty] | 948 | 27.85% | 0%
GLASGOW | 2430 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 2446.428 | 71.88% | 0.6302%
Total | 3327.4 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 2 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 3403.598 | 100% | 2.15%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q415
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Oliver Smith | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Durham | Liam Skinner | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | M. Ebert | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.3 | 0.3 | 0.3
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G Qin | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 1 | 1 | 1 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0 | 0 | 0 | 0.5 | 0.5 | 0.5
Total |  | 4.75 | 4.75 | 4.75 | 1.1 | 1.1 | 1.1
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q415
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Carried out tender for new equipment to expand the Grid resources.
ECDF | Marcus Ebert joined the Edinburgh group to work on storage management for GridPP and LSST Collaborated with ATLAS and LHCb software groups to test if their software is compatible with the SL7 operating system. This will be required for successful running on the new Eddie Mk3 compute cluster. We were able to test and validate a patch now included in the ATLAS software setup chain which will help SL7-based queues elsewhere in the future.
GLASGOW | Finalised deployment of Openstack, initial testing and preparing to allow vcycle workloads.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
Edinburgh: New shared cluster will exclusively run on Scientific Linux 7 which is currently unsupported by all the VOs supported by the site |  | Worked with LHC VOs on compatibility testing to allow SL6-based software to be run on an SL7 platform. Some progress made (see above) but validation on the new cluster is still ongoing. We will have access to a small section of cluster resources for SL6 use in the short term if there are any major incompatibility issues that need to be addressed.
Edinburgh: Critical systems (e.g storage head node) have recently fallen out of warranty |  | Replace systems using GridPP4+ equipment funding
Glasgow: Infrastructure including power, air con and space. |  | ScotGrid working with local Estates to procure Data facility
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Durham: Further purchase and installation of WN hardware, switching capacity upgrades and additional disk server |  | 2015-01-01 |  | Equipment has arrived and will be comissioned this quarter
Durham: Negotiate new bandwidth limit with central IT once new 10gbit Janet connection is installed |  | 2015-01-01 |  | Will be receiving 4Gbit beginning Feb 2016
Edinburgh: Eddie Mk3 workload testing and middleware integration |  | 2015-01-01 |  | Integration still underway with full migration to the new cluster expected to be completed this quarter. The original deadline set by ECDF (end of December) has now been pushed back due to issues in validating their high performance storage (used by non-grid users). We will now get assistance from the ECDF systems team to help with the transition.
Glasgow: Complete Openstack deployment, along with object store |  | 2015-01-01 |  | Openstack deployment was completed, whowever object store deployment was on hold while discussion continued around technology
Glasgow: Allocate more resources to VAC testing and request Experimental Queues. |  | 2015-01-01 |  | After discussion focus was to be moved to vcycle and use of the the openstack instance
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Edinburgh: Eddie Mk3 workload testing and middleware integration |  | 2016-04-01 |  | Jobs from supported VOs running on the new cluster by the end of the quarter. Jobs running on the old cluster will cease as soon as possible pending a successful switchover.
Edinburgh: RDF Storage Enhancement |  | 2016-04-01 |  | Update and add DPM head node services for access to storage at the Research Data Facility (RDF). We already have a test DPM connected to this storage which we would now like to convert into a production instance.
Glasgow: Deploy centralised account management |  | 2016-04-01 |  | Replace account management at Glasgow with centralised account managemnt system.
Glasgow: Retire/Replace SL5 systems |  | 2016-04-01 |  | Retire or replace all systems running SL5, with either Centos 6 or 7 where appropriate
Glasgow: Investigate security technologies in conjunction with CERN |  | 2016-03-01 |  | Report on progress at March GDB
Durham: Commsion new equipment. |  | 2016-04-01 |  | Commision newly arrived equipment.
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
GridPP - Security and Traceability |  | 2015-09-11 |  | D. Crooks
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Cloud Traceability TF |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
Co-chair of ATLAS future software and technology forum, |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A