## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q116 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 191% | 191% | 858.6% | 358% | 358% | 358.2% | 308% | 308% | 308.1% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 112% | 200% | 334.8%
.x.2 | % of promised (by that time) CPU available | 100% | 1052% | 1818% | 3076% | 469% | 469% | 469.5% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 559% | 472% | 636.1%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 98% | 100% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 100%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 98% | 100% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 100%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 61% | 71% | 64.78% | 19% | 33% | 24.71% | 46% | 73% | 66.01% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 66% | 40% | 57.93%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 64% | 58% | 50.79% | 20% | 27% | 19.86% | 33% | 61% | 51.15% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 47% | 36% | 45.24%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q116
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2016-01-01 | 2016-02-01 | 2016-03-01 | Total |  | Site | 2016-01-01 | 2016-02-01 | 2016-03-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 6401766 | 12334285 | 12657111 | 31393162 |  | DURHAM | 7617044 | 14822992 | 17603020 | 40043056
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 3850885 | 923260 | 1492020 | 6266165 |  | ECDF | 4871758 | 1143705 | 1781382 | 7796845
[8 empty] | GLASGOW | 11639409 | 15284822 | 12621097 | 39545328 |  | GLASGOW | 14519181 | 18358004 | 18152220 | 51029405
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 21892060 | 28542367 | 26770228 | 77204655 |  | Total | 27007983 | 34324701 | 37536622 | 98869306
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2014) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 28301 | 240.417 | 920 | 28 | 3076% | 858.6% | 36.22% | 5.989% | 31393162 | 40.66% | 2184 | 61809384 | 50.79% | 64.78%
ECDF | 14445.2 | 1185.793 | 3077 | 331 | 469.5% | 358.2% | 18.49% | 29.54% | 6266165 | 8.116% | 2184 | 31548316.8 | 19.86% | 24.71%
GLASGOW | 35397 | 2588 | 8287 | 840 | 427.1% | 308.1% | 45.3% | 64.47% | 39545328 | 51.22% | 2184 | 77307048 | 51.15% | 66.01%
Totals | 78143.2 | 4014.21 | 12284 | 1199 | 636.1% | 334.8% | 100% | 100% | 77204655 | 100% | 2184 | 170664748.8 | 45.24% | 57.93%
Please check the figures in the Yellow
| MoU figures taken from S.Lloyds spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 264 | 28301 | 240.417 | 2419200 | DURHAM
ECDF | 568 | 43249.024 | 945.793 | 10812256 | ECDF | NOTE: Above ECDF is a combination of ECDF + ECDF-RDF
ECDF-RDF | 0 | 0 | 240 | 0 | ECDF-RDF
GLASGOW | 573 | 35397 | 2588 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q116
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | total | fraction used | Site percentage non LHC
DURHAM | 1.4 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [11 empty] | 9.17 | 0.2694% | 84.73%
ECDF | 896 | [14 empty] | 2 | 50 |  |  |  |  | 0 | [12 empty] | 948 | 27.85% | 0%
GLASGOW | 2430 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 2446.428 | 71.88% | 0.6302%
Total | 3327.4 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 2 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 3403.598 | 100% | 2.15%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q116
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Oliver Smith | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Durham | Liam Skinner | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | M. Ebert | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.3 | 0.3 | 0.3
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G Qin | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 1 | 1 | 1 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0 | 0 | 0 | 0.5 | 0.5 | 0.5
Total |  | 4.75 | 4.75 | 4.75 | 1.1 | 1.1 | 1.1
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q116
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | New hardware has been commissioned. 36 nodes and single new disk server have replaced 3 old unreliable disk servers. 864 additional CPU cores. |  | Issues with network connectivity due to upgraded Janet links.
ECDF | Test middleware service attached to the Archer supercomputer can accept Grid jobs. ATLAS test queue is now enabled and we are working with ATLAS distributed computing to provide a reliable production resource. Secured short term manpower to work in this area and we will be supervising an MSc student to look into HPC workload optimisation. Testing storage usage for LSST and implementing one kind of the LSST computing workflows into GridPP computing using the dirac cli. Testing ZFS on Linux as a new storage backend. |  | Due to decommising of Eddie Mk2 and migration to SL7 on Eddie Mk3 resources provided by ECDF have been reduced this Quarter. This is expected to improve next quarter when migration to Eddie Mk3 is completed.
GLASGOW | Continued wirth OpenStack work and deployment, moving to new release of Liberty. Reconfiuguring networking so that it can be more reliable and easier to manage. Investigation into using FreeIPA as a IdM platform continues, new hardware arriving next Quarter to allow work to be moved into production |  | Due to damage associated with a a power failure on Jan 1 2016, 8481 HEPSPEC was lost at the site. Due to issues with procurement replacement Tranche hardware was not delivered until the end of this quarter.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Remaining tasks of the migration to new ECDF cluster do not go to plan |  | The ECDF systems team will not close down our access to the present cluster whilst any issues remain. We agreed on a two week burn-in window where we have access to both clusters before a final sign off. However any extension will not be indefinite due to hardware retirement and power considerations at the Advanced Computing Facility.
Glasgow: Air Condition/power issues leading to damaged equipment |  | Working with E&B to supply new data facility.
Glasgow: Staff loss, Gang Qin leaving for Sussex at the end of this Quarter |  | Documentation produced on HTCondor, ARC-CE and CGMEMD
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Edinburgh: Eddie Mk3 workload testing and middleware integration |  | 2016-04-01 |  | Issues with new high performance storage on the new cluster (unrelated to our grid storage offering) have resulted in delays with ECDF personnel having time to work with GridPP on migrating our workload to the new setup. This work is now ongoing and we expect migration to be done within the next month (assuming there are no unexpected problems with the remainder of the migration tasks)
Edinburgh: RDF Storage Enhancement |  | 2016-04-01 |  | Had discussions with RDF personnel to determine best long term solution. Deployment put on hold whilst our primary storage was upgraded. We will move RDF storage into production once our site DPM service has been migrated to new middleware platform
Glasgow: Deploy centralised account management |  | 2016-04-01 |  | On hold until new hardware is installed, original hardware designated was found to be faulty with install of new OS
Glasgow: Retire/Replace SL5 systems |  | 2016-04-01 |  | All services oither than DPM and WMS migrated to Centos6. WMS will be retired this quarter, DPM wil be upgraded this quarter
Glasgow: Investigate security technologies in conjunction with CERN |  | 2016-03-01 |  | Presented onging work at GDB, investigation MSIP ongoing
Durham: Commsion new equipment. |  | 2016-04-01 |  | New hardware commissioned
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Retire WMS |  | 31-Apr-16 |  | WMS and all components will be removed from the GOCDB
Glasgow: Upgrade DPM to Centos6 |  | 31-Apr-16 |  | DPM Upgraded to Centos6
Glasgow: Install Tranche hardware |  | 31-Apr-16 |  | New hardware added to resource allocation
Durham:Replacing virtual hosts which host grid services. |  | 2016-06-30 |  | Hosts upgraded to CentOS 7 where possible and appropriate
Durham: Replacing virtual SE and one virtual CE with a physical hosts to improve performance |  | 2016-06-30 |  | New SE & CE operational on hardware
Durham: Installing additional new nodes |  | 2016-06-30 |  | Hardware Comissioned
ECDF: Ugrade Storage to SL6, change backend to ZFS |  | 2016-06-30 |  | Pool nodes on SL6
ECDF: Virtualisation of Middle ware services |  | 2016-06-30 |  | Migrate services to a virtualised platform.
ECDF: Eddie Mk3 migration |  | 2016-06-01 |  | Complete migration to Eddie Mk3 cluster and move key services to new middleware platform
ECDF: RDF Storage Replacement |  | 2016-07-01 |  | Update DPM services to access to storage at the Research Data Facility (RDF).
ECDF: Optimisation for LHC workloads on HPC |  | 2016-09-01 |  | Provide detailed study into optimising LHC workload on Archer
ECDF: Data processing for EUCLID |  | 2016-10-01 |  | Work with members of EUCLID experiment at Edinburgh to provide a Grid interface to their data processing pipeline
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Marcus Ebert 50% LUSC DAC Team
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
Gang Qin - Sussex University |  | 2016-04-01 |  | Gang has moved to Sussex as the Grid admin there.
Dissemmination events |  | Date |  | Notes
GDB |  | 2016-03-07 |  | David Crooks - Security Operations Centre Update (with Liviu Valsan)
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Cloud Traceability TF |  | Present |  | David Crooks
SOC Working Group |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
Co-chair of ATLAS future software and technology forum, |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A