## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q216 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 319% | 319% | 240.3% | 381.2% | 381.2% | 281.5% | 246.5% | 246.5% | 204.2% | 305.3% | 248.4% | 145.8% |  |  | 0% | 259.5% | 303.2% | 214.5%
.x.2 | % of promised (by that time) CPU available | 100% | 533.9% | 646.4% | 373.7% | 205.5% | 205.5% | 160% | 302.4% | 302.4% | 313.3% | 320.7% | 320.7% | 447.3% |  |  | 0% | 291.1% | 304.9% | 278.3%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% |  |  |  | 99.8% | 99.75% | 100%
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% |  |  |  | 99.8% | 99.75% | 100%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 64.67% | 44.79% | 75.56% | 91.92% | 76.12% | 86.06% | 41.89% | 71.13% | 108.9% | 71.12% | 70.82% | 62.57% |  |  |  | 74% | 66.35% | 83.64%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 50.16% | 26.6% | 44.78% | 83.62% | 68.09% | 68.19% | 40.86% | 57.41% | 91.81% | 85.74% | 54.83% | 53.32% |  |  |  | 70% | 61.82% | 64.72% | Brunel low
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q216
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  | SITE | 2016-04 | 2016-05 | 2016-06 | Total |  | SITE | 2016-04 | 2016-05 | 2016-06 | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 11036676.475 | 11858512.2232 | 12316324.5895 | 35211513 |  | UKI-LT2-Brunel | 20219188.9185 | 21290192.2467 | 17895188.6453 | 59404570
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 18650339.215 | 15854792.315 | 17719314.3901 | 52224446 |  | UKI-LT2-IC-HEP | 22208261.31 | 20491951.225 | 23211023.174 | 65911236
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 21737108.1108 | 29415000.8076 | 24822288.6583 | 75974398 |  | UKI-LT2-QMUL | 28811179.7983 | 33315257.0492 | 27990197.7102 | 90116635
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 10066395.2729 | 6194937.6294 | 27679310.8452 | 43940644 |  | UKI-LT2-RHUL | 12432564.8209 | 8218511.9752 | 30911977.8406 | 51563055
[8 empty] | UKI-LT2-UCL-HEP | 418789.0938 | 145193.2721 | 261854.1918 | 825837 |  | UKI-LT2-UCL-HEP | 491645.8025 | 170977.8464 | 286819.4482 | 949443
[8 empty] | Total | 61909308 | 63468436 | 82799093 | 208176837 |  | Total | 84162841 | 83486890 | 100295207 | 267944938
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 36000 | 1100 | 9632.812 | 457.8006 | 373.7% | 240.3% | 24.54% | 12.04% | 35211513 | 16.98% | 2184 | 78624000 | 44.78% | 75.56% | 59.27%
UKI-LT2-IC-HEP | 35068.4 | 3699 | 21915.766 | 1313.8219 | 160% | 281.5% | 23.91% | 40.47% | 52224446 | 25.19% | 2184 | 76589385.6 | 68.19% | 86.06% | 79.23%
UKI-LT2-QMUL | 37890.25 | 2900 | 12094.921 | 1420.211 | 313.3% | 204.2% | 25.83% | 31.73% | 75974398 | 36.64% | 2184 | 82752306 | 91.81% | 108.9% | 84.31%
UKI-LT2-RHUL | 37730 | 1440 | 8434.349 | 987.6466 | 447.3% | 145.8% | 25.72% | 15.76% | 43940644 | 21.19% | 2184 | 82402320 | 53.32% | 62.57% | 85.22%
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 146688.65 | 9139 | 52714.598 | 4260.48 | 278.3% | 214.5% | 100% | 100% | 207351001 | 100% | 2184 | 320368011.6 | 64.72% | 83.64% | 77.69%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 4566 | 54563 | 1387
UKI-LT2-IC-HEP | 4460 | 41210 | 3613
UKI-LT2-QMUL | 2724 | 32211 | 3164
UKI-LT2-RHUL | 3824 | 36204 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 164188 | 9624 |  | 0
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx
Note on E34: gronbech:Gstat displays SI2000 so this needs converting to HS06

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q216
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cedar | cernatschool.org | comet.j-parc.jp | cms | dteam | dzero | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | ilc | ipv6.hepix.org | lhcb | lz | mice | na48 | na62.vo.gridpp.ac.uk | neiss.org.uk | ngs.ac.uk | ops | pheno | snoplus.snolab.ca | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | vo.helio-vo.eu | vo.landslides.mossaic.org | vo.londongrid.ac.uk | zeus | Total
UKI-LT2-Brunel | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 1 | 1 | 21
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 23
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 22
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 15
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 1 | 4 | 4 | 2 | 3 | 1 | 1 | 1 | 4 | 4 | 2 | 1 | 2 | 1 | 4 | 3 | 2 |  | 1 | 4 | 1 | 4 | 1 | 1 | 1 | 1 | 4 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 3 | 81
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | lsst | cernatschool.org | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.357 |  | 0.304 |  |  |  | 0.065 | 833.198 |  | 34.372 | 0.017 | 0.003 |  |  |  |  | 1.691 | [6 empty] | 0.149 |  |  |  |  | 0.202 | [6 empty] | 0.019 |  | 0 |  |  |  | 870.377 | 14.15% | 0.3225%
UKI-LT2-IC-HEP |  | 30.291 | 0 |  | 0 |  | 0 | 1598.9185 |  | 14.48 |  |  |  |  | 220.803 |  |  |  | 0 | [15 empty] | 29.679 |  |  | 86.371 |  |  | 21.27 | 2001.8125 | 32.54% | 8.373%
UKI-LT2-QMUL |  | 79 | 0.814 |  |  | 0 |  | 8.7 |  | 2000 | 0.052 |  |  |  | 11 |  | 0.673 | 0.0068 |  |  |  | 0.016 | 0.013 | 0.319 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 7 |  |  |  | 0 | 0.1 | 0 |  | 2107.718 | 34.26% | 4.176%
UKI-LT2-RHUL | 0 |  | 0.471 |  |  |  |  | 1.06 |  | 1170.099 | 0.015 | 0 |  |  |  |  | 0.19 | [5 empty] | 0.005 | 0.27 | [6 empty] | 0.01 | 0 | [5 empty] | 0 |  |  |  | 1172.12 | 19.05% | 0.08199%
Total | 0.357 | 109.291 | 1.589 | 0 | 0 | 0 | 0.065 | 2441.8765 | 0 | 3218.951 | 0.084 | 0.003 | 0 | 0 | 231.803 | 0 | 2.554 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.018 | 0.738 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.01 | 0 | 0.019 | 7 | 29.679 | 0.019 | 0 | 86.371 |  |  | 21.27 | 6152.0275 | 100% | 4.216%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q216
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3
| Ivan Reid | 0.7 | 0.7 | 0.7 | 0.15 | 0.15 | 0.15
| P. Hobson | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 1; GridPP Funded Month 2: 0.75; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| network team + Alex Owen/Cozmin | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| B.Green/Tom | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 7.4 | 7.15 | 6.9 | 1.9 | 1.9 | 1.9

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q216
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | Adding new hardware: - new disk server; - 100 cores that are configured on C7 running CMS in containers. - Ivan Reid involved in CMS@home.
UKI-LT2-IC-HEP | Attended IPv6 F2F and pre-GDB meetings at CERN. Tuning of inbound FTS transfers.
UKI-LT2-QMUL | Installation and commissioning of new kit (31 DL60 compute nodes 10K hepspec). Installation and testing of two new HP Apollo 4200 storage boxes (150TB usable per box). Have obtained a Nvidia K40 gpgpu and brought 2 K80s for the grid cluster. Have worked with cream CE developers to enable submission of jobs with gpu requirements (https://wiki.egi.eu/wiki/GPGPU-CREAM) via gridengine. Have setup slurm batch system on (new hardware for master) with cgroups capabilities and gpu resources. tested with cream CE and ops/dteam. Have started process of testing LHC VOs with new system Development of new deployment system Improved health and safety risk assessment and loan working procedures for data centre Preparations and in depth discussions with Universities network team about improved science DMZ while allowing other parts of the university to use the Intrusion detection system (limited to 10G) on both university links. IPV6 discussions with Universities network team with aim to put IPv6 on to worker nodes requiring routing changes.
UKI-LT2-RHUL | - Site issues :- downtime due to network switch config issue - New kit commissioned
UKI-LT2-UCL-HEP | VAC now working for ATLAS.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes