## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q2 2016 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 250% | 273% | 184% | 210% | 208% | 151.5% | 130% | 210% | 147.9% | 178% | 190% | 136.2% | 159.2% | Big difference between Q-1 and current Quarter figures due to using new MoU numbers.
.x.2 | % of promised (by that time) CPU available | 100% | 599% | 666% | 442.9% | 411% | 325% | 175.5% | 395% | 487% | 313.9% | 561% | 564% | 334.4% | 323.4% | Same with these figures.
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 99.75%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 99.75%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 25% | 36% | 62.12% | 63% | 90% | 105.2% | 51% | 82% | 79.62% | 15% | 36% | 61.76% | 73.96%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 36% | 30% | 53.74% | 73% | 84% | 96.56% | 72% | 75% | 65.71% | 31% | 31% | 35.4% | 61.75%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2016
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Site | 2016-04-01 | 2016-05-01 | 2016-06-01 | Total |  | Site | 2016-04-01 | 2016-05-01 | 2016-06-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 14169175 | 18043077 | 21872221 | 54084473 |  | Lancaster | 17468121 | 21311579 | 23735447 | 62515147
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 11475355 | 10304212 | 6827141 | 28606708 |  | Liverpool | 12534281 | 11210419 | 7428531 | 31173231
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 22977890 | 20943292 | 19503983 | 63425165 |  | Manchester | 28579818 | 25770700 | 22505964 | 76856482
[7 empty] | Sheffield | 2883122 | 2810989 | 2471321 | 8165432 |  | Sheffield | 4341454 | 4675687 | 5225856 | 14242997
[7 empty] | Total CPU hrs | 48622420 | 49290581 | 48203345 | 146116346 |  | Total | 62923674 | 62968385 | 58895798 | 184787857
Current Resources Available | [6 empty] | Used dev accounting portal. | [5 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normcpu/SITE/DATE/2016/4/2016/6/all/onlygridjobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 46080 | 2300 | 10405 | 1250 | 442.9% | 184% | 40.28% | 37.43% | 54084473 | 35.06% | 2184 | 100638720 | 53.74% | 62.12%
Liverpool | 13565 | 1223 | 7729 | 807 | 175.5% | 151.5% | 11.86% | 19.91% | 28606708 | 18.54% | 2184 | 29625960 | 96.56% | 105.2%
Manchester | 44197 | 2090 | 14080 | 1413 | 313.9% | 147.9% | 38.63% | 34.02% | 63425165 | 41.11% | 2184 | 96526248 | 65.71% | 79.62%
Sheffield | 10560 | 531 | 3158 | 390 | 334.4% | 136.2% | 9.231% | 8.643% | 8165432 | 5.293% | 2184 | 23063040 | 35.4% | 61.76%
Totals | 114402 | 6144 | 35372 | 3860 | 323.4% | 159.2% | 100% | 100% | 154281778 | 100% | 2184 | 249853968 | 61.75% | 73.96%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 46080 | 2300 | NA | Lancaster
Liverpool | 1330 | 13565 | 1223 | NA | Liverpool
Manchester | 4494 | 44197 | 2090 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 9824 | 114402 | 6144 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2016
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | na48 | neiss | ops | pheno | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  | 1 |  | 1 | 0 |  | 1 | 1 | 1 | 0 | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1 | 0 | 1 |  |  | 1 |  |  | 1 | 1 | 19
Liverpool | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 31
Manchester |  | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 19
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 0 | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 19
Total | 2 | 4 | 1 | 4 | 1 | 3 | 1 | 1 | 4 | 4 | 3 | 1 | 2 | 1 |  | 2 | 4 | 3 |  | 2 | 4 | 1 |  | 2 | 2 | 1 |  | 4 | 3 | 3 | 1 | 1 | 4 | 2 | 3 | 4 |  | 88
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1500 | 0 | 16 | 6 | 1522 | 1.051% | 1.445%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3670.24 | 0.57 | 178 | 13.47 | 3970.46 | 4.483% | 4.837%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2016
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | bar: GridPP Funded Month 1 to GridPP Funded Month 3
M. Doidge | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| P. Love | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
Liverpool | S. Jones | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| R. Fay | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
| J. Bland | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Manchester | A. Forti | bar: GridPP Funded Month 1 to GridPP Funded Month 3
R. Frank | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| A. McNab | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Sheffield | E. Korolkova | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| M. Robinson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | EGI Funded Month 1: 0.5; EGI Funded Month 2: 0.5; EGI Funded Month 3: 0.5
Manchester | A. Forti | bar: Unfunded Month 1 to Unfunded Month 3

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q2
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Getting uboone jobs running SL7 tarball work SL7 feasibility tests Discussions with T2K to host more data. | uboone jobs! Prelim UI tarball, involvement with MR WG Moving towards SL7 next year T2K transfers work
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Slow to decommission SL5 pool nodes. |  |  | SL5 DPM still supported, big August downtime will be used to reinstall others.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | More VOs supported. Tarball work Cluster tweaks Upgrade Prep |  |  | 30/6/16 |  | Increased support New tarball releases, SL7 works started Better throughput A smoother cluster upgrade in August
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Cluster Upgrade in August IPv6 fist steps SL5 expunged Even more Vos supported |  |  | 2016-09-30 |  | Minimum downtime IPv6 at last Upgraded All Lancaster user groups represented.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q2
Reported by | S Jones, R Fay, J Bland
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Documentation Talks Talks Admin Admin Admin Admin Admin “ “ “ “ “ “ “ “ | Wrote intro -How to Enable CGROUPS on Condor Vac talk at Pitlochry (Gridpp36) Admin for 3 clusters, vac, condor, torque, Hepsysman Rebenchmarked all HW types in all cluster DB system for cluster layouts (vac, condor, torque) VAC work (mem/swap mon, fs types, MJFs, +nodes) Decomm. two CREAM CEs (not needed) Routines (tickets, ARGUS banning, VO/VOMS support (icecube, fermilab), certs, security updates, HW maint, rebuilds, space management) Roll out of expanded monitoring and metric collection based on sensu and graphite/collectd Recovered site from prolonged power cuts. Procured and installed new Grid WNs, 528TB of new RAID6 storage. Upgrading from YAIM-DPM 1.8.8 to Puppet-DPM 1.8.11. |  | 32 bit metric still used!
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | Still in discussion with CSD about IPv6 upgrades and removing network filtering. Centos7 VAC not yet used by many VOs |  | Still waiting - Need firmware update. Not in our control. Quite different to SL6. Will need testing for migration. Needs VM process to be automatic, easy and well defined.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | IPV6 Test System CSD Cluster Share + Explore Cloud Technologies VAC Centos7 Tests |  | 30/06/2016 30/06/2016 30/06/2016 |  | Still awaiting allocation. Asked for status. Done, but continue to expand to 800 slots. On going
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | IPV6 Test System CSD Cluster Share + Explore Cloud Technologies VAC Centos7 Tests Accounting system Data Flow Diagram VAC Monitoring system (Data collection, Elastic search, Kibana, Grafana and similar) Stubborn bug in ARC, kills tests, high priority |  | 31/09/2016 31/09/2016 31/09/2016 31/09/2016 31/09/2016 31/08/2016 |  | Waiting for firmware to allow this. Move to 800 slots Ongoing. Will try to get service nodes on. Possible option. Will clarify operation of subsystem. Prototype plotting system. Passes new argo-egi tests.

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q2
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | dune vo has been set up in Sheffield and tested. dune vo has been registered with EGI. Publishing was fixed in the last quater and torque server was tuned in this quater to allow more non-LHC vo's jobs to run. CPU utilization is up but new accounting portal shows smaller CPU numbers. This needs to be investigated. Analysis abailability for ATLAS ( ASAP metric) is 99%. |  |  | There is still a problem with Perfsonar server. Needs to ask to open more ports.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Moving grid servers to ipv6 configured may cause lots of problem. |  |  | Wait for gaining more experience and proper instructions for ipv6 configuration
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Dune vo is now supported by UK and running at Sheffield. Good site availability. There are still not enough open ports for personar server. |  |  | 30 June 2016
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Check accounting. Perfsonar: open the ports. |  |  | 2016-09-30
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes