## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q2 2016 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | EFDA JET |  |  | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 21.43% | 21.43% | 25% | 140.3% | 140.3% | 86.71% | 205.7% | 445.3% | 652.4% | 239.7% | 226% | 159.4% | 250% | 250% | 128.4% | 278% | 278% | 242.6% | 538.5% | 538.5% | 155.6% | 237.7% | 248.6% | 188.3%
.x.2 | % of promised (by that time) CPU available | 100% | 630.6% | 630.6% | 918.1% | 248.5% | 248.5% | 198.3% | 526.8% | 802% | 471.4% | 212.4% | 212.4% | 257% | 234.1% | 234.1% | 300.4% | 334.6% | 334.6% | 324.4% | 1521% | 1521% | 538.8% | 308.6% | 327.4% | 311.1%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 93% | 86% | 86% | 99% | 98% | 98%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 93% | 86% | 86% | 99% | 98% | 98%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 2.476% | 4.899% | 8.404% | 78.1% | 67.05% | 74.69% | 21.83% | 11.99% | 35.81% | 88.08% | 87.02% | 72.07% | 70.59% | 75.92% | 63.02% | 78.85% | 78.46% | 75.82% | 88.17% | 62.33% | 57.4% | 69.58% | 63.95% | 65.31%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 1.499% | 4.658% | 8.123% | 70.95% | 58.31% | 68.95% | 19.99% | 9.724% | 29.74% | 75.71% | 70.8% | 64.03% | 63.61% | 65.53% | 57.09% | 64.04% | 69.29% | 63.59% | 82.98% | 52.48% | 52.5% | 59.44% | 55.65% | 56.74%
bi
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2016
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
EFDA JET | EMI2 | EMI3/SL6 |  | 1Gb/s | 1Gb/s | DPM 1.8.8-4 (EMI3) |  | Site | 2016-04-01 | 2016-05-01 | 2016-06-01 | Total |  | Site | 2016-04-01 | 2016-05-01 | 2016-06-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 |  | EFDA JET | 134917.359 | 68013.8572 | 111437.1153 | 314368.3315 |  | EFDA JET | 136930.556 | 69201.07 | 119099.2861 | 325230.9121
Bristol | EMI-2/EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 6713590.7971 | 6497591.1333 | 5594635.4805 | 18805817.4109 |  | Birmingham | 7192372.9605 | 7091805.8637 | 6087572.3442 | 20371751.1684
Cambridge | EMI-3 | EMI-3/SL6 |  | 10Gb/s | 2*10Gb/s | DPM 1.8.11 |  | Bristol | 2738633.3188 | 2012227.7889 | 5540742.5701 | 10291603.6778 |  | Bristol | 3230797.5965 | 2578304.3969 | 6585478.963 | 12394580.9564
Oxford | EMI 3 | EMI 3/SL6 |  | 10Gb/s | 2*20Gb/s | DPM 1.8.10 |  | Cambridge | 2032581.6292 | 2946438.1611 | 3327951.1651 | 8306970.9554 |  | Cambridge | 2510748.3483 | 3303069.0476 | 3535381.6321 | 9349199.028
RALPP | UMD2/3 | UMD2/3 |  | 10Gb/s | 10Gb/s | Dcache 2.2 |  | Oxford | 10929275.8524 | 11028191.3742 | 10564982.8006 | 32522450.0272 |  | Oxford | 12212439.9187 | 12004666.1709 | 11686297.4472 | 35903403.5368
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 17875585.3217 | 22313354.0675 | 24111821.8118 | 64300761.201 |  | RALPP | 22883258.8007 | 25932559.488 | 27848215.6642 | 76664033.9529
[8 empty] | Sussex | 1005593.6527 | 712748.8398 | 548889.6661 | 2267232.1586 |  | Sussex | 1042814.116 | 821928.6119 | 614093.7385 | 2478836.4664
[8 empty] | Total CPU hrs | 41430177.9309 | 45578565.222 | 49800460.6095 | 136809203.7624 |  | Total | 49209362.2967 | 51801534.649 | 56476139.0753 | 157487036.021
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
EFDA JET | 1772 | 1.5 | 193 | 6 | 918.1% | 25% | 1.605% | 0.02693% | 314368.3315 | 0.2298% | 2184 | 3870048 | 8.123% | 8.404%
Birmingham | 12489 | 620 | 6298 | 715 | 198.3% | 86.71% | 11.31% | 11.13% | 18805817.4109 | 13.75% | 2184 | 27275976 | 68.95% | 74.69%
Bristol | 15847 | 959 | 3362 | 147 | 471.4% | 652.4% | 14.35% | 17.22% | 10291603.6778 | 7.523% | 2184 | 34609848 | 29.74% | 35.81%
Cambridge | 5940 | 330 | 2311 | 207 | 257% | 159.4% | 5.38% | 5.924% | 8306970.9554 | 6.072% | 2184 | 12972960 | 64.03% | 72.07%
Oxford | 26084 | 980 | 8682 | 763 | 300.4% | 128.4% | 23.62% | 17.59% | 32522450.0272 | 23.77% | 2184 | 56967456 | 57.09% | 63.02%
RALPP | 46300 | 2610 | 14274 | 1076 | 324.4% | 242.6% | 41.93% | 46.85% | 64300761.201 | 47% | 2184 | 101119200 | 63.59% | 75.82%
Sussex | 1977.32 | 70 | 367 | 45 | 538.8% | 155.6% | 1.791% | 1.257% | 2267232.1586 | 1.657% | 2184 | 4318466.88 | 52.5% | 57.4%
Totals | 110409.32 | 5570.5 | 35487 | 2959 | 311.1% | 188.3% | 100% | 100% | 136809203.7624 | 100% | 2184 | 241133954.88 | 56.74% | 65.31%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken |  | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
EFDA JET |  | 1327.104 | 1.968 | 331776 | EFDA JET | 1327 | 1.968
Birmingham |  | 12892.8 | 661 | 3223200 | Birmingham | 12894 | 661
Bristol |  | 10158.96 | 0 | 2539740 | Bristol | 9607 | 0
Cambridge |  | 5938.848 | 331 | 1484712 | Cambridge | 5940 | 331
Oxford |  | 3414.324 | 940 | 853581 | Oxford | 3196 | 940
RALPP |  | 21420 | 2646 | 5355000 | RALPP | 10710 | 2646
Sussex |  | 2007.552 | 83 | 501888 | Sussex | 2006 | 83
Totals |  | 57159.588 | 4662.968 | 14289897
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2016
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
EFDA JET | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 11
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [20 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[44 empty] | 0 | 0
[44 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 2 | 2 | 2 | 1 | 0 | 0 | 3 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 3 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 112
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
EFDA JET | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.0248% | 16.43%
Birmingham | 254 | 232 | 0.12 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0.2 | 0.02 |  | 0.53 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 488.501 | 12.44% | 0.5118%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.4 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.409 | 9.43% | 0.00189%
Cambridge | 0 | 262.8 | 0 | 0 | 0.09 | 0.02 | 0 | 0 | 0 | 0 | 0.004 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0 |  | 0 | 0 | 0.4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263.484 | 6.708% | 0.1078%
Oxford | 0 | 577 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 | 0.049 | 0.625 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 6.48 | 0.018 | 0.016 | 1.5 | 31.98 | 0 | 0 | 0.0234 | 618.8404 | 15.75% | 6.593%
RALPP | 1 | 658 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1130 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 378 |  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2175.6 | 55.39% | 0.3953%
Sussex |  | 9 | [8 empty] | 0.008 | [25 empty] | 1 |  |  | 0.176 |  |  |  |  | 10.184 | 0.2593% | 11.63%
Total | 255 | 1739.424 | 2.12 | 0.65 | 0.39 | 0.044 | 0 | 0 | 0 | 1501.411 | 0.169 | 0.049 | 0.635 | 0 | 0.025 | 0 | 0.37 | 0.055 | 0 | 2.534 | 0 | 378.622 | 0 | 0 | 2 | 1 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 7.48 | 0.018 | 0.016 | 1.676 | 31.98 | 0 | 0 | 1.0434 | 3927.9924 | 100% | 1.363%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2016
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
| Matt Williams | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
Bristol | Winnie Lacesso | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
| Luke Kreczko | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
Cambridge
| John Hill | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2
Oxford
| Kashif Mohammad | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
RALPP | Ian Loader | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
| Chris Brew | 0.4 | 0.4 | 0.4 | 0.35 | 0.35 | 0.35
| FedericoMelaccio | 0 | 0 | 0 | 0 | 0 | 0
Sussex | Emyr James | [6 empty] | red text last quarters figures
| Matt Raso-Barnett | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.15
Jeremy Maris
Total |  | 2.7 | 2.7 | 2.7 | 1.85 | 1.85 | 1.7
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q2 2016
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
EFDA JET | The PMB acknowledged the work done by this site over many years as they now close down. |  | JET has decided to decommission the site so has started the process, by making the required official announcements to EGI.
Birmingham |  |  | The new hardware is installed but Matt has been having signifcant trouble getting the new puppet configuration of DPM working and I'm also waiting on central IT to sort out the DNS changes (this has been known to take some time...). These should both hopefully be resolved in the next 1-2 weeks. One of the oldest storage nodes has also been having trouble with it's connection to the RAID array.
Bristol | Completed migrating CREAM-CE WN to ARC CE & decommissioned SL5 CREAM-CEs. All WNs now migrated to the new Puppet master (SL 7.2, Puppet 4). Got ARC-CE accounting mostly working, with some problems yet to fix (WIP) |  | HDFS namenode failover still not in DPM Update dpm-1.8.10 to 1-8.11 AND change in monitoring caused problems (ticketed). Alas took a while to fix (both site admins on alternating vacations).
Cambridge | All pool nodes upgraded to SL6/DPM 1.8.11. SE replaced with new hardware, running SL6/DPM 1.8.11. Everything now SL6. New CPU commissioned (extra 2283 HS06) |  | More old disk servers likely to be turned off (and not replaced).
Oxford | Site relativley stable except for an outage caused by an A/C failure following a power spike in June. All the new CPU has been commisioned and added to the HTCondor batch system. |  | Lack of staff has meant we have had to concentrate on core business and stop all development work. Recruitment is in progress to replace Ewan but we will still be 0.5FTE less than we were in GridPP4.
RALPP | deployed 7,500HS06 of New worker nods (640 slots) and decommisioned 3,000HS06 of old WNs (320 slots) Commisioning ~500TB of new disk, will replace an almost equal amount of old disk once it's in production New dCache head node with more RAM and SSD for DB storage dCache Updated to 2.13, headnode running CentOS7 CentOS7 ArcCE brought into production SL5 Squids replaced with CentOS7 ones Replaced condor_defragd with fallow for MCore draining, rewriting fallow to add some more features |  | Lack of effort without FM
Sussex | We (mainly Matt RB) have migrated all data from our Lustre 1.8.9 system to a new system running Lustre 2.5.3 - using parallel rsync to move around 280TB of data Matt RB patched Lustre 2.5.3 such that the extended attributes required by StoRM work Matt RB has migrated Grid services that were running on old hardware to VM, including the SRM We’ve recruited a replacement for Matt RB who should be starting with us on 1st April (Tier 2 Visa permitting…) |  | Matt RB left on 14th December and limited cover is being provided by Sussex IT Services. Unfortunately, we (ITS) didn’t notice the problems associated with the renaming of our SRM from grid-storm to grid-storm-02, partly because of other workload. Ticket processing also suffered as some acknowledgement were made late. ITS are more up to speed with covering this now! Atlas knew about the plans which were discussed them a couple of times at the support cloud meeting. It was intended that AGIS would be updated with the new SRM but this didn’t happen; ATLAS production jobs stopped, along with problems with SNO+ and the LFC We lost about 8 weeks of production jobs (Most in Q116) before the problem was understood and AGIS was updated. We have another 7 nodes (112 physical cores) of 2650 v2 and 2640 v3 that we are about to add to our Grid queue so we should be able to catch up with lost production work. It also seems that we may have not copied some files from atlaslocalgroupdisk in the lustre migration. We are attempting to reconcile what ATLAS thinks we have with what we actually have so that we can declare missing files lost.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol, Sussex and (currently) Oxford continues to be a concern. |  | Recruitment ongoing at Sussex and Oxford.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Deploy new dCache Head Node |  | 2016-05-01 |  | Done
RALPP: Deploy Test CentOS7/UMD4 ArcCE |  | 2016-06-01 |  | Done
RALPP: Replace SL5 Frontier/CVMFS Squids with CentOS7 ones. |  | 2016-04-15 |  | Done
Bristol - upgrade ARC CE from 4.2 to 5.X |  | 06/31/2016 |  | Abandoned - no need / no pressure to & ongoing lack of manpower
Bristol- Fix ARC CE accounting |  | 06/31/2016 |  | Mostly done, still some problems to fix
Bristol - Deploy HTCondor CE on lcgce02 |  | 03/31/2016 |  | On hold or abandoned - there is no proper accounting module for HT Condor CE (only a CERN version) & we have no capacity to do the software mods ourselves.
Bristol- Add new hardware: 280 more cores, 256 TB (after replication) |  | 03/31/2016
Bristol: Establish workflows for Solid experiment and medicine-imaging |  | 2016-07-01 |  | Ongoing
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP:Replace cluster top level router |  | 2016-09-30 |  | Date for switchover has been set for 7th September
RALPP:Commision New Disk |  | 2016-09-30
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
Landslides |  |  |  | Bristol
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop