## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q3 2016 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | EFDA JET |  |  | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 21.43% | 25% | 25% | 140.3% | 86.71% | 128.7% | 445.3% | 652.4% | 381% | 226% | 159.4% | 140.1% | 250% | 128.4% | 128.4% | 278% | 242.6% | 242.6% | 538.5% | 155.6% | 155.6% | 248.6% | 188.3% | 183.6%
.x.2 | % of promised (by that time) CPU available | 100% | 630.6% | 918.1% | 918.1% | 248.5% | 198.3% | 269.8% | 802% | 471.4% | 471.4% | 212.4% | 257% | 257% | 234.1% | 300.4% | 300.4% | 334.6% | 324.4% | 324.4% | 1521% | 538.8% | 538.8% | 327.4% | 311.1% | 323.8%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 86% | 86% | 86% | 98% | 98% | 98%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 86% | 86% | 86% | 98% | 98% | 98%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 4.899% | 8.404% | 11.34% | 67.05% | 74.69% | 64.92% | 11.99% | 35.81% | 37.38% | 87.02% | 72.07% | 83.15% | 75.92% | 63.02% | 67.4% | 78.46% | 75.82% | 68.28% | 62.33% | 57.4% | 59.58% | 63.95% | 65.31% | 63.06%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 4.658% | 8.123% | 11.17% | 58.31% | 68.95% | 60.51% | 9.724% | 29.74% | 29.42% | 70.8% | 64.03% | 74.73% | 65.53% | 57.09% | 60.34% | 69.29% | 63.59% | 57.03% | 52.48% | 52.5% | 53.85% | 55.65% | 56.74% | 54.64%
bi
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2016
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
EFDA JET | EMI2 | EMI3/SL6 |  | 1Gb/s | 1Gb/s | DPM 1.8.8-4 (EMI3) |  | Site | 2016-07-01 | 2016-08-01 | 2016-09-01 | Total |  | Site | 2016-07-01 | 2016-08-01 | 2016-09-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 |  | EFDA JET | 218447.8735 | 218529.2605 |  | 436977.134 |  | EFDA JET | 224058.1418 | 219820.6177 |  | 443878.7595
Bristol | EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 6274106.4752 | 7161870.725 | 9267875.7533 | 22703852.9535 |  | Birmingham | 6872284.5891 | 7782869.7386 | 9703984.8084 | 24359139.1361
Cambridge | EMI-3 | EMI-3/SL6 |  | 10Gb/s | 2*10Gb/s | DPM 1.8.11 |  | Bristol | 3530758.1741 | 1831204.0688 | 4932180.1224 | 10294142.3653 |  | Bristol | 4654170.8614 | 2551470.7304 | 5874087.1545 | 13079728.7463
Oxford | EMI 3 | EMI 3/SL6 |  | 10Gb/s | 2*20Gb/s | DPM 1.8.10 |  | Cambridge | 2850708.6074 | 3264426.2027 | 3686196.5252 | 9801331.3353 |  | Cambridge | 3255024.0314 | 3674777.9687 | 3975573.3499 | 10905375.35
RALPP | UMD2/3 | UMD2/3 |  | 10Gb/s | 10Gb/s | Dcache 2.2 |  | Oxford | 10970115.5102 | 10672977.6739 | 13109783.1204 | 34752876.3045 |  | Oxford | 12187370.6714 | 12041828.9858 | 14588543.222 | 38817742.8792
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 23824433.1272 | 22511823.0506 | 11967310.7538 | 58303566.9316 |  | RALPP | 29144067.1789 | 26957909.6595 | 13704511.3667 | 69806488.2051
[8 empty] | Sussex | 510154.8361 | 460560.9337 | 1380494.1638 | 2351209.9336 |  | Sussex | 616814.5335 | 518208.0128 | 1466084.755 | 2601107.3013
[8 empty] | Total CPU hrs | 48178724.6037 | 46121391.9152 | 44343840.4389 | 138643956.9578 |  | Total | 56953790.0075 | 53746885.7135 | 49312784.6565 | 160013460.3775
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
EFDA JET | 1772 | 1.5 | 193 | 6 | 918.1% | 25% | 1.542% | 0.02762% | 436977.134 | 0.3152% | 2208 | 3912576 | 11.17% | 11.34%
Birmingham | 16994 | 920 | 6298 | 715 | 269.8% | 128.7% | 14.79% | 16.94% | 22703852.9535 | 16.38% | 2208 | 37522752 | 60.51% | 64.92%
Bristol | 15847 | 560 | 3362 | 147 | 471.4% | 381% | 13.79% | 10.31% | 10294142.3653 | 7.425% | 2208 | 34990176 | 29.42% | 37.38%
Cambridge | 5940 | 290 | 2311 | 207 | 257% | 140.1% | 5.169% | 5.339% | 9801331.3353 | 7.069% | 2208 | 13115520 | 74.73% | 83.15%
Oxford | 26084 | 980 | 8682 | 763 | 300.4% | 128.4% | 22.7% | 18.04% | 34752876.3045 | 25.07% | 2208 | 57593472 | 60.34% | 67.4%
RALPP | 46300 | 2610 | 14274 | 1076 | 324.4% | 242.6% | 40.29% | 48.05% | 58303566.9316 | 42.05% | 2208 | 102230400 | 57.03% | 68.28%
Sussex | 1977.32 | 70 | 367 | 45 | 538.8% | 155.6% | 1.721% | 1.289% | 2351209.9336 | 1.696% | 2208 | 4365922.56 | 53.85% | 59.58%
Totals | 114914.32 | 5431.5 | 35487 | 2959 | 323.8% | 183.6% | 100% | 100% | 138643956.9578 | 100% | 2208 | 253730818.56 | 54.64% | 63.06%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken |  | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
EFDA JET |  | 1327.104 | 1.968 | 331776 | EFDA JET | 0 | 0
Birmingham |  | 12892.8 | 661 | 3223200 | Birmingham | 22433 | 980
Bristol |  | 10158.96 | 0 | 2539740 | Bristol | 9607 | 0
Cambridge |  | 5938.848 | 293 | 1484712 | Cambridge | 5940 | 293
Oxford |  | 3414.324 | 940 | 853581 | Oxford | 26240 | 940
RALPP |  | 21420 | 2646 | 5355000 | RALPP | 42840 | 3079
Sussex |  | 2007.552 | 83 | 501888 | Sussex | 2006 | 83
Totals |  | 57159.588 | 4624.968 | 14289897
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2016
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
EFDA JET | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 11
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [20 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[44 empty] | 0 | 0
[44 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 2 | 2 | 2 | 1 | 0 | 0 | 3 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 3 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 112
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
EFDA JET | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.02495% | 16.43%
Birmingham | 225 | 305 | 0.12 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0.2 | 0.02 |  | 0.53 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 532.501 | 13.64% | 0.4695%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.4 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370.409 | 9.487% | 0.00189%
Cambridge | 0 | 258.9 | 0 | 0 | 0.1 | 0.02 | 0 | 0 | 0 | 0 | 0.004 | 0 | 0 | 0 | 0 | 0 | 0.43 | 0 |  | 0 | 0 | 0.45 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259.904 | 6.657% | 0.2132%
Oxford | 0 | 577 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 | 0.049 | 0.625 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 6.48 | 0.018 | 0.016 | 1.5 | 31.98 | 0 | 0 | 0.0234 | 618.8404 | 15.85% | 6.593%
RALPP | 1 | 672 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1030 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 399 |  |  | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2111.6 | 54.08% | 0.4546%
Sussex |  | 9 | [8 empty] | 0.008 | [25 empty] | 1 |  |  | 0.176 |  |  |  |  | 10.184 | 0.2608% | 11.63%
Total | 226 | 1822.524 | 2.12 | 0.65 | 0.4 | 0.044 | 0 | 0 | 0 | 1401.411 | 0.169 | 0.049 | 0.635 | 0 | 0.025 | 0 | 0.63 | 0.055 | 0 | 2.534 | 0 | 399.672 | 0 | 0 | 3 | 1 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 7.48 | 0.018 | 0.016 | 1.676 | 31.98 | 0 | 0 | 1.0434 | 3904.4124 | 100% | 1.404%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2016
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater |  |  |  | 0.3 | 0.3 | 0.3
| Matt Williams | 1 | 1 | 1
Bristol | Winnie Lacesso | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
| Luke Kreczko | 0 | 0 | 0 | 0 | 0 | 0
Cambridge
| John Hill | 0 | 0 | 0 | 0.5 | 0.5 | 0.5
Oxford
| Vip Davda |  | 0.25 | 0.5
| Kashif Mohammad | 0.5 | 0.5 | 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4
| Chris Brew | 0.2 | 0.2 | 0.2 | 0.35 | 0.35 | 0.35
Sussex | Emyr James | [6 empty] | red text last quarters figures
Matt Raso-Barnett
Jeremy Maris
Total |  | 2.1 | 2.35 | 2.6 | 1.35 | 1.35 | 1.35
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q3 2016
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
EFDA JET |  |  | The Jet site is now decommissioned.
Birmingham | Finished installing all the new hardware. |  | Matt Williams has left and so Mark Slater is in the process of continuing where he left off. In addition, some more of our oldest disks have started having failures. Some mitigation has been put in place to prevent this but they may need to be retired soon.
Bristol | New GridFTP server with 40Gbit/s capability in production; retired two GridFTP servers |  | Cluster outage due to cooling failure for a few weeks in July
Cambridge | DPM upgraded to 1.8.11. Torque upgraded to 2.5.13. |  | Loss of further 40TB of storage due to natural wastage.
Oxford | 1. Testing Atlas diskless site option for Oxford. Setup an influxdb/grafana monitoring at Oxford which may be useful for distinguishing for different kind of jobs. 2. Investigating a Perfsonar issue, apparently bandwidth monitoring rate doesn't match with actual transfer rate. |  | Oxfrod suffered from two A/C incidents during the quarter. The first on Friday 12th August, when we switched off most of the workers over the weekend. The second incident on Friday 16th September but the A/C was restored before we had to turn off any worker nodes. Temperature monitoring of the room which will shutdown worker nodes automatically if the temperature is above threshold is now in place.
RALPP | Deployed just over 450TB of 2016 disk into dCache and retired almost exactly the same ammount of old disk. New disk is ZFS on JBOD, no hardware RAID involved. So far performance seems to be as good as if not better than HW RAID. New top level router for the Tier 2 network brought into production. It's an s4810 with the latest firmware release which includes policy based routing. So a single router can handle but the default traffic and the data flows round the firewall bypass. Still needs a second intervention to bring up the second of the redundant pair as the first VRRP/VLT/MLAG config did not work as expected.
Sussex | We (mainly Matt RB) have migrated all data from our Lustre 1.8.9 system to a new system running Lustre 2.5.3 - using parallel rsync to move around 280TB of data Matt RB patched Lustre 2.5.3 such that the extended attributes required by StoRM work Matt RB has migrated Grid services that were running on old hardware to VM, including the SRM We’ve recruited a replacement for Matt RB who should be starting with us on 1st April (Tier 2 Visa permitting…) |  | Matt RB left on 14th December and limited cover is being provided by Sussex IT Services. Unfortunately, we (ITS) didn’t notice the problems associated with the renaming of our SRM from grid-storm to grid-storm-02, partly because of other workload. Ticket processing also suffered as some acknowledgement were made late. ITS are more up to speed with covering this now! Atlas knew about the plans which were discussed them a couple of times at the support cloud meeting. It was intended that AGIS would be updated with the new SRM but this didn’t happen; ATLAS production jobs stopped, along with problems with SNO+ and the LFC We lost about 8 weeks of production jobs (Most in Q116) before the problem was understood and AGIS was updated. We have another 7 nodes (112 physical cores) of 2650 v2 and 2640 v3 that we are about to add to our Grid queue so we should be able to catch up with lost production work. It also seems that we may have not copied some files from atlaslocalgroupdisk in the lustre migration. We are attempting to reconcile what ATLAS thinks we have with what we actually have so that we can declare missing files lost.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern. |  | Recruitment ongoing at Sussex.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP:Replace cluster top level router |  | 2016-09-30 |  | Done (though we still need another intervention to fix a couple of issues)
RALPP:Commision New Disk |  | 2016-09-30 |  | Done
Bristol - upgrade ARC CE from 4.2 to 5.X |  | 06/31/2016 |  | Abandoned - no need / no pressure to & ongoing lack of manpower
Bristol- Fix ARC CE accounting |  | 06/31/2016 |  | Mostly done, done (see ggus#121683), waiting on APEL team
Bristol: Establish workflows for Solid experiment and medicine-imaging |  | 2016-07-01 |  | Ongoing
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Refine Top Level Router Config |  | 2016-12-15 |  | Second router is Hot Standby
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
Landslides |  |  |  | Bristol
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop