## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q416 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 240.3% | 240.3% | 240.3% | 281.5% | 281.5% | 281.5% | 204.2% | 204.2% | 233.5% | 145.8% | 145.8% | 151.9% |  |  | 0% | 214.5% | 214.5% | 225.7%
.x.2 | % of promised (by that time) CPU available | 100% | 373.7% | 373.7% | 373.7% | 160% | 160% | 160% | 313.3% | 313.3% | 375.1% | 447.3% | 447.3% | 450.5% |  |  | 0% | 278.3% | 278.3% | 293%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  | 100% | 100% | 100%
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  | 100% | 100% | 100%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 75.56% | 50.52% | 61.58% | 86.06% | 85.12% | 95.11% | 108.9% | 78.09% | 52.53% | 62.57% | 117.3% | 61.43% |  |  |  | 83.64% | 83.26% | 67.07%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 44.78% | 37.34% | 42.4% | 68.19% | 67.45% | 80.06% | 91.81% | 68.37% | 62.99% | 53.32% | 102.3% | 53.04% |  |  |  | 64.72% | 69.27% | 59.62% | Brunel low
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q416
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2016 Oct | 2016 Nov | 2016 Dec | Total |  |  | 2016 Oct | 2016 Nov | 2016 Dec | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 14176601.09 | 9393744.208 | 10131300.02 | 33701645 |  | UKI-LT2-Brunel | 19532914.99 | 14804956.86 | 14613831.29 | 48951703
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 19296376.84 | 19902693.18 | 22790787.83 | 61989858 |  | UKI-LT2-IC-HEP | 22200724.18 | 24804530.74 | 26640516.33 | 73645771
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 20870308.74 | 24686453.47 | 17538503.28 | 63095265 |  | UKI-LT2-QMUL | 19841842.5 | 18588902.52 | 14185661.76 | 52616407
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 17603494.66 | 12083776.28 | 14813958 | 44501229 |  | UKI-LT2-RHUL | 20377793.65 | 14351604.28 | 16813862.52 | 51543260
[8 empty] | UKI-LT2-UCL-HEP | 812024.1824 | 456841.5844 | 324272.5341 | 1593138 |  | UKI-LT2-UCL-HEP | 924376.0417 | 560180.4509 | 470859.8853 | 1955416
[8 empty] | Total | 72758806 | 66523509 | 65598822 | 204881136 |  | Total | 82877651 | 73110175 | 72724732 | 228712558
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 36000 | 1100 | 9632.812 | 457.8006 | 373.7% | 240.3% | 23.31% | 11.44% | 33701645 | 16.58% | 2208 | 79488000 | 42.4% | 61.58% | 68.85%
UKI-LT2-IC-HEP | 35068.4 | 3699 | 21915.766 | 1313.8219 | 160% | 281.5% | 22.71% | 38.47% | 61989858 | 30.49% | 2208 | 77431027.2 | 80.06% | 95.11% | 84.17%
UKI-LT2-QMUL | 45363 | 3316 | 12094.921 | 1420.211 | 375.1% | 233.5% | 29.37% | 34.49% | 63095265 | 31.04% | 2208 | 100161504 | 62.99% | 52.53% | 119.9%
UKI-LT2-RHUL | 38000 | 1500 | 8434.349 | 987.6466 | 450.5% | 151.9% | 24.61% | 15.6% | 44501229 | 21.89% | 2208 | 83904000 | 53.04% | 61.43% | 86.34%
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 154431.4 | 9615 | 52714.598 | 4260.48 | 293% | 225.7% | 100% | 100% | 203287997 | 100% | 2208 | 340984531.2 | 59.62% | 67.07% | 89.58%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 4510 | 54668 | 1441
UKI-LT2-IC-HEP | 4460 | 41210 | 3613
UKI-LT2-QMUL | 3970 | 45216 | 3226
UKI-LT2-RHUL | 3970 | 38503 | 1462
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 179597 | 9742 |  | 0
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx
Note on E34: gronbech:Gstat displays SI2000 so this needs converting to HS06

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q416
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cernatschool.org | comet.j-parc.jp | cms | dteam | dzero | enmr.eu | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | icecube | ilc | ipv6.hepix.org | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | neiss.org.uk | ops | pheno | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.gear.cern.ch | vo.helio-vo.eu | vo.landslides.mossaic.org | vo.londongrid.ac.uk | zeus | Total
UKI-LT2-Brunel | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 16
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 26
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 25
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 19
Total | 0 | 4 | 4 | 2 | 2 | 3 | 1 | 4 | 4 | 1 | 1 | 1 | 2 | 0 | 4 | 3 | 3 | 1 | 4 | 1 | 4 | 3 | 2 | 4 | 1 | 1 | 4 | 4 | 4 |  | 1 | 0 | 4 | 0 |  | 0 | 1 | 1 | 4 | 2 | 86
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | lsst | cernatschool.org |  | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.311 |  | 0.276 |  |  |  | 0.064 | 822.711 |  | 32.892 | 0.017 | 0.003 |  |  |  |  | 1.491 | [5 empty] | 0.002 | 0.006 |  |  |  |  | 0.202 | [6 empty] | 0.018 |  | 0 |  |  |  |  | 857.993 | 11.39% | 0.2786%
UKI-LT2-IC-HEP |  | 30.291 | 0 |  | 0 |  | 0 | 2937.989 |  | 10.37 |  |  |  |  | 308.7 |  |  |  | 0 | [15 empty] | 36.155 |  |  | 189.6 |  |  |  | 33.797 | 3546.902 | 47.09% | 8.172%
UKI-LT2-QMUL |  | 83 | 0.933 |  |  | 0 |  | 1.6 |  | 1800 | 0.052 |  |  |  | 93 |  | 0.673 | 0.0068 |  |  |  | 0.016 | 0.016 | 0.0025 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 9.3 |  |  |  | 0 | 0.109 | 0.021 |  |  | 1988.7535 | 26.4% | 4.734%
UKI-LT2-RHUL | 0 |  | 0.63 |  |  |  |  | 1.618 |  | 1136 | 0.015 | 0.001 |  |  |  |  | 0.19 | [5 empty] | 0.005 | 0.005 | [6 empty] | 0.009 | 0 | [5 empty] | 0 |  |  |  |  | 1138.473 | 15.11% | 0.0751%
Total | 0.311 | 113.291 | 1.839 | 0 | 0 | 0 | 0.064 | 3763.918 | 0 | 2979.262 | 0.084 | 0.004 | 0 | 0 | 401.7 | 0 | 2.354 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.023 | 0.0135 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.009 | 0 | 0.019 | 9.3 | 36.155 | 0.018 | 0 | 189.6 | 0.109 |  |  | 33.797 | 7532.1215 | 100% | 5.141%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q416
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.7 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3
| Ivan Reid | 0.7 | 0.7 | 0.7 | 0.15 | 0.15 | 0.15
| P. Hobson | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| B.Green/Tom | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 6.9 | 6.9 | 6.9 | 1.9 | 1.9 | 1.9

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q416
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | Developing an IPv6-only worker node, testing for LHC VOs in conjunction with Duncan Rand and HEPiX working group.
UKI-LT2-IC-HEP
UKI-LT2-QMUL | Dan: Attended CHEP2016 conference. Presented 2 posters and wrote proceedings for the Lustre Poster. Attended computing insight UK meeting, got knowledge of computing hardware availability. Completed SLURM batch system deployment to full cluster. Have enabled additional VOs: cepc, dune, LZ Performed performance studies of WAN link and studies impact of adding in IDS/IPS inline to network link. Terry: * Kea DHCP implementation (will be replacing existing ISC dhcpd on fe0x hosts). * Consultation and assistance to RAL re: their IPv6 deployment (this is ongoing). * Upgrades to Jool NAT64 to fix a critical memory leak. * Logging and reporting of DNS requests to better understand NAT64 utilization (this was suggested by Chris Walker and it seemed sensible to do). * Writing my 464XLAT CHEP paper. * Continuing to 'disassemble' Alex Martin's installer process, setup_scripts and writing Ansible playbooks. * Currently working on an sFlow collector to receive network flows from the Dell/Force10 switches for the purpose of understanding where, if any, network bottlenecks exist internally within the cluster; this will also provide us with data which shows us who we exchange the most data with and who would also benefit from adopting jumbo frames within the GridPP community (as you know, the benefits are only visible when *both* endpoints support jumbo frames).
UKI-LT2-RHUL | DPM headnode migration Storage accounting
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes