## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q4 2016 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 184% | 178% | 177.9% | 152% | 152% | 151.5% | 148% | 156% | 156.1% | 136% | 136% | 136.2% | 160.2%
.x.2 | % of promised (by that time) CPU available | 100% | 443% | 443% | 442.9% | 176% | 176% | 276.8% | 314% | 314% | 313.9% | 334% | 334% | 334.4% | 345.6%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | No Q4 figures on SLL page, but no cause to believe
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Any site figures below 98% for Q4.
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 63% | 61% | 72.6% | 90% | 116% | 85.27% | 82% | 87% | 95.52% | 36% | 67% | 69.28% | 82.82%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 54% | 56% | 59.13% | 84% | 108% | 77.41% | 75% | 77% | 84.97% | 31% | 61% | 63.22% | 72.03%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2016
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Site | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total |  | Site | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 20157729 | 17971921 | 20727264 | 58856914 |  | Lancaster | 24238493 | 21701798 | 26319064 | 72259355
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 12622955 | 10243208 | 12907606 | 35773769 |  | Liverpool | 13391859 | 11371598 | 14643213 | 39406670
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 28020347 | 25237592 | 27862904 | 81120843 |  | Manchester | 31352983 | 28876650 | 30954540 | 91184173
[7 empty] | Sheffield | 3811250 | 3843663 | 6764523 | 14419436 |  | Sheffield | 4200516 | 4226371 | 7375768 | 15802655
[7 empty] | Total CPU hrs | 60801031 | 53452721 | 61497774 | 175751526 |  | Total | 73183851 | 66176417 | 79292585 | 218652853
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2016/10/2016/12
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 46080 | 2224 | 10405 | 1250 | 442.9% | 177.9% | 37.7% | 35.97% | 58856914 | 30.95% | 2160 | 99532800 | 59.13% | 72.6%
Liverpool | 21395 | 1223 | 7729 | 807 | 276.8% | 151.5% | 17.5% | 19.78% | 35773769 | 18.81% | 2160 | 46213200 | 77.41% | 85.27%
Manchester | 44197 | 2205 | 14080 | 1413 | 313.9% | 156.1% | 36.16% | 35.66% | 81120843 | 42.66% | 2160 | 95465520 | 84.97% | 95.52%
Sheffield | 10560 | 531 | 3158 | 390 | 334.4% | 136.2% | 8.639% | 8.588% | 14419436 | 7.582% | 2160 | 22809600 | 63.22% | 69.28%
Totals | 122232 | 6183 | 35372 | 3860 | 345.6% | 160.2% | 100% | 100% | 190170962 | 100% | 2160 | 264021120 | 72.03% | 82.82%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 46080 | 2224 | NA | Lancaster
Liverpool | 1986 | 21385 | 1223 | NA | Liverpool
Manchester | 4494 | 44197 | 2205 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 10480 | 122222 | 6183 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2016
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | na48 | neiss | ops | pheno | vo.skatelescope.eu | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1 | 0 |  | 1 |  |  | 1 |  |  | 1 |  | 14
Liverpool | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 33
Manchester | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 24
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 0 | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 |  |  | 1 | 1 | 1 | 1 |  | 20
Total | 3 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 1 |  | 2 | 4 | 2 |  | 2 | 4 | 1 |  | 2 | 2 | 1 |  | 4 | 3 |  | 4 | 1 | 1 | 4 | 2 | 3 | 4 |  | 91
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1450 | 0 | 17 | 5 | 1472 | 1.155% | 1.495%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3620.24 | 0.57 | 179 | 12.47 | 3920.46 | 4.566% | 4.898%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2016
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | bar: GridPP Funded Month 1 to GridPP Funded Month 3
M. Doidge | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| P. Love | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
Liverpool | S. Jones | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| R. Fay | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
| J. Bland | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Manchester | A. Forti | bar: GridPP Funded Month 1 to GridPP Funded Month 3
R. Frank | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| A. McNab | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Sheffield | E. Korolkova | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| M. Robinson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | EGI Funded Month 1: 0.5; EGI Funded Month 2: 0.5; EGI Funded Month 3: 0.5
Manchester | A. Forti | bar: Unfunded Month 1 to Unfunded Month 3

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q4
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | SL5 retirement IPv6 Centos7 Procurement ZFS testing New VO support | All SL5 nodes retired Routing fixed, perfsonar dual-stacked Learning curve being climbed Started the conversation with vendors ZFS feasibility study started (finised at time of writing) Dune and other supported and working, but… |  |  | None None Need to devote more resources to testing None (yet) None ...their work flows overload our system.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Threat that centos 7 will “sneak up on us”. Need a new SE headnode – current one out of warranty. Dual-stacking our storage next on list- not entirely risk-free. Need to adjust CE/batch to deal with small VO workloads |  |  | Devote more resources and time to testing, setup “mini-cluster” on centos7 Setup dummy SE to test configs first. Be ready to roll back! Again, be ready to roll back changes!
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Tarball Work IPv6 mesh joined Final SL5 nodes retired New Vos enabled |  |  | 23/12/16 |  | Centos 7 “prelim” tarballs built Lancaster in mesh No need to worry about SL5 EOL More Vos.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Create “grid-facing” centos7 mini-cluster Fix cluster for smaller VO jobs Attempt to roll out a Bro instance as part of SOC work Aid UK NGI pakiti work Increase procurement readiness |  |  | 31/3/2017 |  | Ready to move to centos7 Increase userbase=more jobs Increased engagement “” Ready to make the best decision for new kit.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q4
Reported by | S Jones, J Bland, R Fay
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Sys Admin Software dev/admin Sys Admin VO Support Sys Admin Machine room provisioning Sys Admin Software Dev WLCG collaboration | Routines (admin of 3 clusters plus storage, tickets, VO support, VOMS documentation, security, HW & SW maint., space management, benchmark corrections, large migration of service nodes to new VM host etc.) Continued development of metric collection and visualisation (sensu/graphite/collectd) Consolidation of auxiliary services to one VM (i.e. layout DB, rpm generation, github for VC, etc.) New VOs (ALICE on VAC, DUNE, MOEDAL on batch) Cluster special ops (Kernel update CVE-5195), rebuild of CE after power cut) Purchasing and tender work (GridPP5 spend, plus new cooling system from central services) Worker node Temp Safety Control VAC Testing (v.02) Accounting taskforce participation (metric names and fundamental units), and audit scripts for site comparison to APEL/Atlas estimates for VAC, ARC and CREAM/Torque. |  | None On going None; uses less IP space. Adding new VO to batch systems is onerous. Power cut caused file corruption. Trash and build. Hard to say whether cpu or disk needed. Coooling should be good but needs outage. Last ditch cut-off, for safety's sake. Ongoing - move to mcore. Some small issues due to auto-updates
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | Centos7 VAC not yet used by many Vos Ipv6 |  | Quite different to SL6. Will need testing for migration. Needs VM process to be easy and well defined. Need to work with external supplier (CSD)
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Continue adoption of Centos7 Centos7 adoption documentation Continue adoption of Ipv6 Ipv6 Adoption Documentation |  | 31/12/2016 31/12/2016 31/12/2016 31/12/2016 |  | More progress towards 100% usage Docs will be developed. More progress towards 100% usage Docs will be developed.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Continue adoption of Centos7, documentation Continue adoption of Ipv6, documentation Finish migration to VAC 02 Finish kernel update CHEP Paper on VAC testing Plans to continue with Tom Whyntie's user guide VAC Superslot/Multicore tests Some HW purchases for GPP5 |  | 31/03/2017 31/03/2017 31/03/2017 31/03/2017 6/02/2017 31/03/2017 31/03/2017 31/03/2017 |  | More progress towards 100% usage More progress towards 100% usage All slots to be superslots Close CVE-2016-7117 Publication accepted. Discuss at Ops Hope to have test results soon. HW configured and online.

## Manchester
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q4
Reported by | Andrew McNab
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Manchester |  | 1) Continued operation of the CREAM/Torque batch service for WLCG and GridPP Vos 2) Continued operation of the DPM storage for WLCG and GridPP Vos 3) Continued development of and running of Vac and Vcycle services (managing VMs at CERN and CC-IN2P3) at Manchester 4) Operating GridPP’s DIRAC monitoring framework 5) Icecube and LHCb are exploiting the prototype GPU service within grid jobs to run their existing GPU-dependent code 6) Manchester has continued as one of the UK’s five LHCb Tier-2 sites with storage 7) Set up skatelescope.eu VO in EGI and GridPP DIRAC, running daily SAM tests at Manchester 8) Worked on ATLAS Event Service usage in Manchester 9) foreman deployment reached production state 10) requested quotes for new hardware 11) Added ALICE to the VAC machines |  |  | - several disk and motherboard failures - no more spare motherboards for old machines, started to reduce capacity
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Manchester | - no more spare motherboards, have to start decommission old WNs due to hardware failures
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/HTCondor on at least 1 cluster (still being evaluated) 2) Integrate DPM in puppet and abandon YAIM (being finalised) 3) Test remaining SE with failed raid array, fix remaining problems, and return it into full service (done) 4) Extend IPv6 to more hosts (ongoing) 8) Look into foreman deployment (in progress) 9) Improve local tools to balance data servers (ongoing) 10) Review next old SE: disk tests, raid array rebuild (in progress) |  |  | 8) done
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Manchester | 1) Install ARC-CE/HTCondor on at least 1 cluster (still being evaluated) 2) Integrate DPM in puppet and abandon YAIM (being finalised) 4) Extend IPv6 to more hosts (ongoing) 9) Improve local tools to balance data servers (ongoing) 10) Review next old SE: disk tests, raid array rebuild (in progress) 11) migrate existing machines into foreman environment 12)commissioning of new hardware
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs.
Working with LSST and SKA users to adapt their workflows to use grid resources
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemination |  |  | Date |  | Notes
11/10/216 Memory handling in the ATLAS submission system, CHEP2016 11/10/2016 Analysis of empty ATLAS pilot jobs and subsequent resource usage on grid sites, poster, CHEP2016 25/11/2016 CentOS7 testing update, ADC weekly
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Alessandra is one of the GridPP representatives and one of the co-chairs of the WLCG Ops Coordination, Atlas Infrastructure and Facilities coordinator and member of the atlas distributed computing coordination; Member of the Traceability, Information System and Accounting task forces, WLCG workshop 2017 planning committee.
Andrew is the Deputy LHCb Computing Coordinator. He is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group and leading the GridPP Tier-2 Evolution project. He is leader of the WLCG "Machine Features” task force, and a member of the "Cloud Traceability”, “Cloud Resource Reporting”, and “Information Systems Evolution" task forces, and the Grid Deployment Board steering group.
Other outputs and Knowledge |  |  | Date |  | Notes

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 16Q4
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | Started to look on moving worker nodes to ipv6, discussed with the university networking team. Contacted vendors and got quotes for a new procurement round. Sheffield is running lz and dune production alonside with "old" vo's jobs. Analysis availability for ATLAS ( ASAP metric) is 98%.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Delay with moving servers to ipv6 |  |  | The work kas been started. Atlas requires sites to completely migrate to IPv6 by start of Run3.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Started to look on moving worker nodes to ipv6, discussed with the university networking team. Contacted vendors and got quotes for a new procurement round. Sheffield is running lz and dune production. |  |  | 25 December 2017
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Finish first part of procurement |  |  | 2017-03-31
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes