## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q3 2016 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | 0 |  |  | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 25% | 25% | 0% | 86.71% | 128.7% | 128.7% | 652.4% | 381% | 381% | 159.4% | 140.1% | 140.1% | 128.4% | 128.4% | 128.4% | 242.6% | 242.6% | 242.6% | 155.6% | 155.6% | 155.6% | 183.6% | 183.6% | 183.9%
.x.2 | % of promised (by that time) CPU available | 100% | 918.1% | 918.1% | 0% | 198.3% | 269.8% | 269.8% | 471.4% | 471.4% | 481.1% | 257% | 257% | 257% | 300.4% | 300.4% | 300.4% | 324.4% | 324.4% | 324.4% | 538.8% | 538.8% | 538.8% | 323.8% | 323.8% | 321.5%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 86% | 86% | 86% | 98% | 98% | 98%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 86% | 86% | 86% | 98% | 98% | 98%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 8.404% | 11.34% | 0% | 74.69% | 64.92% | 65.42% | 35.81% | 37.38% | 57.15% | 72.07% | 83.15% | 88.5% | 63.02% | 67.4% | 70.59% | 75.82% | 68.28% | 72.27% | 57.4% | 59.58% | 77.78% | 63.06% | 63.06% | 69.65%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 8.123% | 11.17% | 0% | 68.95% | 60.51% | 59.85% | 29.74% | 29.42% | 46.96% | 64.03% | 74.73% | 77.32% | 57.09% | 60.34% | 58.4% | 63.59% | 57.03% | 52.12% | 52.5% | 53.85% | 69.44% | 54.64% | 54.64% | 55.6%
bi
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2016
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total |  | Site | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 6179240 | 7136241 | 9141503 | 22456984 |  | Birmingham | 6649102 | 8083144 | 9815171 | 24547417
Cambridge | UMD 4/SL6 | UMD 4/SL6 |  | 10Gb/s | 2*10Gb/s | DPM 1.8.11 |  | Bristol | 7118872 | 3542492 | 6110121 | 16771485 |  | Bristol | 8438447 | 4632947 | 7338659 | 20410053
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.8.11.1 |  | Cambridge | 3651783 | 3308135 | 3181555 | 10141473 |  | Cambridge | 4113883 | 3873345 | 3619987 | 11607215
RALPP | UMD3/4 | UMD3 |  | 10Gb/s | 10Gb/s | Dcache 2.13.51 |  | Oxford | 12008194 | 10203725 | 11420600 | 33632519 |  | Oxford | 14140969 | 12710406 | 13803878 | 40655253
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 13251369 | 21826124 | 18201334 | 53278827 |  | RALPP | 20501925 | 27238318 | 26139121 | 73879364
[8 empty] | Sussex | 1440013 | 1078530 | 512996 | 3031539 |  | Sussex | 1569607 | 1219779 | 606588 | 3395974
[8 empty] | Total CPU hrs | 43649471 | 47095247 | 48568109 | 139312827 |  | Total | 55413933 | 57757939 | 61323404 | 174495276
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Birmingham | 16994 | 920 | 6298 | 715 | 269.8% | 128.7% | 14.98% | 16.94% | 22456984 | 16.12% | 2208 | 37522752 | 59.85% | 65.42%
Bristol | 16175 | 560 | 3362 | 147 | 481.1% | 381% | 14.25% | 10.31% | 16771485 | 12.04% | 2208 | 35714400 | 46.96% | 57.15%
Cambridge | 5940 | 290 | 2311 | 207 | 257% | 140.1% | 5.235% | 5.341% | 10141473 | 7.28% | 2208 | 13115520 | 77.32% | 88.5%
Oxford | 26084 | 980 | 8682 | 763 | 300.4% | 128.4% | 22.99% | 18.05% | 33632519 | 24.14% | 2208 | 57593472 | 58.4% | 70.59%
RALPP | 46300 | 2610 | 14274 | 1076 | 324.4% | 242.6% | 40.8% | 48.07% | 53278827 | 38.24% | 2208 | 102230400 | 52.12% | 72.27%
Sussex | 1977.32 | 70 | 367 | 45 | 538.8% | 155.6% | 1.743% | 1.289% | 3031539 | 2.176% | 2208 | 4365922.56 | 69.44% | 77.78%
Totals | 113470.32 | 5430 | 35294 | 2953 | 321.5% | 183.9% | 100% | 100% | 139312827 | 100% | 2208 | 250542466.56 | 55.6% | 69.65%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken |  | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Birmingham |  | 0 |  |  | Birmingham | 22433 | 980
Bristol |  | 0 |  |  | Bristol | 9607 | 0
Cambridge |  | 0 |  |  | Cambridge | 5940 | 293
Oxford |  | 0 |  |  | Oxford | 26240 | 940
RALPP |  | 0 |  |  | RALPP | 42840 | 3079
Sussex |  | 0 |  |  | Sussex | 2006 | 83
Totals |  | 0 | 0 | 0
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2016
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 11
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [20 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[44 empty] | 0 | 0
[44 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 2 | 2 | 2 | 1 | 0 | 0 | 3 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 3 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 112
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
0 | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.02377% | 16.43%
Birmingham | 357.4 | 240.37 | 0.12 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0.2 | 0.02 |  | 0.53 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 600.271 | 14.65% | 0.4165%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427.4 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427.409 | 10.43% | 0.001638%
Cambridge | 0 | 246.9 | 0 | 0 | 0.08 | 0.02 | 0 | 0 | 0 | 0 | 0.004 | 0 | 0 | 0 | 0 | 0 | 0.44 | 0 |  | 0 | 0 | 0.39 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247.834 | 6.049% | 0.2195%
Oxford | 0 | 577 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 | 0.049 | 0.625 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 6.48 | 0.018 | 0.016 | 1.5 | 31.98 | 0 | 0 | 0.0234 | 618.8404 | 15.1% | 6.593%
RALPP | 1 | 661 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1156 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 365 |  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2191.6 | 53.49% | 0.3924%
Sussex |  | 9 | [8 empty] | 0.008 | [25 empty] | 1 |  |  | 0.176 |  |  |  |  | 10.184 | 0.2486% | 11.63%
Total | 358.4 | 1734.894 | 2.12 | 0.65 | 0.38 | 0.044 | 0 | 0 | 0 | 1584.411 | 0.169 | 0.049 | 0.635 | 0 | 0.025 | 0 | 0.64 | 0.055 | 0 | 2.534 | 0 | 365.612 | 0 | 0 | 2 | 1 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.021 | 0 | 0 | 0 | 7.48 | 0.018 | 0.016 | 1.676 | 31.98 | 0 | 0 | 1.0434 | 4097.1124 | 100% | 1.313%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2016
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | 1 | 1 | 1
Matt Williams
Bristol | Winnie Lacesso |  |  |  | 0.2 | 0.2 | 0.2
Luke Kreczko
Cambridge
| John Hill |  |  |  | 0.5 | 0.5 | 0.5
Oxford
| Vip Davda | 0.5 | 0.5 | 0.5
| Kashif Mohammad | 0.5 | 0.5 | 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4
| Chris Brew | 0.2 | 0.2 | 0.2 | 0.35 | 0.35 | 0.35
Sussex | Emyr James | [6 empty] | red text last quarters figures
Matt Raso-Barnett
Jeremy Maris
Total |  | 2.6 | 2.6 | 2.6 | 1.05 | 1.05 | 1.05
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q3 2016
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Kept the site going after loss of Matt Williams |  | Some older disks started failing and needed decomissioning. Had issues setting up xrootd frontend - this would need a reinstall of the DPM head node.
Bristol | - a LOT of work on Stacki OS deployment - Nov'16: ARC CE accounting fixed as good as it can be (GGUS#121683) - *Extremely* successful SouthGrid meeting in Oxford = easiest for everyone to get to. Everyone agreed we should do this more. |  | - Site outage due to HPC power problems Nov 25-28 - Some new DICE WN logging Hardware Errors; still under warranty, must find time to run diags & juggle WN storage outage with Dell site visit - Some older (no warranty) DICE WN starting to log hardware/disk problems
Cambridge | Changed repos to UMD 4 on all service and worker nodes. Transferred ganglia/nagios monitoring to newer host. |  | perfsonar host started having problems in mid-December - monitoring would hang after a few days. Possibly traced to full root partition.
Oxford | Updated all service nodes and worker nodes to UMD4. Setup influxdb and grafana based monitoring system ARC CE update created many issues. Migrated ARC DB from Berkley DB to sqlite. Updated version of ARC CE seems to be very resource hungry so ARC VM was upgraded to 4 CPU and 8GB RAM. Enabled monitoring for LSST VO through vo-nagios. Added an automated shutdown script based on computer room temperature monitoring from one wire sensors. Statrted testing Oxofrd as a CMS site with data at RALPP. Jobs started flowing on 22nd December onwards.
RALPP | Started moving ArcCE nodes from VMs to physical machines due to occasional IO load issues with them on the VM infrastructure Rebuilt the ELK stack machines using version 5 of filebeat, logstash, elasticsearch and kibana, needs more work to get metrics into it. Work is ongoing to try to bring up the second half of the redundant router pair Started CMS T2C testing work with Oxford as the CPU only site |  | We've started experiencing load issue on our SRM and have purchased extra hardware to split the dCache headnode services
Sussex
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern. |  | Recruitment ongoing at Sussex.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol: Establish workflows for Solid experiment and medicine-imaging |  | 2016-07-01 |  | Ongoing
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Refine Top Level Router Config |  | 2017-03-31 |  | Second router is Hot Standby
Bristol: Update all nodes to UMD4 |  | 2017-03-31 |  | No nodes use EMI3
Bristiol:Order new DICE Hardware with GridPP and other funding |  | 2017-03-31 |  | At least 2 new DICE WN
Bristol: Improve reliability of OS deployment infrastructure |  | 2017-03-31 |  | Painless WN rebuilds
Bristol: Implement new IPV4 and IPV6 netwoork to bypass university firewall |  | 31/1/117 |  | Bristol T2 in "Science DMZ"
Bristol: Deploy new perfsonar hosts hosted by Itservices |  | 2017-05-31 |  | Retire old perfsonar nodes
Bristol:Have another successful SouthGrid meeting |  | 2017-03-31 |  | T2 Evolution Evolves
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
Landslides |  |  |  | Bristol
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop