## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q1 2017 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 178% | 178% | 176.6% | 152% | 152% | 151.5% | 156% | 156% | 220.5% | 136% | 136% | 136.2% | 183.3%
.x.2 | % of promised (by that time) CPU available | 100% | 443% | 443% | 442.9% | 176% | 277% | 285.1% | 314% | 314% | 313.7% | 334% | 334% | 334.4% | 347.3%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 97% | 99% | 100% | 97% | 100% | 100% | 98% | 100% | 100% | 97% | 97.25%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 97% | 99% | 100% | 97% | 100% | 100% | 99% | 100% | 100% | 97% | 97.5%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 61% | 73% | 73.53% | 116% | 85% | 89.89% | 87% | 96% | 95.13% | 67% | 69% | 79.97% | 84.78%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 56% | 59% | 64.12% | 108% | 77% | 81.76% | 77% | 85% | 84.98% | 61% | 63% | 71.13% | 75.38%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2017
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Site | 2017-01-01 | 2017-02-01 | 2017-03-01 | Total |  | Site | 2017-01-01 | 2017-02-01 | 2017-03-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 22238554 | 21014484 | 20563513 | 63816551 |  | Lancaster | 25152092 | 23506561 | 24525732 | 73184385
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 12677187 | 12361122 | 13882467 | 38920776 |  | Liverpool | 14494466 | 13638587 | 14656342 | 42789395
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 25599815 | 25348015 | 30127408 | 81075238 |  | Manchester | 28776976 | 28570393 | 33409505 | 90756874
[7 empty] | Sheffield | 4957068 | 6082184 | 5184917 | 16224169 |  | Sheffield | 5751144 | 6888759 | 5601686 | 18241589
[7 empty] | Total CPU hrs | 60515556 | 58723621 | 64573388 | 183812565 |  | Total | 74174678 | 72604300 | 78193265 | 224972243
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2017/1/2017/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 46080 | 2208 | 10405 | 1250 | 442.9% | 176.6% | 37.51% | 31.2% | 63816551 | 31.9% | 2160 | 99532800 | 64.12% | 73.53% | 87.2%
Liverpool | 22039 | 1223 | 7729 | 807 | 285.1% | 151.5% | 17.94% | 17.28% | 38920776 | 19.46% | 2160 | 47604240 | 81.76% | 89.89% | 90.96%
Manchester | 44170 | 3115 | 14080 | 1413 | 313.7% | 220.5% | 35.95% | 44.02% | 81075238 | 40.53% | 2160 | 95407200 | 84.98% | 95.13% | 89.33%
Sheffield | 10560 | 531 | 3158 | 390 | 334.4% | 136.2% | 8.596% | 7.503% | 16224169 | 8.111% | 2160 | 22809600 | 71.13% | 79.97% | 88.94%
Totals | 122849 | 7077 | 35372 | 3860 | 347.3% | 183.3% | 100% | 100% | 200036734 | 100% | 2160 | 265353840 | 75.38% | 84.78% | 88.92%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 46080 | 2208 | NA | Lancaster
Liverpool | 2070 | 22039 | 1223 | NA | Liverpool
Manchester | 4480 | 44170 | 3115 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 10550 | 122849 | 7077 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2017
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | na48 | neiss | ops | pheno | vo.skatelescope.eu | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1 | 0 |  | 1 |  |  | 1 |  |  | 1 |  | 14
Liverpool | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 33
Manchester | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 24
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 0 | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 |  |  | 1 | 1 | 1 | 1 |  | 20
Total | 3 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 1 |  | 2 | 4 | 2 |  | 2 | 4 | 1 |  | 2 | 2 | 1 |  | 4 | 3 |  | 4 | 1 | 1 | 4 | 2 | 3 | 4 |  | 91
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1450 | 0 | 17 | 5 | 1472 | 1.155% | 1.495%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3620.24 | 0.57 | 179 | 12.47 | 3920.46 | 4.566% | 4.898%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2017
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | bar: GridPP Funded Month 1 to GridPP Funded Month 3
M. Doidge | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| P. Love | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
Liverpool | S. Jones | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| R. Fay | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
| J. Bland | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Manchester | A. Forti | bar: GridPP Funded Month 1 to GridPP Funded Month 3
R. Frank | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| A. McNab | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Sheffield | E. Korolkova | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| M. Robinson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | EGI Funded Month 1: 0.5; EGI Funded Month 2: 0.5; EGI Funded Month 3: 0.5
Manchester | A. Forti | bar: Unfunded Month 1 to Unfunded Month 3

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q1
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Procurement CentOs 7 Readiness ZFS testing Tarball Other VO support IPv6 | New kit on its way next quarter Test cluster groundwork layed Ready to deploy zfs on new kit Umd4 versions updated Added SW for other Vos to cluster RIPE moved to IPv6, almost ready to move SE |  |  | Time consuming. None None (yet). None. Still have some problems with stagein/out for non-atlas jobs Fears of IPv6 traffic affects on our network.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Threat that centos 7 will “sneak up on us”. Still need a new SE headnode – current one out of warranty. Dual-stacking our storage might break it or the network. Need to adjust CE/batch to deal with small VO workloads (this is all much the same has last quarter A lot of slippage in Q1 |  |  | Devote more resources and time to testing, setup “mini-cluster” on centos7 Setup dummy SE to test configs first. “Gentle” IPv6 testing New CE might be called for. Q2 has a lot of groundwork layed down already.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Tarball Work Procurement Decommission old nodes Centos 7 build tested |  |  | 30/3/17 |  | Umd4 sl6 tarballs, centos 7 tarball updated New kit incoming Space for new kit Ready to test once tarball WN finished.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Create “grid-facing” centos7 mini-cluster Fix cluster for smaller VO jobs Attempt to roll out a Bro instance as part of SOC work Aid UK NGI pakiti work |  |  | 30/6/2017 |  | Ready to move to centos7-slipped from last quarter Increase userbase=more jobs- requires new CE Increased engagement “”
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q1
Reported by | S Jones, J Bland, R Fay
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Purchase (spec, quote, procure, setup) Sys Admin Software dev Early Adoption/Testing VO Support | DPM Storage server, adding ~ 250 TB Routine sys admin (admin of 3 clusters plus storage, tickets, VO support, VOMS documentation, security certificates, GOCDB Maint, decommission CREAM, HW & SW maint., auto space management, new cooling system work, auto BDII restart, powercut recovery, benchmark corrections, kernel changes x 2.) Adding ranking expr to fallow (mcore drain tool), move Java apps to github/Maven, tweaks to temperature protection measures, For grid systems, Centos 7 Workernode Test Cluster, used to test readiness of LHCb, ATLAS, ILC middleware. Plus puppet modules, and YAIMless WN build. For Cloud systems, tests of migration to VAC V2. For storage, tests of ZFS in progress. Test and monitor newish VAC ALICE support. |  | Under test loads. Cooling to be provided by Liverpool facilities dept. None Centos7 cluster so far underused. Need more customers to use this resource to test C7 migration. None
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | Ipv6 Medium sized site |  | Need to work with external supplier (CSD) Difficult to plot course as medium site, due to various unknowns.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Continue adoption of Centos7, documentation Continue adoption of Ipv6, documentation Finish migration to VAC 02 Finish kernel update CHEP Paper on VAC testing Some HW purchases for GPP5 |  | '31/03/2017 '31/03/2017 '31/03/2017 '31/03/2017 '31/03/2017 '31/03/2017 |  | Centos7 test cluster in use. Docs pending. Postponed to next quarter Complete Complete Publication accepted. Diskserver, purchase complete.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Plans to continue with Tom Whyntie's user guide VAC Superslot/Multicore tests Continue adoption of Centos7, documentation Continue adoption of Ipv6, documentation Continue GridPP5 HW purchases Progress on new cooling from Facilities Convert site to Puppet 3 |  | '30/06/2017 '30/06/2017 '30/06/2017 '30/06/2017 '30/06/2017 '30/06/2017 '30/06/2017 |  | Delayed. Will review next quarter Will ask Andrew McNab about this. An ongoing task over year, moving towards 100% This will be an ongoing task over year. Ongoing task, will report in due course Ongoing task, will report in due course All node types will be parameterised and modular.