## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q1 2017 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 128.7% | 128.7% | 128.7% | 381% | 381% | 381% | 140.1% | 140.1% | 140.1% | 128.4% | 128.4% | 128.4% | 242.6% | 242.6% | 242.6% | 155.6% | 155.6% | 155.6% | 183.6% | 183.9% | 183.9%
.x.2 | % of promised (by that time) CPU available | 100% | 269.8% | 269.8% | 269.8% | 471.4% | 481.1% | 481.1% | 257% | 257% | 257% | 300.4% | 300.4% | 339.5% | 324.4% | 324.4% | 324.4% | 538.8% | 538.8% | 538.8% | 323.8% | 321.5% | 331.1%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 86.9% | 100% | 100% | 99.6% | 100% | 100% | 100% | 100% | 100% | 97.06% | 100% | 100% | 86.77% | 86% | 86% | 99.33% | 98% | 98% | 94.94%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 86.9% | 100% | 100% | 99.6% | 100% | 100% | 100% | 100% | 100% | 97.06% | 100% | 100% | 87.06% | 86% | 86% | 99.55% | 98% | 98% | 95.03%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 64.92% | 65.42% | 64.52% | 37.38% | 57.15% | 44.3% | 83.15% | 88.5% | 88.68% | 67.4% | 70.59% | 81.91% | 68.28% | 72.27% | 83.73% | 59.58% | 77.78% | 78.66% | 63.06% | 69.65% | 75.19%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 60.51% | 59.85% | 57.68% | 29.42% | 46.96% | 35.23% | 74.73% | 77.32% | 78.4% | 60.34% | 58.4% | 52.83% | 57.03% | 52.12% | 66.35% | 53.85% | 69.44% | 71.02% | 54.64% | 55.6% | 58.06%
bi
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2017
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2017-01-01 | 2017-02-01 | 2017-03-01 | Total |  | Site | 2017-01-01 | 2017-02-01 | 2017-03-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 8696651.864 | 6721323.239 | 5754811.336 | 21172786.439 |  | Birmingham | 9577627.2277 | 7336814.8775 | 6769933.1617 | 23684375.2669
Cambridge | UMD 4/SL6 | UMD 4/SL6 |  | 10Gb/s | 2*10Gb/s | DPM 1.8.11 |  | Bristol | 7287843.369 | 1804310.482 | 3216104.719 | 12308258.57 |  | Bristol | 9454495.4364 | 2158791.3627 | 3865257.5942 | 15478544.3933
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.8.11.1 |  | Cambridge | 3214151.877 | 3240863.564 | 3603656.29 | 10058671.731 |  | Cambridge | 3738522.8654 | 3601992.117 | 4037723.7166 | 11378238.699
RALPP | UMD3/4 | UMD3 |  | 10Gb/s | 10Gb/s | Dcache 2.13.51 |  | Oxford | 16015239.58 | 12705796.83 | 15859703.32 | 33632519 |  | Oxford | 18777879.9309 | 14860214.2275 | 18504042.6733 | 52142136.8317
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 20026256.59 | 22637426.72 | 23688608.25 | 66352291.56 |  | RALPP | 27237608.3911 | 26880033.1931 | 29620704.747 | 83738346.3312
[8 empty] | Sussex | 1089707.326 | 1274504.663 | 669072.1703 | 3033284.1593 |  | Sussex | 1240246.7818 | 1387034.1476 | 732406.505 | 3359687.4344
[8 empty] | Total CPU hrs | 56329850.606 | 48384225.498 | 52791956.0853 | 157506032.1893 |  | Total | 70026380.6333 | 56224879.9254 | 63530068.3978 | 189781328.9565
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | efficiency
Birmingham | 16994 | 920 | 6298 | 715 | 269.8% | 128.7% | 14.54% | 16.94% | 21172786.439 | 14.45% | 2160 | 36707040 | 57.68% | 64.52% | 89.4%
Bristol | 16175 | 560 | 3362 | 147 | 481.1% | 381% | 13.84% | 10.31% | 12308258.57 | 8.398% | 2160 | 34938000 | 35.23% | 44.3% | 79.52%
Cambridge | 5940 | 290 | 2311 | 207 | 257% | 140.1% | 5.083% | 5.341% | 10058671.731 | 6.863% | 2160 | 12830400 | 78.4% | 88.68% | 88.4%
Oxford | 29473 | 980 | 8682 | 763 | 339.5% | 128.4% | 25.22% | 18.05% | 33632519 | 22.95% | 2160 | 63661680 | 52.83% | 81.91% | 64.5%
RALPP | 46300 | 2610 | 14274 | 1076 | 324.4% | 242.6% | 39.62% | 48.07% | 66352291.56 | 45.27% | 2160 | 100008000 | 66.35% | 83.73% | 79.24%
Sussex | 1977.32 | 70 | 367 | 45 | 538.8% | 155.6% | 1.692% | 1.289% | 3033284.1593 | 2.07% | 2160 | 4271011.2 | 71.02% | 78.66% | 90.28%
Totals | 116859.32 | 5430 | 35294 | 2953 | 331.1% | 183.9% | 100% | 100% | 146557811.4593 | 100% | 2160 | 252416131.2 | 58.06% | 75.19% | 77.22%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken |  | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Birmingham |  | 0 |  |  | Birmingham | 22433 | 980
Bristol |  | 0 |  |  | Bristol | 9607 | 0
Cambridge |  | 0 |  |  | Cambridge | 5940 | 293
Oxford |  | 0 |  |  | Oxford | 26240 | 940
RALPP |  | 0 |  |  | RALPP | 42840 | 3079
Sussex |  | 0 |  |  | Sussex | 2006 | 83
Totals |  | 0 | 0 | 0
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2017
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 11
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [20 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[44 empty] | 0 | 0
[44 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 2 | 2 | 2 | 1 | 0 | 0 | 3 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 3 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 112
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
0 | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.02423% | 16.43%
Birmingham | 397 | 228 | 0.12 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0.2 | 0.02 |  | 0.53 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 627.501 | 15.61% | 0.3984%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427.4 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427.409 | 10.63% | 0.001638%
Cambridge | 0 | 254.9 | 0 | 0 | 0.1 | 0.02 | 0 | 0 | 0 | 0 | 0.004 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0 |  | 0 | 0 | 0.45 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.944 | 6.366% | 0.2321%
Oxford | 0 | 635 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 | 0.049 | 0.59 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032 | 0 | 0 | 0 | 7.88 | 0.018 | 0.016 | 1.5 | 31.98 | 0 | 0 | 0.0234 | 678.2364 | 16.87% | 6.221%
RALPP | 0 | 644 | 2 | 0.8 | 0 | 0 | 0 | 0 | 0 | 1030 | 0.27 | 0 | 0.148 | 0 | 0 | 0 | 0 | 0 |  | 1.753 | 0 | 332 |  |  | 7.586 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.786 | 0 | 0 | 0 | 0 | 2019.943 | 50.24% | 0.6903%
Sussex |  | 9 | [8 empty] | 0.008 | [25 empty] | 1 |  |  | 0.176 |  |  |  |  | 10.184 | 0.2533% | 11.63%
Total | 397 | 1771.524 | 2.12 | 0.95 | 0.4 | 0.044 | 0 | 0 | 0 | 1458.411 | 0.339 | 0.049 | 0.748 | 0 | 0.025 | 0 | 0.67 | 0.055 | 0 | 2.287 | 0 | 332.672 | 0 | 0 | 7.586 | 0.6 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.052 | 0 | 0 | 0 | 8.88 | 0.018 | 0.016 | 2.462 | 31.98 | 0 | 0 | 0.0434 | 4020.1914 | 100% | 1.507%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2017
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | 1 | 1 | 1
Matt Williams
Bristol | Winnie Lacesso |  |  |  | 0.2 | 0.2 | 0.2
Luke Kreczko
Cambridge
| John Hill |  |  |  | 0.5 | 0.5 | 0.5
Oxford
| Vip Davda | 0.5 | 0.5 | 0.5
| Kashif Mohammad | 0.5 | 0.5 | 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
Jeremy Maris
Total |  | 2.6 | 2.6 | 2.6 | 1.4 | 1.4 | 1.4
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q1 2017
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Made significant progress to converting the site to using VAC. The conversion should be complete by the end of the next quarter. |  | Had a couple of significant outages, one due to DHCP problems and another due to disk issues.
Bristol | - enabled CentOS 7 stacki - first CentOS Worker Nodes (not yet in production) - first CentOS7 submission node under test, - installed Singularity on all worker nodes - testing "bare" worker nodes without pool accounts and without worker node software (instead from CVMFS) - working on a way to have it easier to enable/disable a VO |  | - Some new DICE WN logging Hardware Errors; still under warranty, must find time to run diags & juggle WN storage outage with Dell site visit - Some older (no warranty) DICE WN starting to log hardware/disk problems
Cambridge | perfSonar problem mentioned in last quarterly report indeed due to a full root partition - now fixed. Rack switches moved from back to front of rack to improve cooling. Added nagios probes for switches. Investigating CentOS 7 for service VMs on new server. cvmfs upgraded to 2.3.3 (despite UMD-4 repos trying to prevent it). |  | University IDS enabled in passthrough mode at end of January caused perfSonar bandwidth to be limited to ~1Gbps. Bypass implemented after I raised the issue: bandwidth values reported then returned to normal. Some instability on SQUID - latest version more stable.
Oxford | 1. Eleven Lenovo NextScale nx360 WNs to Grid Condor cluster has been added. It contributed 352 additional jobs slots to cluster. 2. vo-nagios.physics.ox.ac.uk has been decommissioned as SL5 comes to end of its life on 31st March 2017. Storage-monit.physics.ox.ac.uk, which was used as replication server for vo-nagios, has also been decommissioned. |  | Suffered a power outage/ brown out at the Begbroke computer room on Feb 23rd and another on the 6th March 2017.
RALPP | dCache load issues, temporarily solved by splitting dCache headnode, then again by tweaking the database connection parameters to increase the number of threads to just below the number of cores and again by rebuilding the indexes of the BD. dCache 2.16 may bring a fix. Final move of ArcCEs to physical hardware still awaiting delivery of SSD before we can free up the required hardware. Testing of providing storage to Oxford as a T2C for CMS is more-or-less complete, no problems were experienced and the site will remain in production for CMS |  | Bringing up the second half of the redundant pair of departmental firewalls failed again with conflicts between the agregated linls and the Virtual router config resulting in 50% of the traffic being blackholed. An new plan involvong stacking the routers rather than running then as separate units sharing a virtual router has been agreed but not yet implemented The PPD firewall bypass network link failed as it tried to fail-over after the router it connects to rebooted on the Wednesday before the Easter break. The exact issue was not diagnosed until the Friday when no networking cover was available, concequently the site was in unscheduled downtime until the problem was resolved on Tuesday afternoon.
Sussex
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern. |  | Recruitment ongoing at Sussex.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Refine Top Level Router Config |  | 2017-03-31 |  | Ongoing
Bristol: Improve reliability of OS deployment infrastructure |  | 2017-03-31 |  | First version of CentOS7 built
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Refine Top Level Router Config |  | 31/06/2017 |  | Second router is Hot Standby
RALPP: Purchase new hardware with GridPP Allocation |  | 31/06/2017 |  | New hardware is in production
Bristol: First deployment of kubernetes |  | 2017-12-31 |  | Run HTCondor and Apache Spark on kubernetes
Bristol: Test singularity deployment |  | 31/06/2017 |  | Singularity available for local & grid users
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop