## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | LHCb |  |  | Close to target
Year | 2016 |  |  | Not OK
Reported by | Andrew McNab |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Comment Q116 | Comment Q216
1.7.1 | Processing: Fraction of jobs executed at UK T1 | Processing jobs at RAL | Andrew McNab | 15% | 15.3% | 22.2%
1.7.2 | Processing: Fraction of jobs that were successful in the RAL Tier-1 | Processing job status at RAL | Andrew McNab | T1>70% | 93.1% | 96.5%
1.7.3 | Processing: Overall job efficiency | Ratio of http://tinyurl.com/5usmnn6 and http://tinyurl.com/6x5kcwu | Andrew McNab | 90% | 96.2% | 97.2%
1.7.4 | UK T1 SE Reliability | SE Reliability | Andrew McNab | #lost files/Q=0 #diskservers down over 8 hours < 3 | 0 5 | 0 1 | No loss of files, but more disk outages than usual, usually with double disk failures. | LHCb saw a low but persistent rate of failure when copying the results of batch jobs to Castor.
1.7.5 | User analysis: Fraction of jobs that were successful in the RAL Tier-1 | Success fraction of User jobs at RAL | Andrew McNab | 50% | 85.9% | 88.2%
1.7.6 | User analysis: Overall job efficiency | Ratio of http://tinyurl.com/64x95hx and http://tinyurl.com/5ufw9a4 | Andrew McNab | 70% | 94.4% | 93.6%
2.3.1 | LHCb T2 data transfer upload rate | T2 Data upload rates | Andrew McNab | 10MB/s | 12.5 | 15.4
2.3.2 | LHCb No. of sites below WLCG SAM tests uptime target | LHCb Dashboard history | Andrew McNab | <2 sites | 1 | 1
2.3.3 | LHCb Fraction of simulation jobs in the UK | Simulation Job Fraction | Andrew McNab | >18% (WLCG MoU) | 14.4% | 25% | Outside of running, the LHCb HLT dominates MC production and this reduces the fractional size of the UK contribution.
2.3.4 | LHCb job success rates in simulation | Simulation Job Success rate | Andrew McNab | 90% | 88.4% | %90.9 | This figure is pulled down by a number of jobs failing during set up due to cvmfs/squid problems or misconfigurations.
Note on B18: Imported Author: gronbech: how do we measure this
Note on B19: Imported Author: gronbech: how do we measure this

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | LHCb |  |  | Overdue
Quarter | 2016 |  |  | Not yet due
Reported by | Andrew McNab |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
1.7.7 | Report to PMB on delivery during year | Andrew McNab | 2016-12-31 |  | oc docs
1.7.8 | Report to PMB on delivery during year | Andrew McNab | 2017-12-31 |  | oc docs
1.7.9 | Report to PMB on delivery during year | Andrew McNab | 2018-12-31 |  | oc docs
1.7.10 | Report to PMB on delivery during year | Andrew McNab | 2019-12-31 |  | oc docs

## Manpower Q116
GridPP Quarterly Report
Area | LHCb
Quarter | 2016
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Manpower Q216
GridPP Quarterly Report
Area | LHCb
Quarter | 2016
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q116
GridPP Quarterly Report
Area | LHCb
Quarter | Q116
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Smooth running during the stripping campaign and for user analysis jobs.
Tier-2 | User jobs at T2-D sites accessing data placed there. QMUL added as a 4th UK T2-D site for LHCb.
Raja Nadakumar | GEOC shifts and expert LHCb liaison with Tier-1
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only (Ceph-fs) storage technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q216
GridPP Quarterly Report
Area | LHCb
Quarter | Q116
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Smooth running during the stripping campaigns and for user analysis jobs.
Tier-2 | User jobs at T2-D sites accessing data placed there. Liverpool added as a 5th UK T2-D site for LHCb.
Raja Nadakumar | GEOC shifts and expert LHCb liaison with Tier-1
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only (Ceph-fs) storage technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes