## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q316 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 191% | 191% | 616.5% | 358% | 210% | 209.8% | 308% | 176% | 176.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 200% | 192% | 192.5%
.x.2 | % of promised (by that time) CPU available | 100% | 1052% | 1818% | 2589% | 469% | 215% | 215% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 472% | 501% | 500.9%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 97% | 97% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 98.5%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 100% | 97% | 97% | 100% | 100% | 100% | [9 empty] | 100% | 100% | 98.5%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 65% | 68% | 70.52% | 25% | 66% | 38.28% | 66% | 71% | 72.53% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 40% | 69% | 68%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 51% | 55% | 70.42% | 20% | 53% | 34.49% | 51% | 48% | 54.91% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 36% | 52% | 58.64%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q316
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2016-07-01 | 2016-08-01 | 2016-09-01 | Total |  | Site | 2016-07-01 | 2016-08-01 | 2016-09-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 15812164 | 16947272 | 21150056 | 53909492 |  | DURHAM | 15812174 | 16973607 | 21200791 | 53986572
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 3124293 | 1485840 | 2922843 | 7532976 |  | ECDF | 3861923 | 1513170 | 2985642 | 8360735
[8 empty] | GLASGOW | 18518853 | 16561455 | 20139590 | 55219898 |  | GLASGOW | 23380194 | 23475816 | 26079954 | 72935964
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 37455310 | 34994567 | 44212489 | 116662366 |  | Total | 43054291 | 41962593 | 50266387 | 135283271
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 35054 | 240.417 | 1354 | 39 | 2589% | 616.5% | 38.48% | 5.688% | 53909492 | 46.21% | 2184 | 76557936 | 70.42% | 70.52%
ECDF | 10000 | 1133 | 4652 | 540 | 215% | 209.8% | 10.98% | 26.81% | 7532976 | 6.457% | 2184 | 21840000 | 34.49% | 38.28%
GLASGOW | 46043 | 2853 | 12181 | 1617 | 378% | 176.4% | 50.54% | 67.5% | 55219898 | 47.33% | 2184 | 100557912 | 54.91% | 72.53%
Totals | 91097 | 4226.417 | 18187 | 2196 | 500.9% | 192.5% | 100% | 100% | 116662366 | 100% | 2184 | 198955848 | 58.64% | 68%
Please check the figures in the Yellow
| MoU figures taken from 2016 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 264 | 35054 | 240.417 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1133 | 10812256 | ECDF
GLASGOW | 573 | 46043 | 2853 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q316
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [11 empty] | 247.77 | 5.759% | 3.136%
ECDF | 1133 | [14 empty] | 2 | 50 |  |  |  |  | 0 | [12 empty] | 1185 | 27.54% | 0%
GLASGOW | 2853 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 2869.428 | 66.7% | 0.5373%
Total | 4226 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 2 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 4302.198 | 100% | 1.701%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q316
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Oliver Smith | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | M. Ebert | 0 | 0 | 0 | 0.3 | 0.3 | 0.3
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 3 | 3 | 3 | 0.8 | 0.8 | 0.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q316
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Deployed new worker nodes to cluster. New VMware virtual host infrastructure implemented in response to cluster scaling problems Migrated heavily loaded virtual machines to physical hardware (CE2, SLURM and Foreman) and added second SLURM server for load balancing. Deployed LFC for Pheno VO use Rebuilt monitoring systems for grid on new hardware ganglia/graphite/grafana/collectd/ELK/Nagios/OSSec/LibreNMS Testing instance of Bro deployed as part of SOC-WG |  | We have faced some issues with the reliability of our grid services when under heavy load. We attributed this to the increase in the CPU size of the cluster over the last 12 months. The deployment of a new virtual host environment and reorganisation of our internal disk server setup has reduced the issue somewhat. We are seeing very heavy traffic to our DPM disk servers, and at this time require additional disk servers to spread out the load we are facing on our CPU cluster.
ECDF | Use of new ECDF Openstack resources for ATLAS SL6 analysis jobs Scaling up of LHCb production jobs on Eddie Mk3 Filled joint GridPP/LHCb post. Successful applicant is due to start in mid/late November. |  | Old Eddie Mk2 (SL6) cluster switched off due to hardware problems - Ongoing issues with LHC VOs on SL7 resources - Correct fairshare scheduling of GridPP jobs on ECDF still be addressed
GLASGOW | Finished migration of all DPM pool nodes to Centos6. Configured and deployed MISP instance at Glasgow. New themal controls located in server room should reduce any damage incase of power failure to AC units. Test Kubernetes cluster installed and under evaluation. Work ongoing to deploy EGI-WN by RPM configuration |  | Downtime due to power cut, flooding and installation of Thermal contral HW in server room.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Underutilisation of available resources due to lack of SL7 compatibility: we have paid for ringfenced compute nodes that are not being 100% utilised due to lack of job throughput from LHC experiments |  | Contiinue to work with experiments to push forward SL7 compatibility.
Glasgow: Air Condition/power issues leading to damaged equipment |  | Working with E&B to supply new data facility, now scheduled for Aug 2017
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Complete Centos6 Migration of DPM Pool Nodes |  | 2016-09-01 |  | All DPM Pool nodes now migrated to Centos 6
Glasgow: Contribute to and Track work of the SOC WG |  | 2016-09-01 |  | Prepared work and collaboration in line with WG goals to be reported on at the WLCG workshop.
Glasgow: Extend low level data collecion to allow scaling to entire cluster |  | 2016-09-01 |  | Development of probes underway and investigation/evaluation of Timeseries DB carried out.
Durham: Procurement and installation of additional nodes. |  | 2016-09-01 |  | Installed as of 14/10. Delayed due to procurement problems.
Durham: Deploy production OpenStack installation and begin testing production grid services on OpenStack. |  | 2016-09-01 |  | Began this deployment but the hardware earmarked for this project was required for the cluster to reduce the load issue. We hope to secure some additional hardware going forward to attempt this again.
ECDF: Virtualisation of Middle ware services |  | 2016-09-01 |  | Platform available but delay in widespread deployment of new services
ECDF: Eddie Mk3 migration |  | 2016-08-31 |  | Done, forced migration due to premature Mk2 shutdown
ECDF: RDF Storage Replacement |  | 2016-09-01 |  | On hold. Performance issues with RDF storage are first being investigated. Will add it first to the xrootd testbed to check on performance
ECDF: Optimisation for LHC workloads on HPC |  | 2016-08-31 |  | Done. Project written up and submitted
ECDF: intensive ZFS tests (for CHEP conference submission) |  | 31-Sep-2016 |  | Studies completed as part of CHEP 2016 submission
ECDF: Evaluation of plain xrootd multi VO installation possibilities |  | 31-Sep-2016 |  | Moved to next quarter, work will start after HEPiX
ECDF: MISP deployment |  | 31-Sep-2016 |  | MISP server installed, configuration work ongoing
ECDF: Data processing for EUCLID |  | 31-Sep-2016 |  | On hold. Not a current priority for EUCLID ROE staff
Objectives and Deliverables for Next Quarter
Objective/Deliverable
Glasgow: Contribute to and Track work of the SOC WG |  | 2016-12-31 |  | Prepare contribution to be presented at WLCG workshop - October 2016
Glasgow: Transition storage to ZFS and flexible pool management scheme on selected pool nodes. |  | 2016-12-31 |  | Test pool nodes moved to ZFS and moved into production
Glasgow: Evaluation of Kubernetes as a management platform for Grid cluster |  | 2016-12-31 |  | Deploy WN container images to kubernetes cluster.
Durham: Procure and install additional disk server to spread out DPM load. |  | 2016-12-31 |  | Equipment procured and an ETA provided.
Durham: Secure hardware for Openstack production installation and attempt hosting of production grid services |  | 2016-12-31 |  | Identify funding, and procurement strategy for creating production Openstack service
ECDF: Eddie Mk3 workload Scheduling |  | 2016-12-31 |  | Tune scheduling of Grid jobs to ensure GridPP funding is used efficiently
ECDF: HPC scaling tests and middleware integration |  | 2016-12-31 |  | Follow on from optimisation studies and run scaling tests ensuring best use of HPC resources available. Work with ARC developers to better integrate middleware with HPC facilities
ECDF: MISP content sharing |  | 2016-12-31 |  | Configure Edinburgh MISP instance for content sharing with RAL and Glasgow
ECDF: Standalione Xrootd instance |  | 2016-12-31 |  | Install redirector(s) and local storage for tests during November, if successful then extent to other sites (Glasgow)
ECDF: New Test DPM instance |  | 2016-12-31 |  | A new test DPM will be installed in VM during November. if successful, production DPM will also be moved to VM
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Marcus Ebert 50% LUSC DAC Team.
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
GridPP: Storage Evolution - Lightweight Sites |  | 2016-09-01 |  | Sam Skipsey
GridPP: Security Update |  | 2016-09-01 |  | David Crooks
ATLAS Software Quality Update, CERN |  | 28-29/9/16 |  | Andrew Washbrook
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Traceability & Isolation WG |  | Present |  | David Crooks
SOC Working Group |  | Present |  | co-lead by David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A