## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q416 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 191% | 616% | 781% | 210% | 210% | 249.1% | 176% | 176% | 176.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 205.1%
.x.2 | % of promised (by that time) CPU available | 100% | 1818% | 2589% | 2589% | 215% | 215% | 215% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 500.9%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 97% | 97% | 100% | 100% | 100% | 100% | [9 empty] | 100% | 99% | 100%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 97% | 97% | 100% | 100% | 100% | 100% | [9 empty] | 100% | 99% | 100%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 68% | 71% | 90.64% | 66% | 38% | 62.58% | 71% | 73% | 81.67% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 69% | 68% | 83.03%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 55% | 70% | 90.77% | 53% | 34% | 54.7% | 48% | 55% | 61.69% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 52% | 59% | 72.12%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q416
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total |  | Site | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 21573680 | 23091829 | 25590267 | 70255776 |  | DURHAM | 21538572 | 23054361 | 25564524 | 70157457
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 3563328 | 1717609 | 6796701 | 12077638 |  | ECDF | 4008877 | 2419284 | 7388995 | 13817156
[8 empty] | GLASGOW | 22951937 | 15603821 | 24164873 | 62720631 |  | GLASGOW | 29395683 | 23308659 | 30323757 | 83028099
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 48088945 | 40413259 | 56551841 | 145054045 |  | Total | 54943132 | 48782304 | 63277276 | 167002712
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 35054 | 304.6 | 1354 | 39 | 2589% | 781% | 38.48% | 6.764% | 70255776 | 48.43% | 2208 | 77399232 | 90.77% | 90.64%
ECDF | 10000 | 1345.339 | 4652 | 540 | 215% | 249.1% | 10.98% | 29.88% | 12077638 | 8.326% | 2208 | 22080000 | 54.7% | 62.58%
GLASGOW | 46043 | 2853 | 12181 | 1617 | 378% | 176.4% | 50.54% | 63.36% | 62720631 | 43.24% | 2208 | 101662944 | 61.69% | 81.67%
Totals | 91097 | 4502.939 | 18187 | 2196 | 500.9% | 205.1% | 100% | 100% | 145054045 | 100% | 2208 | 201142176 | 72.12% | 83.03%
Please check the figures in the Yellow
| MoU figures taken from 2016 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 264 | 35054 | 304.6 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 46043 | 2853 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q416
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 5.552% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 30.15% | 20.39%
GLASGOW | 2853 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 2869.428 | 64.3% | 0.5373%
Total | 4164 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 4462.537 | 100% | 6.667%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q416
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Oliver Smith | 0 | 0 | 0 | 0 | 0 | 0
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | M. Ebert | 0 | 0 | 0 | 0.3 | 0.3 | 0.3
Edinburgh | R. Currie | 0 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 3 | 3.5 | 3.5 | 0.8 | 0.8 | 0.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q416
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Additional disk server installed, spreading disk load across an extra server. Bandwidth increase for site to 4/4gbit, however issues with the link have been apparent. Future increase to 10gbit discussed and planned for this year. Single SL6 Argus host replaced with load balanced dual SL7 Argus hosts |  | Issues with firewall bypass towards the end of Dec limiting bandwidth to 0.5/4gbit. No obvious impact on site operations.
ECDF | Fully running ATLAS and LHCb SL7 jobs across the Eddie 3 cluster Hired and trained up new post (Rob Currie) to provide Tier-2 site operations support |  | ATLAS configuration changes have resulted in a long standing issue that prevents us from running ATLAS user analysis jobs. Investigation ongoing by DDM experts in ATLAS. We do not have access to opportunistic computing resources due to a security patch that was only partially applied across the Eddie 3 cluster. As a mitigation we have been given exclusive access to more than our paid-for resources for the last two months.
GLASGOW | Tested routing MISP IoC data to campus security team from WLCG through Glasgow instance VM hosting infrastructure installed and working, being used as part of ongoing development of RPM configuration workflow |  | Downtime due to damage power distribution in server room. Currently running with reduced load with scheduled eletrical works in the new year to repair and upgrade distribution
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: We have been affected by a number of cluster outages due to the poor performance of the cluster filesystem. Despite grid jobs not using the filesystem we have been affected due the workload scheduler binaries residing on the affected filesystem. |  | The underlying issues with the filesystem performance are currently being resolved by ECDF staff. In case of any future issues with the cluster filesystem we have requested that a portable version of the scheduler binaries be made available.
Glasgow: Air Condition/power issues leading to damaged equipment |  | Working with E&B to supply new data facility, now scheduled for Aug 2017
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Contribute to and Track work of the SOC WG |  | 2016-12-31 |  | Presented on status of WLCG SOC WG at December GDB; tested sync of Glasgow MISP instance with WLCG instance and local Glasgow access
Glasgow: Transition storage to ZFS and flexible pool management scheme on selected pool nodes. |  | 2016-12-31 |  | Ongoing, systems earmarked for initial testing.
Glasgow: Evaluation of Kubernetes as a management platform for Grid cluster |  | 2016-12-31 |  | Test system set up on three older WN, initial attempts at conainerising MW ongoing
Durham: Procure and install additional disk server to spread out DPM load. |  | 2016-12-31 |  | Disk server procured and installed as of 17/01
Durham: Secure hardware for Openstack production installation and attempt hosting of production grid services |  | 2016-12-31 |  | Hardware identified, installation and initial testing will begin in January
ECDF: Eddie Mk3 workload Scheduling |  | 2016-12-31 |  | Dependent on input and changes form ECDF staff which was postponed due to ongoing problems with cluster filesystem
ECDF: HPC scaling tests and middleware integration |  | 2016-12-31 |  | Started to refactor performance analysis from Q316 and took part in discussions with ARC developers at their brainstorming camp about future directions of HPC integration. Work ongoing throughout this year.
ECDF: MISP content sharing |  | 2016-12-31 |  | Work postponed to this quarter
ECDF: Standalone Xrootd instance |  | 2016-12-31 |  | Work postponed to this quarter since another server needs be made available first
ECDF: New Test DPM instance |  | 2016-12-31 |  | Waiting for Atlas to move data out of the old test DPM installation, work postponed to this quarter
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Begin investigation of Bro IDS as part of SOC WG |  | 2017-03-31 |  | Report on SOC WG at ISGC, March 2017
Glasgow: Deploy VM MISP instance as part of SOC WG |  | 2017-03-31 |  | Report on SOC WG at ISGC, March 2017
Glasgow: Investigate test deployment of pakiti for UK NGI Security Team |  | 2017-03-31 |  | Reporting at UK NGI Security team meeting
ECDF: Investigate use of Ansible for automated configuration of MW |  | 2017-03-31 |  | Setting up a test VM running services such as BDII deployed using Ansible aiming to replace/upgrade production services
ECDF: Openstack migration |  | 2017-06-30 |  | Plan to move our main Grid job workflow to the new Eddie 3 Openstack service following a successful trial run last year
ECDF: MISP content sharing |  | 2017-03-31 |  | Work will continue with Rob Currie providing effort to help initiative from SOC WG led by David Crooks
ECDF: Moving production DPM to new Hypervisor machine |  | 2017-03-31 |  | Production DPM, still on SL5, needs to be moved as soon as possible due to end-of-support for SL5 by end of March
ECDF: Standalone Xrootd instance |  | 2017-03-31 |  | Test configuration available, need to make a server with real storage space available to test real life usage of such installation for Atlas, prototype should be ready and tested by GridPP38
ECDF: New Test DPM instance |  | 2017-03-31 |  | Work depends on timing of Atlas moving all their files out of the current test DPM installation (19TB left)
Durham: Continue with Openstack production installation, move backend grid service as initial test and trial openstack nodes |  | 2017-03-31 |  | Openstack production instance built and stable. Argus instance running from Openstack along with VM nodes in SLURM
Durham: Finish procurement of additional nodes and disk, and install. |  | 2017-03-31 |  | Additional nodes and disk installed, increase in capacity
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Marcus Ebert 50% LUSC DAC Team.
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
HEPSYSMAN, "WLCG Federated Access" |  | 2016-11-07 |  | David Crooks
GDB, "SOC Working Group Report" |  | 2016-12-14 |  | David Crooks
HEPiX, "ZFS on Linux" |  | 2016-10-19 |  | Marcus Ebert
CHEP, "Evaluation of ZFS as an efficient WLCG storage backend" |  | 2016-10-10 |  | Marcus Ebert
Presentation on Static Code Analysis in ATLAS for Software Quality Analysis workshop, CERN |  | 2016-11-23 |  | Andrew Washbrook
ATLAS Coordination of 2nd Openlab/Intel Workshop on Code Optimisation (summary talk given to ATLAS software community on 15/12/2016) |  | 24-25/11/2016 |  | Andrew Washbrook
UK sites representative for the ARC Brainstorming Camp (summary talk given in UK Ops meeting on 13/12/2016) |  | 28/11/2016 - 02/12/2016 |  | Andrew Washbrook
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Traceability & Isolation WG |  | Present |  | David Crooks
SOC Working Group |  | Present |  | co-lead by David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A