## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q117 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 616% | 781% | 781% | 210% | 249% | 249.1% | 176% | 176% | 176.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 205.1%
.x.2 | % of promised (by that time) CPU available | 100% | 2589% | 2589% | 2589% | 215% | 215% | 215% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 500.9%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 98.9% | 97% | 100% | 87.28% | 100% | 100% | 90.12% | [9 empty] | 100% | 99% | 88.7% | Glasgow low availabilty due to power cut leading to issues with cooling and corrupt DPM database
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 98.9% | 97% | 100% | 90.16% | 100% | 100% | 90.56% | [9 empty] | 100% | 99% | 90.36% | Glasgow low reliabilitydue to power cut leading to issues with cooling and corrupt DPM database
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 71% | 91% | 87.78% | 38% | 63% | 99.42% | 73% | 82% | 76.73% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 69% | 68% | 83.48%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 70% | 91% | 87.84% | 34% | 55% | 93.94% | 55% | 62% | 60.7% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 52% | 59% | 74.79%
Availablity and Reliability figures reduced for ECDF due to problems with ARGO monitoring probes, see https://ggus.eu/?mode=ticket_info&ticket_id=126349
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q117
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2017-01-01 | 2017-02-01 | 2017-03-01 | Total |  | Site | 2017-01-01 | 2017-02-01 | 2017-03-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 26070570 | 19497488 | 20942756 | 66510814 |  | DURHAM | 26021481 | 19510274 | 20936091 | 66467846
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 6530835 | 7024858 | 6735883 | 20291576 |  | ECDF | 6677785 | 7637691 | 7159559 | 21475035
[8 empty] | GLASGOW | 21882984 | 20728491 | 17757868 | 60369343 |  | GLASGOW | 29383992 | 25411555 | 21516027 | 76311574
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 54484389 | 47250837 | 45436507 | 147171733 |  | Total | 62083258 | 52559520 | 49611677 | 164254455
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | efficiency?
DURHAM | 35054 | 304.6 | 1354 | 39 | 2589% | 781% | 38.48% | 6.764% | 66510814 | 45.19% | 2160 | 75716640 | 87.84% | 87.78% | 100.1%
ECDF | 10000 | 1345.339 | 4652 | 540 | 215% | 249.1% | 10.98% | 29.88% | 20291576 | 13.79% | 2160 | 21600000 | 93.94% | 99.42% | 94.49%
GLASGOW | 46043 | 2853 | 12181 | 1617 | 378% | 176.4% | 50.54% | 63.36% | 60369343 | 41.02% | 2160 | 99452880 | 60.7% | 76.73% | 79.11%
Totals | 91097 | 4502.939 | 18187 | 2196 | 500.9% | 205.1% | 100% | 100% | 147171733 | 100% | 2160 | 196769520 | 74.79% | 83.48% | 89.6%
Please check the figures in the Yellow
| MoU figures taken from 2016 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 264 | 35054 | 304.6 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 46043 | 2853 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q117
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 5.552% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 30.15% | 20.39%
GLASGOW | 2853 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 2869.428 | 64.3% | 0.5373%
Total | 4164 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 4462.537 | 100% | 6.667%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q117
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Oliver Smith | 0 | 0 | 0 | 0 | 0 | 0
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | M. Ebert | 0 | 0 | 0 | 0.3 | 0.3 | 0.3
Edinburgh | R. Currie | 0 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 3 | 3.5 | 3.5 | 0.8 | 0.8 | 0.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q117
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Procuement of new hardware. Installation of new Disk Server (available via DPM). Delivery of new nodes, awiating to be installed. A test environment for Docker/MESOS has been setup and currently in development in an aim to provide WN containers. Initial testing of xRootD |  | Univeristy lost core routing which disconnected the cluster from the internet (12 hours). There is a capacity issue on the internet connection for the cluster which is causing bandwidth to drop away; this is being investigated. An upgrade to SLURM has caused some instabilities which caused a short period (4 hours) of downtime initiailly although this has now been mitigated; possible issue with SSSD and enumeration although we're investigating this further. A failure on a virtual host caused SLURM to lock up for a couple of hours over a weekend.
ECDF | Coordination of Fed Xrootd service and pilot studies at other ScotGrid sites, Upgrade of our production DPM, Deployment of new test DPM for WLCG readiness effort |  | Two lengthy outages in January due to problems with cluster storage. This has since been stable.
GLASGOW | Procurement and delivery complete of Tranche Hardware Works completed to improve power and resiliency within server rooms |  | Power cut lead to reduced availabilty this quarter
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Use of RDF disk in production environment means we are risk of outages as part of external maintanence |  | Working with RDF team to minsimise outages to at least once per quarter
Glasgow: Air Condition/power issues leading to damaged equipment |  | Working with E&B to supply new data facility, now scheduled for Aug 2017
Durham: DISK! Our local VO home space disk server has chewed up and spat out a couple of disks meaning it was showing some performance issues; along with said server deciding to RAID scrub while it was undergoing a ZFS resilver. |  | Asked the server to play nicely as well as giving it nice shiney new disks and disabling RAID verify/scrub for the (single disk) arrays. There was no noticable impact on the cluster.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Begin investigation of Bro IDS as part of SOC WG |  | 2017-03-31 |  | Complete and reported on at ISGC
Glasgow: Deploy VM MISP instance as part of SOC WG |  | 2017-03-31 |  | Complete and reported on at ISGC
Glasgow: Investigate test deployment of pakiti for UK NGI Security Team |  | 2017-03-31 |  | Investigation has begun, ongoing
ECDF: Investigate use of Ansible for automated configuration of MW |  | 2017-03-31 |  | Evaluation complete, now deploying Ainsible across the site
ECDF: Openstack migration |  | 2017-06-30 |  | Stalled. Loss of Marcus meant we refocused on storage development. Aim to deploy over next quarter
ECDF: MISP content sharing |  | 2017-03-31 |  | No progress, work moved to this quarter
ECDF: Moving production DPM to new Hypervisor machine |  | 2017-03-31 |  | Done
ECDF: Standalone Xrootd instance |  | 2017-03-31 |  | Done
ECDF: New Test DPM instance |  | 2017-03-31 |  | Done
Durham: Continue with Openstack production installation, move backend grid service as initial test and trial openstack nodes |  | 2017-03-31 |  | Openstack was setup and tested although the complexity and instability was too much of a significant problem to continue trialing the platform at this time.
Durham: Finish procurement of additional nodes and disk, and install. |  | 2017-03-31 |  | Completed
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Continue deployment of pakiti for UK NGI Security Team |  | 2017-06-30 |  | Reporting at Security Team meeting
Glasgow: Deploy internal CA |  | 2017-06-30 |  | Reporting at T2 Technical meeting
Glasgow: Deploy internal elasticsearch cluster |  | 2017-06-30 |  | Reporting at T2 Technical meeting
Durham: Trial Docker/Containers |  | 2017-06-30 |  | Reporting at T2 Technical meeting
Durham: Install new nodes |  | 2017-06-30 |  | There will be more nodes available. Reporting at T2 Technical meeting
ECDF: Openstack migration |  | 2017-06-30 |  | Reporting at T2 Technical meeting
ECDF: Singularity evaluation on Eddie3 and Tier-2 HPC |  | 2017-08-30 |  | Reporting at T2 Technical meeting
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Marcus Ebert (and replacement) 50% LUSC DAC Team.
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
Marcus Ebert |  | 2017-04-01 |  | University of Victoria (Canada)
Dissemination events |  | Date |  | Notes
ISGC, "WLCG Security Operations Centres Working Group" |  | 2017-03-07 |  | David Crooks
Ran ATLAS Code Review Shift Tutorial, CERN |  | 2017-02-02 |  | Andrew Washbrook
ATLAS Software Quality presentation, CERN |  | 2017-03-15 |  | Andrew Washbrook
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Traceability & Isolation WG |  | Present |  | David Crooks
SOC Working Group |  | Present |  | co-lead by David Crooks
EGI Software Vulnerability Group |  | Present |  | David Crooks
UK NGI Security Team |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A