## Overview
GridPP5 Goal
Distributed Computing for Particle Physics
Tier- 1 |  | WP1 | Tier-1 |  | WP1 | Tier-2 |  | WP2 |  |  | WP3 |  |  | WP4
Operations |  |  | Experiments |  |  | Experiments and Ops |  |  | Grid and expt support |  |  | Management and Impact
Manager: A. Dewhurst |  |  | Manager: A.Dewhurst |  |  | Manager: S. Lloyd |  |  | Manager: J. Coles |  |  | Manager: D. Britton
| Task 1.1 |  |  | Task 1.5 |  |  | Task 2.1 |  |  | Task 3.2 |  |  | Task 4.1
|  |  |  | ATLAS |  |  | ATLAS
| Production and grid |  |  | Tier-1 |  |  | Tier-2 |  |  | Data Group |  |  | Planning
| A. Dewhurst |  |  | R.Jones |  |  | R.Jones |  |  | D.Colling |  |  | P Gronbech
| Task 1.2 |  |  | Task 1.6 |  |  | Task 2.2 |  |  | Task 3.3 |  |  | Task 4.2
|  |  |  | CMS |  |  | CMS
| Storage system |  |  | Tier-1 |  |  | Tier-2 |  |  | Security |  |  | Execution
| A. Dewhurst |  |  | D.Colling |  |  | D.Colling |  |  | D. Kelsey |  |  | P Gronbech
| Task 1.3 |  |  | Task 1.7 |  |  | Task 2.3 |  |  | Task 3.4 |  |  | Task 4.3
| Fabric and |  |  | LHCb |  |  | LHCb
| machine room |  |  | Tier-1 |  |  | Tier-2 |  |  | Experiment Support |  |  | Outreach
| A. Dewhurst |  |  | A. McNab |  |  | A. McNab |  |  | P.Gronbech |  |  | No one.
| Task 1.4 |  |  | Task 1.8 |  |  | Task 2.4
Hardware
| procurement |  |  | Other expts Tier-1 |  |  | Other expts Tier-2
| A. Dewhurst |  |  | P.Gronbech |  |  | P.Gronbech
Task 3.1
Grid Deployment and
Operational Performance
J.Coles

## Metrics and Milestones
GridPP5 Goal
Distributed Computing for Particle Physics
[26 empty] | Date | 2019-04-29
[26 empty] | 124 |  | Metric OK
| Tier- 1 |  |  |  | WP1 | Tier-1 |  |  |  | WP1 | Tier-2 |  |  | WP2/3 |  |  |  |  | WP3 |  |  |  |  | WP4 |  | 14 |  | Metric close to target
| Operations |  |  |  |  | Experiments |  |  |  |  | Experiments and Ops |  |  |  |  | Grid and expt support |  |  |  |  | Management and Impact |  |  |  |  | 1 |  | Metric not OK
[26 empty] | 3 |  | Not able to be measured
[26 empty] | 44 |  | Milestone achieved
| Production and grid |  |  |  |  | ATLAS T1 |  |  |  |  | ATLAS T2 |  |  |  |  | Data Group |  |  |  |  | Planning |  |  |  |  | 0 |  | Milestone underway
| 1.1 |  |  |  |  | 1.5 |  |  |  |  | 2.1 |  |  |  |  | 3.2 |  |  |  |  | 4.1 |  |  |  |  | 2 |  | Milestone overdue
| 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.5.5 | 2.1.1 | 2.1.2 | 2.1.3 | 2.1.4 | 2.1.5 | 3.2.1 | 3.2.2 | 3.2.3 | 3.2.4 | 3.2.5 | 4.1.1 | 4.1.2 | 4.1.3 | 4.1.4 | 4.1.5 | 26 |  | Milestone not due / metric n/a
| 1.1.6 | 1.1.7 | 1.1.8 | 1.1.9 | 1.1.10 | 1.5.6 | 1.5.7 | 1.5.8 | 1.5.9 |  | 2.1.6 | 2.1.7 | 2.1.8 |  |  | 3.2.6 | 3.2.7 | 3.2.8 | 3.2.9 | 3.2.10 | 4.1.6 | 4.1.7 | 4.1.8 | 4.1.9 | 4.1.10 | 3 |  | Suspended
| 1.1.11 | 1.1.12 | 1.1.13 | [12 empty] | 3.2.11 | 3.2.12 |  |  |  | 4.1.11 | 4.1.12 | [5 empty] | Awaiting input
[26 empty] | 217 |  | Total | 217
| Storage system |  |  |  |  | CMS T1 |  |  |  |  | CMS T2 |  |  |  |  | Security |  |  |  |  | Execution
| 1.2 |  |  |  |  | 1.6 |  |  |  |  | 2.2 |  |  |  |  | 3.3 |  |  |  |  | 4.2
| 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5 | 2.2.1 | 2.2.2 | 2.2.3 | 2.2.4 | 2.2.5 | 3.3.1 | 3.3.2 | 3.3.3 | 3.3.4 | 3.3.5 | 4.2.1 | 4.2.2 | 4.2.3 | 4.2.4 | 4.2.5
| 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.6.6 | 1.6.7 | 1.6.8 | 1.6.9 | 1.6.10 | 2.2.6 | 2.2.7 | 2.2.8 | [7 empty] | 4.2.6 | 4.2.7 | 4.2.8 | 4.2.9 | 4.2.10
| 1.2.11 | 1.2.12 | [18 empty] | 4.2.11 | 4.2.12 | 4.2.13 | 4.2.14 | 4.2.15
[21 empty] | 4.2.16 | 4.2.17 | 4.2.18
| Fabric |  |  |  |  | LHCb T1 |  |  |  |  | LHCb T2 |  |  |  |  | Experiment Support |  |  |  |  | Outreach
| 1.3 |  |  |  |  | 1.7 |  |  |  |  | 2.3 |  |  |  |  | 3.4 |  |  |  |  | 4.3
| 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.7.1 | 1.7.2 | 1.7.3 | 1.7.4 | 1.7.5 | 2.3.1 | 2.3.2 | 2.3.3 | 2.3.4 | 2.3.5 | 3.4.1 | 3.4.2 | 3.4.3 | 3.4.4 | 3.4.5 | 4.3.1 | 4.3.2 | 4.3.3 | 4.3.4 | 4.3.5
| 1.3.6 | 1.3.7 | 1.3.8 | 1.3.9 | 1.3.10 | 1.7.6 | 1.7.7 | 1.7.8 | 1.7.9 | 1.7.10 | [5 empty] | 3.4.6 | 3.4.7 | 3.4.8 | 3.4.9 | 3.4.10 | 4.3.6 | 4.3.7 | 4.3.8 | 4.3.9 | 4.3.10
| 1.3.11 |  |  |  |  | 1.7.11 | [9 empty] | 3.4.11 | 3.4.12 | 3.4.13 | 3.4.14 |  | 4.3.11
| Hardware Procurement |  |  |  |  | Other expts T1 |  |  |  |  | Other expts T2
| 1.4 |  |  |  |  | 1.8 |  |  |  |  | 2.4
| 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.8.1 | 1.8.2 | 1.8.3 | 1.8.4 | 1.8.5 | 2.4.1 | 2.4.2
| 1.4.6 | 1.4.7 | 1.4.8 | 1.4.9 | 1.4.10 | 1.8.6 | 1.8.7 | 1.8.8 | 1.8.9
| 1.4.11 | 1.4.12 | 1.4.13 | 1.4.14 | 1.4.15
1.4.16
Deployment and Performance
3.1
[11 empty] | 3.1.1 | 3.1.2 | 3.1.3 | 3.1.4 | 3.1.5
[11 empty] | 3.1.6 | 3.1.7 | 3.1.8 | 3.1.9 | 3.1.10
[11 empty] | 3.1.11 | 3.1.12 | 3.1.13 | 3.1.14 | 3.1.15
[11 empty] | 3.1.16 | 3.1.17 | 3.1.18 | 3.1.19 | 3.1.20
[11 empty] | 3.1.21 | 3.1.22 | 3.1.23 | 3.1.24 | 3.1.25
[11 empty] | 3.1.26 | 3.1.27 | 3.1.28 | 3.1.29 | 3.1.30
3.1.31
Note on AO17: Peter Gronbech: New Data group milestone added in Q318

## WP1
WP1 | Tier-1 Status
Manager: Andrew Sansum
Task no. | Task | Metric | Milestone | Baseline Target date | Target/ date | Monthly | Date completed | Owner | Description | Q418 | Comment | status
1.1 | Production and grid | 1 |  |  | 100% |  |  | Alastair Dewhurst | Fraction of WLCG MoU commitment for CPU 100 % | 119%%
1.1 | Production and grid | 2 |  |  | 100% |  |  | Alastair Dewhurst | % met of RB allocation for CPU 100 % | 118%%
1.1 | Production and grid | 3 |  |  | 99% |  |  | Alastair Dewhurst | Availability of CE service 99 %
1.1 | Production and grid | 4 |  |  | 2 | Yes |  | Alastair Dewhurst | Number of Security Incidents 2 per year | 0
1.1 | Production and grid | 5 |  |  | 0 | Yes |  | Alastair Dewhurst | # level 3 incidents(newly entered or active) in disaster management system 0 | 0
1.1 | Production and grid | 6 |  |  | 0 | Yes |  | Alastair Dewhurst | # level 4 incidents (newly entered or active) in disaster management system 0 | 0
1.1 | Production and grid | 7 |  |  | 0.94 |  |  | Alastair Dewhurst | Percentage of GRIDPP5 Staff in Post 94 % | 99%
1.1 | Production and grid |  | 8 | 2016-06-01 | 2016-10-01 |  | 2016-10-01 | Alastair Dewhurst | Strategic and operations plan agreed |  |  | Completed
1.1 | Production and grid |  | 9 | 2016-11-01 | 2016-11-01 |  |  | Alastair Dewhurst | GridPP review of operation (biennial) |  | Tier-1 review 1.2.17 | Completed
1.1 | Production and grid |  | 10 | 2017-06-01 | 2017-06-01 |  |  | Alastair Dewhurst | Strategic and operations plan agreed |  |  | Completed
1.1 | Production and grid |  | 11 | 2018-06-01 | 2018-06-01 |  |  | Alastair Dewhurst | Strategic and operations plan agreed |  |  | Completed
1.1 | Production and grid |  | 12 | 2018-10-01 | 2018-10-01 |  |  | Alastair Dewhurst | GridPP review of operation (biennial) |  |  | Completed
1.1 | Production and grid |  | 13 | 2019-06-01 | 2019-06-01 |  |  | Andrew Sansum | Strategic and operations plan agreed |  |  | on track
1.2 | Storage system | 1 |  |  | 1 |  |  | Alastair Dewhurst | Fraction of WLCG MoU commitment for Disk 100 % | 155%
1.2 | Storage system | 2 |  |  | 1 |  |  | Alastair Dewhurst | Fraction of WLCG MoU commitment for Tape 100 % | 95%
1.2 | Storage system | 3 |  |  | 1 |  |  | Alastair Dewhurst | % met of RB Allocation for Tape 100 % | 84%
1.2 | Storage system | 4 |  |  | 1 |  |  | Alastair Dewhurst | % met of RB Allocation for Disk 100 % | 98%
1.2 | Storage system | 5 |  |  | 2 |  |  | Alastair Dewhurst | # Storage node failures leading to filesystem loss or damage | 0
1.2 | Storage system | 6 |  |  | 1% |  |  | Alastair Dewhurst | % Lost disk server hours due to hardware problems over deployed base | <1% | Difficult to estimate. No disk servers were out in Echo, but an increasing number are having problems in Castor.
1.2 | Storage system | 7 |  |  | 1 |  |  | Alastair Dewhurst | Number of Damaged GRIDPP Tapes, leading to data loss 1 in 500 | 0 | 6 ATLAS files lost
1.2 | Storage system | 8 |  |  | 99% |  |  | Alastair Dewhurst | CASTOR SAM tests: ATLAS VO
1.2 | Storage system | 9 |  |  | 99% |  |  | Alastair Dewhurst | CASTOR SAM tests: ALICE VO | 100%%
1.2 | Storage system | 10 |  |  | 99% |  |  | Alastair Dewhurst | CASTOR SAM tests: CMS VO
1.2 | Storage system | 11 |  |  | 99% |  |  | Alastair Dewhurst | CASTOR SAM tests: LHCb VO
1.2 | Storage system | 12 |  |  | 99% |  |  | Alastair Dewhurst | Reliability of tape robot 99 % | 100%%
1.3 | Fabric and machine room | 1 |  |  | 97% | Yes |  | Alastair Dewhurst | WLCG Service Availability Target (set lower by WLCG than MoU, taken from OPS availability) 97 % | 99%%
1.3 | Fabric and machine room | 2 |  |  | 97% | Yes |  | Alastair Dewhurst | WLCG Service Availability for Alice 97 % | 98.7%
1.3 | Fabric and machine room | 3 |  |  | 97% | Yes |  | Alastair Dewhurst | WLCG Service Availability for ATLAS 97 % | 99.3%
1.3 | Fabric and machine room | 4 |  |  | 97% | Yes |  | Alastair Dewhurst | WLCG Service Availability for CMS 97 % | 97.3%
1.3 | Fabric and machine room | 5 |  |  | 97% | Yes |  | Alastair Dewhurst | WLCG Service Availability for LHCB 97 % | 100%
1.3 | Fabric and machine room | 6 |  |  | 95% |  |  | Gareth Smith | Respond to pager within 2 hours 95 % | 100%
1.3 | Fabric and machine room | 7 |  |  | 3 per month |  |  | Gareth Smith | Number of GGUS Tickets not responded to within two hours . | 0
1.3 | Fabric and machine room | 8 |  |  | 70% |  |  | Gareth Smith | Job Efficiency (CPU/Wall) 70 % | 82.3%
1.3 | Fabric and machine room | 9 |  |  | 70 |  |  | Gareth Smith | Farm Occupancy 70 % | 97.1%
1.3 | Fabric and machine room | 10 |  |  | 75% |  |  | Gareth Smith | Percentage used of available T1 Disk 1 in quarter (target between 75% +_ 20%)
1.3 | Fabric and machine room | 11 | [5 empty] | Gareth Smith | Used tape capacity (TB) | 41034
1.4 | Hardware procurement |  | 1 | 2016-06-01 | 2016-06-01 |  | 2016-10-01 | Alastair Dewhurst | Produce the purchasing plan | 2017-01-01 | A purchasing plan swas produced but changes in the amount of money available require the plan to be re-visited. | completed
1.4 | Hardware procurement |  | 2 | 2016-11-01 | 2016-11-01 |  | 2017-02-01 | Alastair Dewhurst | FY16 Capacity order placed | 2017-02-01 | Order for CPU & disk storage received by vendor mid-Feb. | completed
1.4 | Hardware procurement |  | 3 | 2017-04-01 | 2017-04-01 |  |  | Alastair Dewhurst | FY16 Purchase in production |  | CPU in use. Storage in Echo | completed
1.4 | Hardware procurement |  | 4 | 2017-05-01 | 2017-05-01 |  |  | Alastair Dewhurst | Tier-1 WLCG MoU commitments met |  | As shown in metrics. | completed
1.4 | Hardware procurement |  | 5 | 2017-06-01 | 2017-06-01 |  |  | Alastair Dewhurst | Produce the purchasing plan |  | Planning completed so that tenders could be issued. | completed
1.4 | Hardware procurement |  | 6 | 2017-11-01 | 2017-11-01 |  |  | Alastair Dewhurst | FY17 Capacity order placed |  | Tenders issued at end of November. Orders placed January 2018. - technically outside this quarter - but it is now done. | completed
1.4 | Hardware procurement |  | 7 | 2018-04-01 | 2018-04-01 |  |  | Alastair Dewhurst | FY17 Purchase in production |  | 50% of CPU in production by June. XMA CPU and all storage still behind. | completed
1.4 | Hardware procurement |  | 8 | 2018-05-01 | 2018-05-01 |  |  | Alastair Dewhurst | Tier-1 WLCG MoU commitments met |  | Waiting on CPU delivery, storage is being ramped up slowly. | completed
1.4 | Hardware procurement |  | 9 | 2018-06-01 | 2018-06-01 |  |  | Alastair Dewhurst | Produce the purchasing plan |  | Unclear finance situation, new hardware is not in production, so hard to make predictions about what we will need. | completed
1.4 | Hardware procurement |  | 10 | 2018-11-01 | 2018-11-01 |  |  | Alastair Dewhurst | FY18 Capacity order placed |  | Disk Tender runs until 7th December. CPU direct award placed in December. | completed
1.4 | Hardware procurement |  | 11 | 2019-04-01 | 2019-04-01 |  |  | Alastair Dewhurst | FY18 Purchase in production |  |  | on track
1.4 | Hardware procurement |  | 12 | 2019-05-01 | 2019-05-01 |  |  | Alastair Dewhurst | Tier-1 WLCG MoU commitments met |  |  | on track
1.4 | Hardware procurement |  | 13 | 2019-06-01 | 2019-06-01 |  |  | Alastair Dewhurst | Produce the purchasing plan |  |  | on track
1.4 | Hardware procurement |  | 14 | 2019-11-01 | 2019-11-01 |  |  | Alastair Dewhurst | FY19 Capacity order placed |  |  | on track
1.4 | Hardware procurement |  | 15 | 2020-04-01 | 2020-04-01 |  |  | Alastair Dewhurst | FY19 Purchase in production |  |  | on track
1.4 | Hardware procurement |  | 16 | 2020-05-01 | 2020-05-01 |  |  | Alastair Dewhurst | Tier-1 WLCG MoU commitments met |  |  | on track
Number of network outages?? Performance or impact??
How to capture capacity issues on external links?
Average load in and out? Average vs peak?
personar gives some measures
Average FTS rate?
Note on K7: gronbech: Fraction of WLCG MoU commitment for CPU 100 %: This is 90% of total farm capacity divided by the WLCG (i.e. LHC VOs only) pledge as provided to us via GridPP. % met of RB allocation for CPU 100 %: This is the whole farm capacity divided by. the total pledge including that for the non-LHC experiments.
Note on M12: Peter Gronbech: Target to be £100K equivalent, ie 1FTE. SO Current target is 16.5 FTE
Note on K13: gronbech: eg planning for staffing levels in coming (april) year.

## WP1 - Experiments
WP1 |  | Tier-1 delivery to experiments
Manager: Andrew Sansum
Task no. | Experiment | Metric | Milestone | Baseline Target Date | Target/ date | Monitored monthly? | Date Completed | Owner | Description | Q418 | Comment | Status
1.5 | ATLAS | 1 | [5 empty] | Roger Jones | T1 Required hardware deployed
1.5 | ATLAS | 2 |  |  | 0.95 | Yes? |  | Roger Jones | T1 Job success rates from ATLAS dashboard (site-only metrics) | 0.952
1.5 | ATLAS | 3 |  |  | 0.98 | Yes? |  | Roger Jones | T1 Data availability from the ATLAS dashboard; if we can automate this reliably, we can make it monthly | 0.95
1.5 | ATLAS | 4 |  |  | 0.98 | Yes? |  | Roger Jones | Data acceptance from Tier 0/Tier 1s/Tier 2s - ATLAS SAM tests | 0.957
1.5 | ATLAS | 5 |  |  | 0.01 |  |  | Roger Jones | Data loss
1.5 | ATLAS |  | 6 | 2016-12-01 | 2016-12-01 |  |  | Roger Jones | Report on delivery to Atlas during year |  | OC Docs and review SS | completed
1.5 | ATLAS |  | 7 | 2017-12-01 | 2017-12-01 |  |  | Roger Jones | Report on delivery to Atlas during year |  | OC Docs and review SS | completed
1.5 | ATLAS |  | 8 | 2018-12-01 | 2018-12-01 |  |  | Roger Jones | Report on delivery to Atlas during year |  |  | on track
1.5 | ATLAS |  | 9 | 2019-12-01 | 2019-12-01 |  |  | Roger Jones | Report on delivery to Atlas during year |  |  | on track
1.6 | CMS | 1 | [5 empty] | Dave Colling | Data Transfer quality
1.6 | CMS | 2 | [5 empty] | Dave Colling | Timely and efficient availability and use of resources at RAL T1
1.6 | CMS | 3 |  |  |  | Yes |  | Dave Colling | Data Loss at Tier-1
1.6 | CMS | 4 |  |  | 0.9 |  |  | Dave Colling | Site availability at the Tier-1
1.6 | CMS | 5 | [5 empty] | Dave Colling | Data availability via AAA
1.6 | CMS | 6 |  |  | 8% |  |  | Dave Colling | CMS Fraction of Tier-1 work carried out at RAL
1.6 | CMS |  | 7 | 2016-12-01 | 2016-12-01 |  |  | Dave Colling | Report on delivery to CMS during year |  |  | completed
1.6 | CMS |  | 8 | 2017-12-01 | 2017-12-01 |  |  | Dave Colling | Report on delivery to CMS during year |  |  | completed
1.6 | CMS |  | 9 | 2018-12-01 | 2018-12-01 |  |  | Dave Colling | Report on delivery to CMS during year |  |  | on track
1.6 | CMS |  | 10 | 2019-12-01 | 2019-12-01 |  |  | Dave Colling | Report on delivery to CMS during year |  |  | on track
1.7 | LHCB | 1 |  |  | 0.9 |  |  | Andrew McNab | RAL prod success rate | 97.1%
1.7 | LHCb | 2 |  |  | 90% | Yes |  | Andrew McNab | RAL prod CPU efficiency | 94.4%
1.7 | LHCb | 3 |  |  | 0.5 |  |  | Andrew McNab | RAL user success rate | 87.6%
1.7 | LHCb | 4 |  |  | 70% |  |  | Andrew McNab | RAL user CPU efficiency | 92%
1.7 | LHCb | 5 |  |  | 0.15 |  |  | Andrew McNab | UK Tier-1 work fraction | 20.9%
1.7 | LHCb | 6 |  |  | lost files target 0, diskservers down over 8 hours, target < 3 | Yes |  | Andrew McNab | UK T1 SE Reliability | 1
1.7 | LHCb | 7 |  |  | <2 |  |  | Andrew McNab | LHCb No. of sites below WLCG SAM tests uptime target
1.7 | LHCb |  | 8 | 2016-12-01 | 2016-12-01 |  |  | Andrew McNab | Report on delivery to LHCb during year |  | OC Docs and review SS | completed
1.7 | LHCb |  | 9 | 2017-12-01 | 2017-12-01 |  |  | Andrew McNab | Report on delivery to LHCb during year |  | OC Docs and review SS | completed
1.7 | LHCb |  | 10 | 2018-12-01 | 2018-12-01 |  |  | Andrew McNab | Report on delivery to LHCb during year |  |  | on track
1.7 | LHCb |  | 11 | 2019-12-01 | 2019-12-01 |  |  | Andrew McNab | Report on delivery to LHCb during year |  |  | on track
1.8 | Other expts | 1 |  |  | 75% |  |  | Duncan Rand | UK T1 CPU efficiency for "other" experiments. (non-alice) | 96.3% | OK
1.8 | Other expts | 2 |  |  |  | Yes |  | Duncan Rand | Fraction of CPU time used by other experiments at UK T1.(non Alice) | 3.9% | OK
1.8 | Other expts | 3 |  |  | >1 |  |  | Duncan Rand | Number of new user groups for UK Grid.
1.8 | Other expts | 4 |  |  | 75% |  |  | Duncan Rand | UK T1 CPU efficiency for Alice. | 88.5% | OK
1.8 | Other expts | 5 |  |  | 2.5% |  |  | Duncan Rand | Fraction of CPU time used by Alice at UK T1. | 2.6% | Large reduction
1.8 | Other expts |  | 6 | 2016-12-01 | 2016-12-01 |  |  | Duncan Rand | Report on delivery to Other experiments during year |  | OC Docs and review SS | completed
1.8 | Other expts |  | 7 | 2017-12-01 | 2017-12-01 |  |  | Duncan Rand | Report on delivery to Other experiments during year |  | OC Docs and review SS | completed
1.8 | Other expts |  | 8 | 2018-12-01 | 2018-12-01 |  |  | Duncan Rand | Report on delivery to Other experiments during year |  |  | on track
1.8 | Other expts |  | 9 | 2019-12-01 | 2019-12-01 |  |  | Duncan Rand | Report on delivery to Other experiments during year |  |  | on track
Note on K10: Peter Gronbech: Roger reports on impact.
Note on K25: gronbech: “Prod” means centrally managed non-simulation production work: reconstruction, stripping etc. “User” is for user analysis jobs. Tier-2A = old T2-Ds at the moment but may expand (as we discussed in Pitlochry.)
Note on K29: gronbech: "UK work fraction" means the amount of CPU work done by the UK sites as a fraction of work by all by pledging countries, so excluding CERN, LHCb HLT, BOINC, and YANDEX. Work = time * HS06.

## WP2-3
WP2 | Tier-2 delivery to experiments and Tier-2 operations
Manager: Steve Lloyd
Task no. | Task | Metric | Target/Date | Monthly? | Owner | Description | Q418 | Comments
2.1 | ATLAS work flows | 1 | Requested Share dynamic |  | Roger Jones | Requested disk space deployed
2.1 | ATLAS work flows | 2 | 0.95 |  | Roger Jones | Production job success rates (site only metrics) - from PANDA dashboard | 0.915 | Pulled down by a very low success rate at RAL PPD
2.1 | ATLAS work flows | 3 | 0.95 | Yes? | Roger Jones | Data availability from the ATLAS dashboard; if we can automate this reliably, we can make it monthly | 0.985
2.1 | ATLAS work flows | 4 | 0.95 |  | Roger Jones | Data acceptance | 0.928
2.1 | ATLAS work flows | 5 | 0.05 |  | Roger Jones | Data loss
2.1 | User analysis and production | 6 | Requested Share dynamic |  | Roger Jones | ATLAS Available slots
2.1 | User analysis and production | 7 |  |  | Roger Jones | Atlas job success in production | 0.896
2.1 | User analysis and production | 8 | 0.95 |  | Roger Jones | ATLAS job success rates in user analysis | 0.967
2.2 | CMS group analysis | 1 |  |  | David Colling | Transfer rates to the UK Tier 2s
2.2 | CMS group analysis | 2 | 80% |  | David Colling | Site availability at the Tier-2s
2.2 | CMS group analysis | 3 | 80% |  | David Colling | Site readiness at the Tier-2s
2.2 | CMS group analysis | 4 |  |  | David Colling | Unique data loss at Tier-2s
2.2 | CMS group analysis | 5 |  |  | David Colling | Failed analysis jobs
2.2 | CMS group analysis | 6 |  |  | David Colling | Failed production jobs
2.2 | CMS group analysis | 7 |  |  | David Colling | T2 sites provide an appropriate level of resource to CMS
2.2 | CMS group analysis | 8 |  |  | David Colling | AAA data transfer performance
2.3 | LHCb Tier-2A : | 1 | >50% |  | Andrew McNab | Tier-2A : User success rate | 88.1%
2.3 | LHCb Tier-2A : | 2 | 70% |  | Andrew McNab | Tier-2A : User CPU efficiency | 0.921
2.3 | LHCb All Tier-2: | 3 | 90% |  | Andrew McNab | All Tier-2: Simulation success rate | 0.934
2.3 | LHCb All Tier-2: | 4 | 90% |  | Andrew McNab | All Tier-2: Simulation CPU efficiency | 0.98
2.3 | LHCb All sites: | 5 | 15% |  | Andrew McNab | UK Tier-2 work fraction | 0.178
2.4 | Other Expts | 1 | 5 |  | Duncan Rand | No of non LHC Vos (including ALICE) active at T2s | 20 | OK
2.4 | Other Expts | 2 | >5% |  | Duncan Rand | Fraction of CPU used by other expts | 11.6% | alice, na62, pheno, ilc, dunce
3.1 | Grid operations | 1 | Number of GridPP sites in certified status. Require 100% |  | Matt Doidge | Fraction of UK sites in Production | 100%
3.1 | Grid operations | 2 | Sum of unique VOs supported across GridPP sites - target 4 LHC + 5 other |  | Matt Doidge | Number of supported VOs | 50
3.1 | Grid operations | 3 | HEPSPEC06 used/ HEPSPEC06 available - 80% |  | Matt Doidge | Fraction of HEPSPEC used | 76%
3.1 | Grid operations | 4 | Total GridPP HEPSPEC06 nominally available at the end of the last quarter. Target WLCG pledge |  | Matt Doidge | GridPP HEPSPEC Available | 845114
3.1 | Grid operations | 5 | Total TB of disk storage nominally available from GridPP at the end of the last quarter. Target WLCG pledge |  | Matt Doidge | GridPP disk storage available | 47118
3.1 | Grid operations | 6 | Percentage of jobs run by LHC V0s processed in UK in last quarter. Target is as pledged shares (11%?) |  | Matt Doidge | UK contribution to LHC experiments | 13.44%
3.1 | Grid operations | 7 | Number of flagged tickets <3 |  | Matt Doidge | GridPP site response to tickets | 0
3.1 | Site performance | 8 | 1 |  | Matt Doidge | Scotgrid % of promised (by that time) disk available to GridPP | 207%
3.1 | Site performance | 9 | 1 |  | Matt Doidge | Scotgrid % of promised (by that time) CPU available | 256%
3.1 | Site performance | 10 | 0.95 | Yes | Matt Doidge | Scotgrid Average SAM (SLL page) availability | 83% | Failed lcg-Ca tests at ECDF, “real” work was unaffected.
3.1 | Site performance | 11 | 0.95 | Yes | Matt Doidge | Scotgrid Average SAM (SLL page) reliability | 83%
3.1 | Site performance | 12 | 0.5 |  | Matt Doidge | Scotgrid CPU utilisation (wall clock time) | 86%
3.1 | Site performance | 13 | 0.5 |  | Matt Doidge | Scotgrid CPU utilisation (CPU time) | 74%
3.1 | Site performance | 14 | 1 |  | Matt Doidge | Southgrid % of promised (by that time) disk available to GridPP | 158%
3.1 | Site performance | 15 | 1 |  | Matt Doidge | Southgrid % of promised (by that time) CPU available | 241%
3.1 | Site performance | 16 | 0.95 | Yes | Matt Doidge | Southgrid Average SAM (SLL page) availability | 89% | Birmingham had a bad time due to the tests artificially failing while their DPM was being decommissioned.
3.1 | Site performance | 17 | 0.95 | Yes | Matt Doidge | Southgrid Average SAM (SLL page) reliability | 90%
3.1 | Site performance | 18 | 0.5 |  | Matt Doidge | Southgrid CPU utilisation (wall clock time) | 78%
3.1 | Site performance | 19 | 0.5 |  | Matt Doidge | Southgrid CPU utilisation (CPU time) | 51%
3.1 | Site performance | 20 | 1 |  | Matt Doidge | Londongrid % of promised (by that time) disk available | 300%
3.1 | Site performance | 21 | 1 |  | Matt Doidge | Londongrid % of promised (by that time) CPU available | 364%
3.1 | Site performance | 22 | 0.95 | Yes | Matt Doidge | Londongrid Average SAM (SLL page) availability | 98%
3.1 | Site performance | 23 | 0.95 | Yes | Matt Doidge | Londongrid Average SAM (SLL page) reliability | 99%
3.1 | Site performance | 24 | 0.5 |  | Matt Doidge | Londongrid CPU utilisation (wall clock time) | 103%
3.1 | Site performance | 25 | 0.5 |  | Matt Doidge | Londongrid CPU utilisation (CPU time) | 69%
3.1 | Site performance | 26 | 1 |  | Matt Doidge | Northgrid % of promised (by that time) disk available to GridPP | 226%
3.1 | Site performance | 27 | 1 |  | Matt Doidge | Northgrid % of promised (by that time) CPU available | 234%
3.1 | Site performance | 28 | 0.95 | Yes | Matt Doidge | Northgrid Average SAM (SLL page) availability | 95% | Lancaster figures a bit low due to SE teething problems.
3.1 | Site performance | 29 | 0.95 | Yes | Matt Doidge | Northgrid Average SAM (SLL page) reliability | 95%
3.1 | Site performance | 30 | 0.5 |  | Matt Doidge | Northgrid CPU utilisation (wall clock time) | 119%
3.1 | Site performance | 31 | 0.5 |  | Matt Doidge | Northgrid CPU utilisation (CPU time) | 102%
Note on H22: gronbech: how do we measure this
Note on H23: gronbech: how do we measure this
Note on H26: gronbech: "UK work fraction" means the amount of CPU work done by the UK sites as a fraction of work by all by pledging countries, so excluding CERN, LHCb HLT, BOINC, and YANDEX. Work = time * HS06.

## WP3
WP3 | Grid and Experiment support
Manager: Jeremy Coles
Task no. | Task | Metric | Milestone | Baseline target date | Target/date | Owner | Completed date | Description | Q418 | Comment | Status
3.2 | Data Group | 1 |  |  | 0 | Jens Jensen |  | Number of VO requested changes not implemented in a timely fashion across whole infrastructure (1wk for small changes, 3wks for medium size, 6wks for large.) - any GridPP VO |  | No requested changes if we don't count the Birmingham EOS-only SE
3.2 | Data Group | 2 |  |  | 0 | Jens Jensen |  | Number of experiments whose data transfer rates from/to RAL to/from T2s do not meet their (realistic) requirements |  | NO DATA
3.2 | Data Group | 3 |  |  | 85% | Jens Jensen |  | FTS data transfer success rate |  | NO DATA and it;'s getting worse; ATLAS are replacing their good moniroting with prettier but useless monitoring
3.2 | Data Group | 4 |  |  | 4/Y | Jens Jensen |  | Conference paper (CHEP, AHM, or similar (or better)) produced each year describing GridPP developments and innovations in data management and storage area |  | 0
3.2 | Data Group | 5 |  |  | 4/Q | Jens Jensen |  | Engage with storage and data management experts within WLCG/EGI/EMI/NGS or similar, or industry, to reinforce GridPP's recognised competence in this area (talks given, meetings, virtual meetings) |  | Good interactions with DOMA WGs Also IRIS counts, trial of new VOs using GridPP
3.2 | Data Group | 6 |  |  | 0 | Jens Jensen |  | Number of incidents not resolved within 1wk after being reported on list |  | 0
3.2 | Data Group | 7 |  |  | 5 | Jens Jensen |  | Number of blog posts | 0 | 0
3.2 | Data Group |  | 8 | 2017-01-31 | 2017-01-31 | Jens Jensen |  | Deploy and test "solution" for T2C storage (e.g. cache+local storage) |  |  | completed
3.2 | Data Group |  | 9 | 2016-09-30 | 2016-09-30 | Brian Davies |  | Present GridPP work at data workshop at CERN |  |  | completed
3.2 | Data Group |  | 10 | 2016-12-31 | 2016-12-31 | Sam Skipsey |  | Develop GridPP as a "data einfrastructure" in the context of UKT0 |  |  | completed
3.2 | Data Group |  | 11 | 2016-11-30 | 2016-11-30 | Brian Davies |  | Data transfer/management comparison with climate |  |  | completed
3.2 | Data Group |  | 12 |  | 2018-04-01 | Jens Jensen |  | All major T2s dual stacked |  |  | delayed
3.3 | Security | 1 |  |  |  | Ian Neilson |  | Number of Tier 2 security incidents in the last quarter | 0
3.3 | Security | 2 |  |  |  | Ian Neilson |  | Number of sites responding poorly to a security incident in last quarter | 0
3.3 | Security |  | 3 | 2017-12-31 | 2017-12-31 | Ian Neilson |  | Security Service Challenge |  | Ian Neilson performed a Security Communication Challenge in Q117. Problems with two sites were fixed. Ian's departure in July 2017 put plans for a fuller security challenge on hold. We will perform this once the replacement Security Officer is in post - probably in Q218. | delayed
3.3 | Security |  | 4 | 2017-06-01 | 2017-06-01 | Ian Neilson |  | UK HEP Sysman Security Training/Workshop | 2017-06-13 | Milestone 3.3.3 has been delayed, but in the meantime we achieved milestone 3.3.4 early. Ian Neilson organised a one-day security workshop for HEP SYSMAN at RAL concentrating on the topic of IPv6 security | completed
3.3 | Security |  | 5 | 2019-12-31 | 2019-12-31 | D.P.Kelsey |  | Security plans for the future beyond end of GridPP5 |  |  | on track
3.4 | NGI | 1 |  |  |  | Ian Collier |  | UK CPU and storage delivered to EGI
3.4 | NGI | 2 |  |  |  | Ian Collier |  | Monthly timesheets complete by 10th of each month
3.4 | NGI | 3 |  |  |  | Ian Collier |  | GridPP staff PM delivered as required
3.4 | NGI | 4 |  |  | 95% | Ian Collier |  | GOCDB Availability | 99.99%
3.4 | NGI | 5 |  |  | 95% | Ian Collier |  | APEL Availability | 100%
3.4 | Tier-1 expt support | 6 |  |  |  | Pete Gronbech |  | ATLAS reporting to T1 expt Liaison and resource meetings
3.4 | Tier-1 expt support | 7 |  |  |  | Pete Gronbech |  | CMS reporting to T1 expt Liaison and resource meetings
3.4 | Tier-1 expt support | 8 |  |  |  | Pete Gronbech |  | LHCb reporting to T1 expt Liaison and resource meetings
3.4 | Ganga and user support | 9 |  |  |  | Ulrik Egede |  | LHCb Ganga: Unit testing of code within area of responsibility |  | These three metrics suspended as funding has been spent up! | Will go once effort is no longer funded.
3.4 | Ganga and user support | 10 |  |  |  | Ulrik Egede |  | LHCb Ganga: Provide new erleases of Ganga
3.4 | Ganga and user support | 11 |  |  |  | Ulrik Egede |  | LHCb Ganga: Provide support for new communities
3.4 | Ganga and user support | 12 |  |  |  | Pete Gronbech |  | Number of new user groups using the T1/UK Grid
3.4 | Ganga and user support | 13 |  |  |  | Pete Gronbech |  | Summary of Work done by support posts |  | Full report from Dan in the main report
3.4 | Ganga and user support | 14 |  |  |  | Pete Gronbech |  | Summary of Work done by support posts |  | Full report by Janusz in main report.
Note on J18: gronbech: Green <=1, Amber 2 or 3 and Red >=4
Note on J19: gronbech: Green 0, Amber 1, Red >=2

## WP4
WP4 | Management & Impact
Manager: Dave Britton
Task no. | Task | Metric | Milestone | Baseline target date | Target/date | Owner | Description | Date Complete | Comment | Status
4.1 | Planning |  | 1 | 2016-04-01 | 2016-04-01 | Dave Britton | Financial plan for GridPP5 established | 2016-03-01 |  | completed
4.1 | Planning |  | 2 | 2016-06-01 | 2016-06-01 | Pete Gronbech | Draft ProjectMap for GridPP5. GridPP5 ProjectMap exists with >80% of areas defined | 2016-06-01 |  | completed
4.1 | Planning |  | 3 | 2016-08-01 | 2016-08-01 | Pete Gronbech | Final project map for GridPP5. More than >95% of areas defined | 2016-08-01 | Completed | completed
4.1 | Planning |  | 4 | 2015-06-01 | 2015-06-01 | Pete Gronbech | Quarterly reporting system agreed for Tier-1 | 2016-08-01 | Completed | completed
4.1 | Planning |  | 5 | 2016-08-01 | 2016-08-01 | Pete Gronbech | Quarterly reporting system agreed for other areas | 2016-10-01 | completed | completed
4.1 | Planning | 6 |  |  | Quarterly | Pete Gronbech | Hardware allocation made by T1 resource board for next period |  | Meeting held 30.8.17
4.1 | Planning |  | 7 | 2015-12-01 | 2015-12-01 | Pete Gronbech | T2 staff grants issued for GridPP5 | 2017-01-01 | Completed in Jan 2016 | completed
4.1 | Planning |  | 8 | 2017-09-01 | 2017-09-01 | Pete Gronbech | Allocations calculated for Tier-2 hardware grants | 2016-11-01 | T2 h/w allocation made early in FY16 not 17 | completed
4.1 | Planning |  | 9 | 2017-10-01 | 2017-10-01 | Pete Gronbech | Grants for Tier-2 hardware issued | 2016-12-01 | All grants were issued 14.12.16 | completed
4.1 | Planning |  | 10 | 2019-09-02 | 2019-09-02 | Pete Gronbech | Allocations calculated for Tier-2 hardware grants | 2018-08-01 | T2 h/w allocation made early in FY18 | completed
4.1 | Planning |  | 11 | 2019-10-03 | 2019-10-03 | Pete Gronbech | Grants for Tier-2 hardware issued | 2018-10-01 | Issued in Oct 2018 | completed
4.1 | Planning |  | 12 | 2019-04-01 | 2019-04-01 | Dave Britton | Post-GridPP5 planning initiated |  |  | on track
4.2 | Execution | 1 |  |  | <6 | Pete Gronbech | Number of vacant posts |  | 3.78
4.2 | Execution | 2 |  |  |  | Pete Gronbech | 100% of quarterly reports received by Project Manager within 2 months of quarter end. |  | Failed in Q3 18
4.2 | Execution | 3 |  |  |  | Pete Gronbech | ProjectMap is updated within 3 months of end of each quarter
4.2 | Execution | 4 |  |  |  | Pete Gronbech | Financial model updated within 1 month of changes
4.2 | Execution | 5 |  |  | 40 per year | Pete Gronbech | Weekly video/phone PMB meetings |  | On track
4.2 | Execution | 6 |  |  | 3 / year | Pete Gronbech | Face to face PMB meetings |  | One at each GridPP collaboration meeting (ie 2/ year) + T1 review
4.2 | Execution | 7 |  |  | 1 per year | Pete Gronbech | CB meetings |  | On track
4.2 | Execution | 8 |  |  | 20 per year | Pete Gronbech | Ops Team meetings |  | On track
4.2 | Execution | 9 |  |  | 2 per year | Pete Gronbech | Collaboration meetings |  | On track
4.2 | Execution |  | 10 |  |  | Pete Gronbech | OC papers submitted 2 weeks before meeting |  |  | completed
4.2 | Execution |  | 11 | 2016-09-30 | 2016-09-30 | Pete Gronbech | WLCG pledges updated |  | Submission date was moved to November 2016 | completed
4.2 | Execution |  | 12 | 2016-12-31 | 2016-12-31 | Pete Gronbech | Year 1 review of service to experiments |  |  | completed
4.2 | Execution |  | 13 | 2017-09-30 | 2017-09-30 | Pete Gronbech | WLCG pledges updated |  |  | completed
4.2 | Execution |  | 14 | 2017-12-31 | 2017-12-31 | Pete Gronbech | Year 2 review of service to experiments |  |  | completed
4.2 | Execution |  | 15 | 2018-09-30 | 2018-09-30 | Pete Gronbech | WLCG pledges updated |  |  | completed
4.2 | Execution |  | 16 | 2018-12-31 | 2018-12-31 | Pete Gronbech | Year 3 review of service to experiments |  |  | on track
4.2 | Execution |  | 17 | 2019-09-30 | 2019-09-30 | Pete Gronbech | WLCG pledges updated |  |  | on track
4.2 | Execution |  | 18 | 2019-12-31 | 2019-12-31 | Pete Gronbech | Year 4 review of service to experiments |  |  | on track
4.3 | Outreach | 1 |  |  | 4 per year | Tom Whyntie | Number of events GridPP attends with stand/posters/talks | 1 | Total in last year 5
4.3 | Outreach | 2 |  |  | 10 per year | Tom Whyntie | Number of GridPP publications | 1 | Total over the last year 4
4.3 | Outreach | 3 |  |  | One per month | Tom Whyntie | Number of articles on GridPP web site | 5 | Total over last year 19
4.3 | Outreach | 4 |  |  | 1 per year | Tom Whyntie | Number of GridPP press releases | 1 | Total for year 1
4.3 | Outreach | 5 |  |  | 5 per year | Tom Whyntie | Number of press articles about GridPP | 7 | Total for last year 8
4.3 | Outreach | 6 |  |  | 1 per year | Tom Whyntie | Number of KE exploration meetings held | 0 | Total over last year 3
4.3 | Outreach | 7 |  |  | 10 | Tom Whyntie | Number of non-GridPP funded Groups who use GridPP hardware | 24 | Total for over last year 4
4.3 | Outreach |  | 8 | 2016-12-31 | 2016-12-31 | Tom Whyntie | KE sections of GridPP website updated |  |  | on track
4.3 | Outreach |  | 9 | 2017-12-31 | 2017-12-31 | Tom Whyntie | KE sections of GridPP website updated |  |  | on track
4.3 | Outreach |  | 10 | 2018-12-31 | 2018-12-31 | Tom Whyntie | KE sections of GridPP website updated |  |  | on track
4.3 | Outreach |  | 11 | 2019-12-31 | 2019-12-31 | Tom Whyntie | KE sections of GridPP website updated |  |  | on track
Could move to UK-T0
recognise how the role has evolved.

## Milestones&Deliverables
Milestones (including Deliverables) Table
No. |  | Work Package | Description | Baseline Date | Target |  | Completion Date | Status | Delay due to |  | Affects Critical Path? | See Note
[5 empty] | Date | Change |  |  | UK | Other
1.1 | 8 | WP1 | Strategic and operations plan agreed | 2016-06-01 | 2016-10-01 | ↑ | 2016-10-01 | Completed
1.1 | 9 | WP1 | GridPP review of operation (biennial) | 2016-11-01 | 2016-11-01 | ↔ |  | Completed
1.1 | 10 | WP1 | Strategic and operations plan agreed | 2017-06-01 | 2017-06-01 | ↔ |  | Completed
1.1 | 11 | WP1 | Strategic and operations plan agreed | 2018-06-01 | 2018-06-01 | ↔ |  | Completed
1.1 | 12 | WP1 | GridPP review of operation (biennial) | 2018-10-01 | 2018-10-01 | ↔ |  | Completed
1.1 | 13 | WP1 | Strategic and operations plan agreed | 2019-06-01 | 2019-06-01 | ↔ |  | on track
1.4 | 1 | WP1 | Produce the purchasing plan | 2016-06-01 | 2016-06-01 | ↔ | 2016-10-01 | completed
1.4 | 2 | WP1 | FY16 Capacity order placed | 2016-11-01 | 2016-11-01 | ↔ | 2017-02-01 | completed
1.4 | 3 | WP1 | FY16 Purchase in production | 2017-04-01 | 2017-04-01 | ↔ |  | completed
1.4 | 4 | WP1 | Tier-1 WLCG MoU commitments met | 2017-05-01 | 2017-05-01 | ↔ |  | completed
1.4 | 5 | WP1 | Produce the purchasing plan | 2017-06-01 | 2017-06-01 | ↔ |  | completed
1.4 | 6 | WP1 | FY17 Capacity order placed | 2017-11-01 | 2017-11-01 | ↔ |  | completed
1.4 | 7 | WP1 | FY17 Purchase in production | 2018-04-01 | 2018-04-01 | ↔ |  | completed
1.4 | 8 | WP1 | Tier-1 WLCG MoU commitments met | 2018-05-01 | 2018-05-01 | ↔ |  | completed
1.4 | 9 | WP1 | Produce the purchasing plan | 2018-06-01 | 2018-06-01 | ↔ |  | completed
1.4 | 10 | WP1 | FY18 Capacity order placed | 2018-11-01 | 2018-11-01 | ↔ |  | completed
1.4 | 11 | WP1 | FY18 Purchase in production | 2019-04-01 | 2019-04-01 | ↔ |  | on track
1.4 | 12 | WP1 | Tier-1 WLCG MoU commitments met | 2019-05-01 | 2019-05-01 | ↔ |  | on track
1.4 | 13 | WP1 | Produce the purchasing plan | 2019-06-01 | 2019-06-01 | ↔ |  | on track
1.4 | 14 | WP1 | FY19 Capacity order placed | 2019-11-01 | 2019-11-01 | ↔ |  | on track
1.4 | 15 | WP1 | FY19 Purchase in production | 2020-04-01 | 2020-04-01 | ↔ |  | on track
1.4 | 16 | WP1 | Tier-1 WLCG MoU commitments met | 2020-05-01 | 2020-05-01 | ↔ |  | on track
1.5 | 6 | WP1 | Report on delivery to Atlas during year | 2016-12-01 | 2016-12-01 | ↔ | 2016-12-01 | completed
1.5 | 7 | WP1 | Report on delivery to Atlas during year | 2017-12-01 | 2017-12-01 | ↔ |  | completed
1.5 | 8 | WP1 | Report on delivery to Atlas during year | 2018-12-01 | 2018-12-01 | ↔ |  | on track
1.5 | 9 | WP1 | Report on delivery to Atlas during year | 2019-12-01 | 2019-12-01 | ↔ |  | on track
1.6 | 7 | WP1 | Report on delivery to CMS during year | 2016-12-01 | 2016-12-01 | ↔ |  | completed
1.6 | 8 | WP1 | Report on delivery to CMS during year | 2017-12-01 | 2017-12-01 | ↔ |  | completed
1.6 | 9 | WP1 | Report on delivery to CMS during year | 2018-12-01 | 2018-12-01 | ↔ |  | on track
1.6 | 10 | WP1 | Report on delivery to CMS during year | 2019-12-01 | 2019-12-01 | ↔ |  | on track
1.7 | 8 | WP1 | Report on delivery to LHCb during year | 2016-12-01 | 2016-12-01 | ↔ |  | completed
1.7 | 9 | WP1 | Report on delivery to LHCb during year | 2017-12-01 | 2017-12-01 | ↔ |  | completed
1.7 | 10 | WP1 | Report on delivery to LHCb during year | 2018-12-01 | 2018-12-01 | ↔ |  | on track
1.7 | 11 | WP1 | Report on delivery to LHCb during year | 2019-12-01 | 2019-12-01 | ↔ |  | on track
1.8 | 6 | WP1 | Report on delivery to Other experiments during year | 2016-12-01 | 2016-12-01 | ↔ |  | completed
1.8 | 7 | WP1 | Report on delivery to Other experiments during year | 2017-12-01 | 2017-12-01 | ↔ |  | completed
1.8 | 8 | WP1 | Report on delivery to Other experiments during year | 2018-12-01 | 2018-12-01 | ↔ |  | on track
1.8 | 9 | WP1 | Report on delivery to Other experiments during year | 2019-12-01 | 2019-12-01 | ↔ |  | on track
3.2 | 8 | WP3 | Deploy and test "solution" for T2C storage (e.g. cache+local storage) | 2017-01-31 | 2017-01-31 | ↔ |  | completed
3.2 | 9 | WP3 | Present GridPP work at data workshop at CERN | 2016-09-30 | 2016-09-30 | ↔ |  | completed
3.2 | 10 | WP3 | Develop GridPP as a "data einfrastructure" in the context of UKT0 | 2016-12-31 | 2016-12-31 | ↔ |  | completed
3.2 | 11 | WP3 | Data transfer/management comparison with climate | 2016-11-30 | 2016-11-30 | ↔ |  | completed
3.2 | 12 | WP3 | All major T2s dual stacked |  | 2018-04-01 |  |  | delayed
3.3 | 3 | WP3 | Security Service Challenge | 2017-12-31 | 2017-12-31 | ↔ |  | delayed
3.3 | 4 | WP3 | UK HEP Sysman Security Training/Workshop | 2017-06-01 | 2017-06-01 | ↔ |  | completed
3.3 | 5 | WP3 | Security plans for the future beyond end of GridPP5 | 2019-12-31 | 2019-12-31 | ↔ |  | on track
4.1 | 1 | WP4 | Financial plan for GridPP5 established | 2016-04-01 | 2016-04-01 | ↔ | 2016-03-01 | completed
4.1 | 2 | WP4 | Draft ProjectMap for GridPP5. GridPP5 ProjectMap exists with >80% of areas defined | 2016-06-01 | 2016-06-01 | ↔ | 2016-06-01 | completed
4.1 | 3 | WP4 | Final project map for GridPP5. More than >95% of areas defined | 2016-08-01 | 2016-08-01 | ↔ | 2016-08-01 | completed
4.1 | 4 | WP4 | Quarterly reporting system agreed for Tier-1 | 2015-06-01 | 2015-06-01 | ↔ | 2016-08-01 | completed
4.1 | 5 | WP4 | Quarterly reporting system agreed for other areas | 2016-08-01 | 2016-08-01 | ↔ | 2016-10-01 | completed
4.1 | 7 | WP4 | T2 staff grants issued for GridPP5 | 2015-12-01 | 2015-12-01 | ↔ | 2017-01-01 | completed
4.1 | 8 | WP4 | Allocations calculated for Tier-2 hardware grants | 2017-09-01 | 2017-09-01 | ↔ | 2016-11-01 | completed
4.1 | 9 | WP4 | Grants for Tier-2 hardware issued | 2017-10-01 | 2017-10-01 | ↔ | 2016-12-01 | completed
4.1 | 10 | WP4 | Allocations calculated for Tier-2 hardware grants | 2019-09-02 | 2019-09-02 | ↔ | 2018-08-01 | completed
4.1 | 11 | WP4 | Grants for Tier-2 hardware issued | 2019-10-03 | 2019-10-03 | ↔ | 2018-10-01 | completed
4.1 | 12 | WP4 | Post-GridPP5 planning initiated | 2019-04-01 | 2019-04-01 | ↔ |  | on track
4.2 | 10 | WP4 | OC papers submitted 2 weeks before meeting | 0 | 0 | ↔ |  | completed
4.2 | 11 | WP4 | WLCG pledges updated | 2016-09-30 | 2016-09-30 | ↔ |  | completed
4.2 | 12 | WP4 | Year 1 review of service to experiments | 2016-12-31 | 2016-12-31 | ↔ |  | completed
4.2 | 13 | WP4 | WLCG pledges updated | 2017-09-30 | 2017-09-30 | ↔ |  | completed
4.2 | 14 | WP4 | Year 2 review of service to experiments | 2017-12-31 | 2017-12-31 | ↔ |  | completed
4.2 | 15 | WP4 | WLCG pledges updated | 2018-09-30 | 2018-09-30 | ↔ |  | completed
4.2 | 16 | WP4 | Year 3 review of service to experiments | 2018-12-31 | 2018-12-31 | ↔ |  | on track
4.2 | 17 | WP4 | WLCG pledges updated | 2019-09-30 | 2019-09-30 | ↔ |  | on track
4.2 | 18 | WP4 | Year 4 review of service to experiments | 2019-12-31 | 2019-12-31 | ↔ |  | on track
4.3 | 8 | WP4 | KE sections of GridPP website updated | 2016-12-31 | 2016-12-31 | ↔ |  | on track
4.3 | 9 | WP4 | KE sections of GridPP website updated | 2017-12-31 | 2017-12-31 | ↔ |  | on track
4.3 | 10 | WP4 | KE sections of GridPP website updated | 2018-12-31 | 2018-12-31 | ↔ |  | on track
4.3 | 11 | WP4 | KE sections of GridPP website updated | 2019-12-31 | 2019-12-31 | ↔ |  | on track
Milestones (M) and Deliverables (D)
Items within this table should map directly from the detailed project shedule
Notes
1
DESCRIPTION OF COLUMNS
· Baseline date = Date set by the PMP
· Target date = Planned date, expected completion date
· Target date change = Movement in the change of the target date compared to the last Oversight Committee meeting.
Key: ↔ = no change, ↑ = target date delayed, ↓ = target date brought forward e.g. time has been made up/recovered
· Completion Date = Date Milestone was achieved
· Status = Commentary on progress, update