## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q217 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 240.3% | 305.8% | 305.8% | 281.5% | 281.5% | 281.5% | 233.5% | 233.5% | 233.5% | 151.9% | 151.9% | 151.9% |  |  | 0% | 225.7% | 232.7% | 232.7%
.x.2 | % of promised (by that time) CPU available | 100% | 373.7% | 363.3% | 363.3% | 160% | 275.9% | 275.9% | 375.1% | 375.1% | 375.1% | 450.5% | 450.5% | 450.5% |  |  | 0% | 293% | 339.2% | 339.2%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 95% | 100% | 100% | 100% | 100% | 100% | 97% | 99% | 100% | 99% | 100% |  |  |  | 100% | 97.75% | 99.75%
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 95% | 100% | 100% | 100% | 100% | 100% | 97% | 100% | 100% | 99% | 100% |  |  |  | 100% | 97.75% | 100%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 61.58% | 91.56% | 47.37% | 95.11% | 71.28% | 82.51% | 52.53% | 54.57% | 56.6% | 61.43% | 71.7% | 93.14% |  |  |  | 67.07% | 71.59% | 71.32%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 42.4% | 69.11% | 33.79% | 80.06% | 60% | 72.23% | 62.99% | 54.57% | 56.6% | 53.04% | 63.15% | 78.93% |  |  |  | 59.62% | 61.08% | 62.17%
.x.3/.4
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q217
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2017 Apr | 2017 May | 2017 Jun | Total |  |  | 2017 Apr | 2017 May | 2017 Jun | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 12457779.7342 | 9572608.6908 | 3799465.9325 | 25829854 |  | UKI-LT2-Brunel | 17873765.743 | 13052232.7348 | 5286021.4452 | 36212020
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 28520820.9359 | 32353211.6028 | 34501899.776 | 95375932 |  | UKI-LT2-IC-HEP | 35258181.4325 | 36749149.9839 | 36930045.9075 | 108937377
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 16044868.5112 | 21151541.8637 | 18881420.6094 | 56077831 |  | UKI-LT2-QMUL | 16044962.121 | 21151561.8363 | 18881425.5413 | 56077949
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 19776010.9623 | 22220555.0648 | 23508302.6137 | 65504869 |  | UKI-LT2-RHUL | 23807630.5165 | 26356898.7677 | 27134814.0037 | 77299343
[8 empty] | Total | 76799480.1436 | 85297917.2221 | 80691088.9316 | 242788486 |  | Total | 92984539.813 | 97309843.3227 | 88232306.8977 | 278526689
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1400 | 9632.812 | 457.8006 | 363.3% | 305.8% | 19.57% | 14.12% | 25829854 | 10.64% | 2184 | 76440000 | 33.79% | 47.37% | 71.33%
UKI-LT2-IC-HEP | 60456 | 3699 | 21915.766 | 1313.8219 | 275.9% | 281.5% | 33.81% | 37.31% | 95375932 | 39.28% | 2184 | 132035904 | 72.23% | 82.51% | 87.55%
UKI-LT2-QMUL | 45363 | 3316 | 12094.921 | 1420.211 | 375.1% | 233.5% | 25.37% | 33.44% | 56077831 | 23.1% | 2184 | 99072792 | 56.6% | 56.6% | 100% | Slurm accounting problem whereby CPU time = wall time
UKI-LT2-RHUL | 38000 | 1500 | 8434.349 | 987.6466 | 450.5% | 151.9% | 21.25% | 15.13% | 65504869 | 26.98% | 2184 | 82992000 | 78.93% | 93.14% | 84.74%
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 178819 | 9915 | 52714.598 | 4260.48 | 339.2% | 232.7% | 100% | 100% | 242788486 | 100% | 2184 | 390540696 | 62.17% | 71.32% | 87.17%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 3845 | 45949 | 1438
UKI-LT2-IC-HEP | 6380 | 60416 | 3592
UKI-LT2-QMUL | 4248 | 46797 | 3394
UKI-LT2-RHUL | 3832 | 38408 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 191570 | 9884 |  | 0
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx
Note on E34: gronbech:Gstat displays SI2000 so this needs converting to HS06

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q217
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cepc | cernatschool.org | comet.j-parc.jp | cms | dteam | dune | dzero | enmr.eu | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | icecube | ilc | ipv6.hepix.org | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | neiss.org.uk | ops | pheno | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.gear.cern.ch | vo.helio-vo.eu | vo.landslides.mossaic.org | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 22
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17
Total | 0 | 4 | 4 | 2 | 0 | 1 | 3 | 1 | 4 | 4 | 4 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 3 | 1 | 4 | 0 | 4 | 3 | 3 | 4 | 1 | 0 | 4 | 4 | 4 | 1 | 0 | 0 | 4 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 75
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | lsst | cernatschool.org | vo.moedal.org | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.311 |  | 0.335 |  |  |  | 0.066 | 999.521 |  | 31.755 | 0.017 | 0.002 |  |  |  |  | 1.491 | [5 empty] | 0.544 | 0.006 |  |  |  |  | 0.202 | [6 empty] | 0.018 |  | 0 |  |  |  |  | 1034.268 | 14.57% | 0.2893%
UKI-LT2-IC-HEP |  | 30.48 | 0 |  | 0 |  | 0 | 1786.342 |  | 7.071 |  |  |  |  | 256.5 |  |  |  | 0 | [15 empty] | 36.155 |  |  | 202.9 |  |  |  | 45.711 | 2365.159 | 33.32% | 13.33%
UKI-LT2-QMUL |  | 106 | 0.648 |  |  | 0 |  | 3.3 |  | 2300 | 0.052 |  |  |  | 139 |  | 0.673 | 0.0068 |  |  |  | 0.016 | 0.014 | 0.0036 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 13 |  |  |  | 0 | 0.109 | 0.044 | 0.0081 |  | 2562.8987 | 36.11% | 4.706%
UKI-LT2-RHUL | 0 |  | 0.42 |  |  |  |  | 1.621 |  | 1133 | 0.015 | 0.001 |  |  |  |  | 0.19 | [5 empty] | 0.001 | 0.006 | [6 empty] | 0.009 | 0 | [5 empty] | 0 |  |  |  |  | 1135.263 | 16% | 0.05655%
Total | 0.311 | 136.48 | 1.403 | 0 | 0 | 0 | 0.066 | 2790.784 | 0 | 3471.826 | 0.084 | 0.003 | 0 | 0 | 395.5 | 0 | 2.354 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.559 | 0.0156 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.009 | 0 | 0.019 | 13 | 36.155 | 0.018 | 0 | 202.9 | 0.109 | 0.044 | 0.0081 | 45.711 | 7097.5887 | 100% | 6.192%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q217
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.85 | 0.85 | 0.85 | 0.15 | 0.15 | 0.15
| Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
| P. Hobson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| B.Green/Tom | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 6.9 | 6.9 | 6.9 | 1.85 | 1.85 | 1.85

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q217
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | There is a new NAT gateway which should hopefully improve xrootd remote reads.
UKI-LT2-IC-HEP | Worker nodes upgraded to Centos7 and Singularity containers. Preparing to upgrade dCache to Centos7.
UKI-LT2-QMUL | Both attended GridPP38 in Sussex. Gave presentation on QMUL cluster status. Setup Proxmox VMhost and transferred VMs to it. Decommissioned old vmhosts and put them into production as compute nodes. Used Proxmox vmhosts for IPv6 training at the WLCG meeting. Terry Froy attended WLCG meeting in Manchester and contributed to the IPv6 training session. Finalised tender document for new storage and published it. Bought new rack to house new storage. Bought retail GPU (Nvidia GTX1080) for price performance comparison with enterprise GPUs. Dan Traynor attended HEP-SYSMAN meeting. Did extensive performance tests of ZFS in preparation for new storage and presented results at HEP-SYSMAN meeting. Researched SSDs technology and conducted extensive performance tests. Presented a summary to HEP-SYSMAN.
UKI-LT2-RHUL | Site has received IPv6 address allocation. PerfSONAR host upgraded to Centos7. EMI to UMD migrations.
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes