## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q2 2017 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 178% | 177% | 176.6% | 152% | 152% | 173.5% | 156% | 220% | 220.5% | 136% | 136% | 136.2% | 187.9%
.x.2 | % of promised (by that time) CPU available | 100% | 443% | 443% | 442.9% | 277% | 285% | 280.2% | 314% | 314% | 313.7% | 334% | 334% | 334.4% | 346.2%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 97% | 86% | 100% | 97% | 100% | 100% | 98% | 100% | 100% | 97% | 74% | 90%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 97% | 86% | 100% | 97% | 100% | 100% | 99% | 100% | 100% | 97% | 74% | 90%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 73% | 74% | 61.62% | 85% | 90% | 73.02% | 96% | 95% | 98.28% | 69% | 80% | 89.44% | 79.26%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 59% | 64% | 53.3% | 77% | 82% | 63.45% | 85% | 85% | 87.11% | 63% | 71% | 82.15% | 69.78%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2017
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | umd4 | 10Gb/s | 10Gb/s | DPM |  | Site | 2017-04-01 | 2017-05-01 | 2017-06-01 | Total |  | Site | 2017-04-01 | 2017-05-01 | 2017-06-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 16268623 | 21286640 | 16089475 | 53644738 |  | Lancaster | 19698790 | 22492411 | 19824044 | 62015245
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 11242376 | 11491693 | 7281203 | 30015272 |  | Liverpool | 14196295 | 12505327 | 7841740 | 34543362
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 21889355 | 31263340 | 30882641 | 84035336 |  | Manchester | 27310559 | 34230550 | 33263736 | 94804845
[7 empty] | Sheffield | 4203382 | 6345226 | 8397425 | 18946033 |  | Sheffield | 4812236 | 6881669 | 8933852 | 20627757
[7 empty] | Total CPU hrs | 49400354 | 64041673 | 54253319 | 167695346 |  | Total | 66017880 | 76109957 | 69863372 | 211991209
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2017/1/2017/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 46080 | 2208 | 10405 | 1250 | 442.9% | 176.6% | 37.63% | 30.44% | 53644738 | 28.74% | 2184 | 100638720 | 53.3% | 61.62%
Liverpool | 21660 | 1400 | 7729 | 807 | 280.2% | 173.5% | 17.69% | 19.3% | 30015272 | 16.08% | 2184 | 47305440 | 63.45% | 73.02%
Manchester | 44170 | 3115 | 14080 | 1413 | 313.7% | 220.5% | 36.07% | 42.94% | 84035336 | 45.03% | 2184 | 96467280 | 87.11% | 98.28%
Sheffield | 10560 | 531 | 3158 | 390 | 334.4% | 136.2% | 8.623% | 7.32% | 18946033 | 10.15% | 2184 | 23063040 | 82.15% | 89.44%
Totals | 122470 | 7254 | 35372 | 3860 | 346.2% | 187.9% | 100% | 100% | 186641379 | 100% | 2184 | 267474480 | 69.78% | 79.26%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 46080 | 2851 | NA | Lancaster
Liverpool | 2018 | 21660 | 1400 | NA | Liverpool
Manchester | 4480 | 44170 | 3506 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 10498 | 122470 | 8288 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2017
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | na48 | neiss | ops | pheno | vo.skatelescope.eu | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1 | 0 |  | 1 |  |  | 1 |  |  | 1 |  | 14
Liverpool | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 33
Manchester | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 24
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 0 | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 |  |  | 1 | 1 | 1 | 1 |  | 20
Total | 3 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 1 |  | 2 | 4 | 2 |  | 2 | 4 | 1 |  | 2 | 2 | 1 |  | 4 | 3 |  | 4 | 1 | 1 | 4 | 2 | 3 | 4 |  | 91
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1450 | 0 | 17 | 5 | 1472 | 1.155% | 1.495%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3620.24 | 0.57 | 179 | 12.47 | 3920.46 | 4.566% | 4.898%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2017
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | bar: GridPP Funded Month 1 to GridPP Funded Month 3
M. Doidge | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| P. Love | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
Liverpool | S. Jones | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| R. Fay | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
| J. Bland | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Manchester | A. Forti | bar: GridPP Funded Month 1 to GridPP Funded Month 3
R. Frank | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| A. McNab | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Sheffield | E. Korolkova | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| M. Robinson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | EGI Funded Month 1: 0.5; EGI Funded Month 2: 0.5; EGI Funded Month 3: 0.5
Manchester | A. Forti | bar: Unfunded Month 1 to Unfunded Month 3

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q2
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Deployment of new kit Retirement of old kit IPv6 testing Tarball development C7 groundwork | Kit deployed, easing into production Old kit being phased out Tracked fault in routing Expanding features Well prepared for centos 7 |  |  | Phasing kit in is taking a while None Delaying v6 rollout further Lack of central repo a problem! Broke everything during cluster rebuild.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Still need a new SE headnode – current one out of warranty. Need new CE as well. NFS server struggling under load |  |  | Not showing its age since updated, will set up test SE next quarter. Looking at HTCondor Need to fix stagein/out scripts.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Tarball Work Deployment Ipv6 tested Many updates and upgrades |  |  | 30/6/17 |  | Umd4 sl6 tarballs, centos 7 tarball updated New kit deployed (took a lot of time) Traced problems with routing Up to date! Increased stability
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | New CE Production centos7 Dualstack SE |  |  | 30/9/2017 |  | Increased reliability C7 ready IPv6 ready
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q2
Reported by | S Jones, J Bland, R Fay
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | More “Site Benefits in Kind.” Purchases and upgrades Routines Software Development Outreach, publications, research | Wholesale refurb of server room (cabs, power, aircon, all wiring). Provided by Liverpool facilities dept. Purchased storage now on-line, ZFS ,DPM Storage server, adding ~ 250 TB. Mostly ATLAS. Rolling upgrades of DPM pool nodes to DPM 1.9.0 on Centos 7. Routine sys admin (admin of 3 clusters plus storage, tickets, VO support, VOMS documentation, security certificates, GOCDB Maint, HW & SW maint, space management, confirmation of benchmark calculations/rebenchmarking, kernel security changes, removal of EMI artefacts, host cert renewal....) Improved Fallow (mcore drain tool) algorithm. Better version of Site Layout Application. Formal release papers provided for new “wn” (was emi-wn) package for Centos7. Document the YAIMless build of Centos7, testing at RHUL. Two papers, funded by GridPP research, accepted for CHEP, one on VAC migration, the other on next generation monitoring. Also peer reviewed two CHEP publications by other parties. Talk on Efficiency and tuning at RAL HepSysMan. |  | Large but temporary effect on throughput hits acc. figures. Not on-line until ~ mid Aug. Gradual progress.... Solved ZFS config issues. On-line None to speak of. Centos7 cluster so far underused. Need more customers to use this resource to test C7 migration. None
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | Ipv6 Medium sized site Risks associated with cluster room refurb. |  | Need to work with external supplier (CSD) Plotting course as “medium sized site.” Standard engineering contingencies, e.g. isolating systems at risk, clean working areas, close comms with Project Manager, replanning etc. But it's a complex operation and some services have had to be stopped.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Continue adoption of Centos7, documentation Continue adoption of Ipv6, documentation CHEP Papers on VAC testing, monitoring, published Some HW purchases for GPP5 Continue adoption of Centos7, documentation Continue GridPP5 HW purchases Progress on new cooling from Facilities Convert site to Puppet 3 Plans to continue with Tom Whyntie's user guide VAC Superslot/Multicore tests |  | '31/03/2017 '31/03/2017 '31/03/2017 '31/03/2017 '30/06/2017 '30/06/2017 '30/06/2017 '30/06/2017 '30/06/2017 '30/06/2017 |  | DONE, incl docs In progress Published Done and installed In progress In progress (Planning) In progress In progress Start delayed Start delayed. Will expedite.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Continue adoption of Ipv6, documentation Continue adoption of Centos7 Continue GridPP5 HW purchases Progress on new cooling from facilities Convert site to Puppet 3 Plans to continue with Tom Whyntie's user guide VAC Superslot/Multicore tests |  | '30/09/2017 '30/09/2017 '30/09/2017 '30/09/2017 '30/09/2017 '30/09/2017 '30/09/2017 |  | Nodes using IPV6 Increased num of C7 nodes CPU to be bought next Move into new cluster room (Aug) Continual progress Not sure Bring forward, e.g. next week.

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q2
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | New wn's purchased and installed. The old machines have been decommissioned. New version of personar installed. Provided CPU resources for LZ during LZ mock data challenge. Routine sysadmin work. |  |  | Problem with storage accounting. There are more atlas files than atlas sees.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Staff leaving. University currently doesn't support ipv6. ipv6 has been disabled on the University border (support issues from the University provider). |  |  | Keeping documentation upto date. Discussion with the University on the ipv6 problem.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | new wn's have been purchased and installed. old wn's wn's have been decommissioned |  |  | 30 June 2017
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Install test wn's with sl7. Fix storage accounting. |  |  | 30 September 2017
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
atlas cloud support work
Other outputs and Knowledge |  |  | Date |  | Notes