## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q1 2017 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 128.7% | 128.7% | 114.9% | 381% | 381% | 72.92% | 140.1% | 140.1% | 147.2% | 128.4% | 128.4% | 186.7% | 242.6% | 242.6% | 189.4% | 155.6% | 155.6% | 155.6% | 183.9% | 183.9% | 146.2%
.x.2 | % of promised (by that time) CPU available | 100% | 269.8% | 269.8% | 232.2% | 481.1% | 481.1% | 402.1% | 257% | 257% | 212.8% | 300.4% | 339.5% | 338.7% | 324.4% | 324.4% | 272.6% | 538.8% | 538.8% | 1522% | 321.5% | 331.1% | 299.8%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 86.9% | 84.24% | 100% | 99.6% | 98.3% | 100% | 100% | 99.1% | 100% | 97.06% | 99.97% | 100% | 86.77% | 72.75% | 86% | 99.33% | 45.8% | 98% | 94.94% | 83.36%
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 86.9% | 85.69% | 100% | 99.6% | 98.3% | 100% | 100% | 99.18% | 100% | 97.06% | 99.97% | 100% | 87.06% | 74.53% | 86% | 99.55% | 45.8% | 98% | 95.03% | 83.91%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 65.42% | 64.52% | 74.24% | 57.15% | 44.3% | 17.31% | 88.5% | 88.68% | 114% | 70.59% | 81.91% | 88.79% | 72.27% | 83.73% | 80.92% | 77.78% | 78.66% | 50.42% | 69.65% | 75.19% | 73.58%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 59.85% | 57.68% | 61.58% | 46.96% | 35.23% | 14.48% | 77.32% | 78.4% | 78.41% | 58.4% | 52.83% | 52.83% | 52.12% | 66.35% | 63.29% | 69.44% | 71.02% | 41.8% | 55.6% | 58.06% | 53.69%
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2017
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2017-04-01 | 2017-05-01 | 2017-06-01 | Total |  | Site | 2017-04-01 | 2017-05-01 | 2017-06-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 4478371.5605 | 9552864.2686 | 8574400.6885 | 22605636.5176 |  | Birmingham | 5112357.587 | 11541031.51 | 10597508.46 | 27250897.557
Cambridge | UMD 4/SL6 | UMD 4/SL6 |  | 10Gb/s | 2*20Gb/s | DPM 1.8.11 |  | Bristol | 2482692.4387 | 1087360.7808 | 1490419.4233 | 5060472.6428 |  | Bristol | 2817516.183 | 1342570.337 | 1888749.027 | 6048835.547
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.8.11.1 |  | Cambridge | 2787699.3321 | 3599358.0487 | 3672867.6547 | 10059925.0355 |  | Cambridge | 3900800.845 | 4085841.03 | 6637516.576 | 14624158.451
RALPP | UMD3/4 | UMD3 |  | 10Gb/s | 10Gb/s | Dcache 2.13.51 |  | Oxford | 13597646.4738 | 16415238.1527 | 17481862.1313 | 33632519 |  | Oxford | 18535523.23 | 18922151.27 | 19064895.69 | 56522570.19
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 17976648.2719 | 22729064.7176 | 22586220.6986 | 63291933.6881 |  | RALPP | 26041822.35 | 27036869.65 | 27852562.87 | 80931254.87
[8 empty] | Sussex | 768884.4319 | 1191334.8651 | 3082027.4447 | 5042246.7417 |  | Sussex | 1215795.611 | 1409183.209 | 3456039.694 | 6081018.514
[8 empty] | Total CPU hrs | 42091942.5089 | 54575220.8335 | 56887798.0411 | 153554961.3835 |  | Total | 57623815.806 | 64337647.006 | 69497272.317 | 191458735.129
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | efficiency
Birmingham | 16994 | 920 | 7319 | 801 | 232.2% | 114.9% | 14.11% | 16.94% | 22605636.5176 | 16.18% | 2160 | 36707040 | 61.58% | 74.24% | 82.95%
Bristol | 16175 | 560 | 4023 | 768 | 402.1% | 72.92% | 13.43% | 10.31% | 5060472.6428 | 3.623% | 2160 | 34938000 | 14.48% | 17.31% | 83.66%
Cambridge | 5940 | 290 | 2791 | 197 | 212.8% | 147.2% | 4.931% | 5.341% | 10059925.0355 | 7.201% | 2160 | 12830400 | 78.41% | 114% | 68.79%
Oxford | 29473 | 980 | 8701 | 525 | 338.7% | 186.7% | 24.47% | 18.05% | 33632519 | 24.08% | 2160 | 63661680 | 52.83% | 88.79% | 59.5%
RALPP | 46300 | 2610 | 16985 | 1378 | 272.6% | 189.4% | 38.43% | 48.07% | 63291933.6881 | 45.31% | 2160 | 100008000 | 63.29% | 80.92% | 78.2%
Sussex | 5584 | 70 | 367 | 45 | 1522% | 155.6% | 4.635% | 1.289% | 5042246.7417 | 3.61% | 2160 | 12061440 | 41.8% | 50.42% | 82.92%
Totals | 120466 | 5430 | 40186 | 3714 | 299.8% | 146.2% | 100% | 100% | 139692733.6257 | 100% | 2160 | 260206560 | 53.69% | 73.58% | 72.96%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken |  | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Birmingham |  | 0 |  |  | Birmingham | 22433 | 980
Bristol |  | 0 |  |  | Bristol | 9607 | 0
Cambridge |  | 0 |  |  | Cambridge | 5940 | 293
Oxford |  | 0 |  |  | Oxford | 26240 | 940
RALPP |  | 0 |  |  | RALPP | 42840 | 3079
Sussex |  | 0 |  |  | Sussex | 2006 | 83
Totals |  | 0 | 0 | 0
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D30: gronbech: Sussex may have promised 2000 by email.?
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2017
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 12
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 1 | 1 | [6 empty] | 5
[45 empty] | 0 | 0
[45 empty] | 0 | 0
Total | 6 | 7 | 0 | 3 | 3 | 3 | 1 | 1 | 2 | 6 | 7 | 1 | 2 | 3 | 0 | 4 | 1 | 6 | 3 | 1 | 5 | 1 | 6 | 2 | 2 | 2 | 1 | 0 | 0 | 3 | 1 | 1 | 7 | 4 | 1 | 0 | 0 | 3 | 7 | 1 | 0 | 2 | 0 | 0 | 4 | 113
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
0 | 0 | 0.624 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.974 | 0.02394% | 16.43%
Birmingham | 352.4 | 216 | 0.12 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0.001 | 0.01 |  | 0 | 0 | 0 | 0.02 | 0 | 0.2 | 0.02 |  | 0.53 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 570.901 | 14.03% | 0.4379%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 9.442% | 0.001822%
Cambridge | 0 | 197.8 | 0 | 0 | 0.096 | 0.02 | 0 | 0 | 0 | 0 | 0.004 |  | 0 | 0 | 0 | 0 | 0 | 0.207 | 0 |  | 0 | 0 | 0.449 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.576 | 4.882% | 0.1647%
Oxford | 0 | 635 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.005 | 0 | 0 | 0.035 |  | 0.004 | 0 | 0.03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032 | 0 | 0 | 0 | 7.88 | 0.018 | 0.016 | 1.5 | 31.98 | 0 | 0 | 0.0234 | 678.2364 | 16.67% | 6.221%
RALPP | 0 | 649 | 2 | 0.9 | 0 | 0 | 0 | 0 | 0 | 1174 | 0.27 | 0 | 0.148 | 0 | 0 | 0 | 0 | 0 |  | 1.753 | 0 | 340 |  | 0 | 20 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.786 | 0 | 0 | 0 | 0 | 0 | 2189.457 | 53.82% | 16.74%
Sussex |  | 44.626 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [8 empty] | 45.636 | 1.122% | 2.213%
Total | 352.4 | 1743.05 | 2.12 | 1.05 | 0.396 | 0.044 | 0 | 0 | 0 | 1559.111 | 0.341 | 0 | 0.197 | 0.6 | 0 | 0.025 | 0 | 0.407 | 0.055 | 1.753 | 0.534 | 340 | 0.671 | 0 | 20 | 0.6 | 0 | 0 | 0 | 1.26 | 0 | 0 | 0 | 0.052 | 0 | 0 | 1 | 7.88 | 0.018 | 0.802 | 1.5 | 31.98 | 0 | 0 | 0.0434 | 4067.8894 | 100% | 10.14%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2017
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | 1 | 1 | 1
Matt Williams
Bristol | Winnie Lacesso |  |  |  | 0.2 | 0.2 | 0.2
Luke Kreczko
Cambridge
| John Hill |  |  |  | 0.5 | 0.5 | 0.5
Oxford
| Vip Davda | 0.5 | 0.5 | 0.5
| Kashif Mohammad | 0.5 | 0.5 | 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris |  |  |  | 0.1 | 0.1 | 0.1
| Leo Rojas |  |  |  | 0.3 | 0.3 | 0.3
Total |  | 2.6 | 2.6 | 2.6 | 1.8 | 1.8 | 1.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q1 2017
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Nearly finished the transfer to VAC - 70% of the site now converted. |  | Nothing of significance to report
Bristol | . Several non-DICE WN now using WN software from cvmfs . Very much improved reliability of OS deployment infrastructure, nearly painless WN rebuilds . Singularity available for local & grid users . 2 New 40TB WN SL7; storage in production, CPU currently in testing only |  | . Severe site staff shortage . Site outage due to HPC power problems 14 Mar (outage only 3.25hrs) . Site outage due to HPC power problems 21 Jun (outage not quite 24hrs) . Some new DICE WN logging Hardware Errors; still under warranty, must find time to run diags & juggle WN storage outage with Dell site visit . Some older (no warranty) DICE WN starting to log hardware/disk problems . IT Networks has lost interest in deploying perfsonar, back to us . IT Networks seems to've lost interest in "Science DMZ", no progress
Cambridge | Squid, UI and Site BDII moved to CentOS7 VMs on new CentOS 7 server. perfSONAR upgraded to V4. cvmfs upgraded to 2.3.5. Part way through moving to new puppetmaster (V3). Nearly ready to implement VAC site (initially on new hardware). |  | perfSONAR server out of warranty - what is policy on replacement? Server supporting CREAM CE VM dying (VM moved to new hardware early in Q3).
Oxford | Installed a xrootd server to test CMS caching and the plan was that Alastair and Chris will coordinate to configure and test it. The second part didn't happen yet. WN's drained and rebooted to apply new Kernel updates for various security updates.
RALPP | dCache successfully updated to 2.16 at the second attempt Second half of top level router brought into production HTCondor updated to version 8.6 CentOS7 VM Test ArcCEs rebuilt as physical machines for production |  | dCache update to 2.16 failed on the first attempt after the database schema update took too long, after discussion with dCache developers more indexes were added to the DB
Sussex | We considerably increased our compute power, from 256 to 568 logical CPUs. We currently provide nearly 5.58 kHS06 to the grid instead of the 2.1 kHS06 we used to. The number of multicore jobs increase from ~39 to ~140. Last quarter availability was affected by failing purge tests on our CE. Operations' jobs were queued for a long time before running. Purge test needed the jobs to run successfully to be able to purge them, so it seems a time out was reached at some point making purge tests to fail almost 80% of the time. An ops jobs dedicated queue was created with one slot reserved. That way ops jobs are not queued any more. Purge tests and availability figures has been fine during the last 3 weeks, so availability warning tickets were cleared up accordingly. |  | Our site capacity has not been properly published. Even though we followed the documented procedure for our cream CE and ran YAIM a number of times with the up-to -date values, REBUS is showing 0 for all our site's parameters. An Xrootd server has been deployed but it has not been able to go into production yet. The xrootd protocol initialization is currently failing since a monitor destination port is missing or invalid in redirfiles (according to the log files).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern. |  | Recruitment ongoing at Sussex.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Refine Top Level Router Config |  | 31/06/2017 |  | Second router box is running
RALPP: Purchase new hardware with GridPP Allocation |  | 31/06/2017 |  | Procurement held up in SBS,
Bristol: First deployment of kubernetes |  | 2017-12-31 |  | Fail mainly due to severe site staff shortage & needing help from outside (e.g. Andrew Lahiff)
Bristol: Roll out new IPv4 and IPv6 network to bypass university firewall |  | 12/31/2017 |  | Probably even higher SE bandwidth? Fail mainly due to Severe site staff shortage & lack of interest from IT Networks
Bristol: Work together with IT services to deploy new perfsonar hosts |  | 12/31/2017 |  | hosts up + running Fail mainly due to Severe site staff shortage & lack of interest from IT Networks
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Purchase new hardware with GridPP Allocation |  | 31/09/2017 |  | Order placed.
Bristol: First deployment of kubernetes |  | 2017-12-31 |  | Run HTCondor and Apache Spark on kubernetes
Bristol: Roll out new IPv4 and IPv6 network to bypass university firewall |  | 12/31/2017 |  | Probably even higher SE bandwidth?
Bristol: Work together with IT services to deploy new perfsonar hosts |  | 12/31/2017 |  | hosts up + running
Bristol: Add support for LZ, lsst, & DUNE Vos |  | 2017-07-31 |  | pass tests for these VOs. (Success as of 05/07/2017)
Sussex |  | 2017-08-31 |  | XrootD front end
Sussex |  | 31/09/2017 |  | Migration of service nodes into a new virtual machine host server
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop