## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q317 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 305.8% | 305.8% | 305.8% | 281.5% | 281.5% | 281.5% | 233.5% | 233.5% | 233.5% | 151.9% | 151.9% | 151.9% |  |  | 0% | 232.7% | 232.7% | 232.7%
.x.2 | % of promised (by that time) CPU available | 100% | 363.3% | 363.3% | 363.3% | 275.9% | 275.9% | 275.9% | 375.1% | 375.1% | 375.1% | 450.5% | 450.5% | 450.5% |  |  | 0% | 339.2% | 339.2% | 339.2%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 95% | 100% | 100% | 100% | 100% | 99% | 97% | 99% | 99% | 99% | 100% | 100% |  |  |  | 97.75% | 99.75% | 99.5%
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 95% | 100% | 100% | 100% | 100% | 99% | 97% | 100% | 99% | 99% | 100% | 100% |  |  |  | 97.75% | 100% | 99.5%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 91.56% | 46.86% | 57.91% | 71.28% | 81.61% | 88.36% | 54.57% | 55.99% | 85.13% | 71.7% | 92.13% | 98.38% |  |  |  | 71.59% | 70.54% | 84.23%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 69.11% | 33.42% | 41.47% | 60% | 71.45% | 81.25% | 54.57% | 55.99% | 85.13% | 63.15% | 78.07% | 84.49% |  |  |  | 61.08% | 61.49% | 75.13%
.x.3/.4
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q317
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2017 Jul | 2017 Aug | 2017 Sep | Total |  |  | 2017 Jul | 2017 Aug | 2017 Sep | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 8615348.5588 | 10917735.7728 | 12511440.5831 | 32044525 |  | UKI-LT2-Brunel | 12125117.8709 | 16217594.8598 | 16413843.9559 | 44756557
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 36473383.9054 | 36557664.839 | 35423522.0303 | 108454571 |  | UKI-LT2-IC-HEP | 37203810.1703 | 40415446.6294 | 40335328.5149 | 117954585
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 29406005.2701 | 29851070.8127 | 26007545.8691 | 85264622 |  | UKI-LT2-QMUL | 29406022.4087 | 29851072.696 | 26007546.9836 | 85264642
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 22767175.228 | 25309534.8767 | 22812558.78 | 70889269 |  | UKI-LT2-RHUL | 26449633.7615 | 29620508.7115 | 26470752.3547 | 82540895
[8 empty] | UKI-LT2-UCL-HEP | 272327.4683 | 909121.2047 | 664389.524 | 1845838 |  | UKI-LT2-UCL-HEP | 315922.4829 | 989162.6978 | 735016.1218 | 2040101
[8 empty] | Total | 97534240 | 103545128 | 97419457 | 298498825 |  | Total | 105500507 | 117093786 | 109962488 | 332556780
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1400 | 9632.812 | 457.8006 | 363.3% | 305.8% | 19.57% | 14.12% | 32044525 | 10.8% | 2208 | 77280000 | 41.47% | 57.91% | 71.6%
UKI-LT2-IC-HEP | 60456 | 3699 | 21915.766 | 1313.8219 | 275.9% | 281.5% | 33.81% | 37.31% | 108454571 | 36.56% | 2208 | 133486848 | 81.25% | 88.36% | 91.95%
UKI-LT2-QMUL | 45363 | 3316 | 12094.921 | 1420.211 | 375.1% | 233.5% | 25.37% | 33.44% | 85264622 | 28.74% | 2208 | 100161504 | 85.13% | 85.13% | 100% | Slurm accounting problem whereby CPU time = wall time
UKI-LT2-RHUL | 38000 | 1500 | 8434.349 | 987.6466 | 450.5% | 151.9% | 21.25% | 15.13% | 70889269 | 23.9% | 2208 | 83904000 | 84.49% | 98.38% | 85.88%
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 178819 | 9915 | 52714.598 | 4260.48 | 339.2% | 232.7% | 100% | 100% | 296652987 | 100% | 2208 | 394832352 | 75.13% | 84.23% | 89.76%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 4503 | 53810 | 1438
UKI-LT2-IC-HEP | 5716 | 56644 | 3568
UKI-LT2-QMUL | 4248 | 46797 | 3410
UKI-LT2-RHUL | 3832 | 38408 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 195659 | 9876
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q317
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cepc | cernatschool.org | comet.j-parc.jp | cms | dteam | dune | dzero | enmr.eu | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | icecube | ilc | ipv6.hepix.org | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | neiss.org.uk | ops | pheno | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.gear.cern.ch | vo.helio-vo.eu | vo.landslides.mossaic.org | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 22
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17
Total | 0 | 4 | 4 | 2 | 0 | 1 | 3 | 1 | 4 | 4 | 4 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 3 | 1 | 4 | 0 | 4 | 3 | 3 | 4 | 1 | 0 | 4 | 4 | 4 | 1 | 0 | 0 | 4 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 75
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | lsst | cernatschool.org | vo.moedal.org | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.311 |  | 0.342 |  |  |  | 0.069 | 930 |  | 34.14 | 0.017 | 0.002 |  |  |  |  | 1.491 | [5 empty] | 0.544 | 0.007 |  |  |  |  | 0.202 | [6 empty] | 0.018 |  | 0 |  |  |  |  | 967.143 | 13.31% | 0.3105%
UKI-LT2-IC-HEP |  | 30.476 | 0 |  | 0 |  | 0 | 1965.662 |  | 17.081 |  |  |  |  | 256.5 |  |  |  | 0 | [15 empty] | 36.652 |  |  | 222.524 |  |  |  | 45.711 | 2574.606 | 35.43% | 13.03%
UKI-LT2-QMUL |  | 132 | 0.711 |  |  | 0 |  | 3.3 |  | 2200 | 0.052 |  |  |  | 238.715 |  | 0.673 | 0.0068 |  |  |  | 0.016 | 0.014 | 0.0043 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 14 |  |  |  | 0 | 0.109 | 0.073 | 0.01 |  | 2589.7083 | 35.64% | 5.703%
UKI-LT2-RHUL | 0 |  | 0.42 |  |  |  |  | 1.621 |  | 1133 | 0.015 | 0.001 |  |  |  |  | 0.19 | [5 empty] | 0.001 | 0.006 | [6 empty] | 0.009 | 0 | [5 empty] | 0 |  |  |  |  | 1135.263 | 15.62% | 0.05655%
Total | 0.311 | 162.476 | 1.473 | 0 | 0 | 0 | 0.069 | 2900.583 | 0 | 3384.221 | 0.084 | 0.003 | 0 | 0 | 495.215 | 0 | 2.354 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.559 | 0.0173 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.009 | 0 | 0.019 | 14 | 36.652 | 0.018 | 0 | 222.524 | 0.109 | 0.073 | 0.01 | 45.711 | 7266.7203 | 100% | 6.698%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q317
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.85 | 0.85 | 0.85 | 0.15 | 0.15 | 0.15
| Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
| P. Hobson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| B.Green/Tom | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 6.9 | 6.9 | 6.9 | 1.85 | 1.85 | 1.85

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q317
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | Testing running jobs in LXD containers
UKI-LT2-IC-HEP | Upgraded dCache to version 3.2 and storage pool nodes also upgraded to CentOS7.
UKI-LT2-QMUL | Tendered and brought and physical installed an additional 2.4PB of storage (1.7PB actual after raid and formatting) This is in a traditional resilient lustre setup of 4 JBODS and two servers (1/2 a rack of new storage = 72 Dell R510s) Brought and installed new rack for storage. Brought and tested a consumer GPU node (Nvidia GTX1080Ti) Gave talk at GridPP39 on GPUs Deployed new syslog and backup server Deployed test Centos 7 systems. Production - One worker node, one production monitoring server, Development - VM host and several build and test nodes * Conversion of existing ISC dhcpd configuration to ISC Kea. * Investigation of dnsdist (https://dnsdist.org) as a means of logging hostnames referenced by submitted jobs that only have A records and not AAAA records; this may be useful information for VOs to have in gearing up towards getting their act together re: preparing for IPv6-only computing resources. * Initial (read: very flaky) implementation of an sFlow collector for purpose of understanding traffic flows between hosts at our site and those at other WLCG sites. * Working towards getting our IPv6 address space properly routed towards our local routers for the purpose of providing native IPv6 connectivity to the entirety of our backend nodes which will fulfil our obligations to provide IPv6-capable computing resources.
UKI-LT2-RHUL
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes