## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q3 2017 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 177% | 161% | 223.2% | 152% | 151% | 151.3% | 220% | 195% | 219.4% | 136% | 154% | 153.9% | 200.4%
.x.2 | % of promised (by that time) CPU available | 100% | 443% | 227% | 226.6% | 285% | 213% | 213% | 314% | 214% | 180.6% | 334% | 210% | 210.2% | 205.8%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 97% | 96% | 92% | 97% | 100% | 85% | 99% | 98% | 100% | 97% | 73% | 84% | 90.25%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 97% | 86% | 95% | 97% | 100% | 100% | 99% | 98% | 100% | 98% | 74% | 84% | 94.75%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 74% | 62% | 64.66% | 90% | 73% | 35.47% | 95% | 98% | 130.6% | 80% | 89% | 88.47% | 82.66%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 64% | 53% | 57.23% | 82% | 63% | 32.31% | 85% | 87% | 119.4% | 71% | 82% | 58.4% | 72.75%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html |  |  | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2017
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | umd4 | 10Gb/s | 10Gb/s | DPM |  | Site | 2017-07-01 | 2017-08-01 | 2017-09-01 | Total |  | Site | 2017-07-01 | 2017-08-01 | 2017-09-01 | Total
Liverpool | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 17878083 | 19739723 | 20607906 | 58225712 |  | Lancaster | 22349878 | 21750041 | 21688562 | 65788481
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 3259293 | 4386097 | 7808871 | 15454261 |  | Liverpool | 3667635 | 4773654 | 8521481 | 16962770
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 32379955 | 34300097 | 31804971 | 98485023 |  | Manchester | 35231920 | 37642099 | 34828644 | 107702663
[7 empty] | Sheffield | 5316142 | 4641445 | 3658729 | 13616316 |  | Sheffield | 4812236 | 6881669 | 8933852 | 20627757
[7 empty] | Total CPU hrs | 53517331 | 58425917 | 60221748 | 172164996 |  | Total | 66061669 | 71047463 | 73972539 | 211081671
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2017/1/2017/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 46080 | 3054 | 20332 | 1368 | 226.6% | 223.2% | 39.84% | 35.96% | 58225712 | 31.34% | 2208 | 101744640 | 57.23% | 64.66%
Liverpool | 21660 | 1403 | 10169 | 927 | 213% | 151.3% | 18.73% | 16.52% | 15454261 | 8.319% | 2208 | 47825280 | 32.31% | 35.47%
Manchester | 37356 | 3504 | 20685 | 1597 | 180.6% | 219.4% | 32.3% | 41.26% | 98485023 | 53.01% | 2208 | 82482048 | 119.4% | 130.6%
Sheffield | 10560 | 531 | 5024 | 345 | 210.2% | 153.9% | 9.131% | 6.253% | 13616316 | 7.329% | 2208 | 23316480 | 58.4% | 88.47%
Totals | 115656 | 8492 | 56210 | 4237 | 205.8% | 200.4% | 100% | 100% | 185781312 | 100% | 2208 | 255368448 | 72.75% | 82.66%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 46080 | 3054 | NA | Lancaster
Liverpool | 2018 | 21660 | 1403 | NA | Liverpool
Manchester | 4480 | 37356 | 3504 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 10498 | 115656 | 8492 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2017
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | na48 | na62 | neiss | ops | pheno | vo.skatelescope.eu | snoplus | vo.sixt.cern.ch | londongrid | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1 | 1 | 0 |  | 1 |  |  | 1 |  |  | 1 |  | 15
Liverpool | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 33
Manchester | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 24
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 0 | 1 | 1 | 0 |  |  |  | 1 | 1 |  | 1 |  |  | 1 | 1 | 0 | 1 |  | 18
Total | 3 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 1 |  | 2 | 4 | 2 |  | 2 | 4 | 1 |  | 2 | 1 | 1 | 1 |  | 4 | 3 |  | 4 | 1 | 1 | 4 | 2 | 2 | 4 |  | 90
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1650 | 0 | 17 | 5 | 1672 | 1.017% | 1.316%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3820.24 | 0.57 | 179 | 12.47 | 4120.46 | 4.344% | 4.661%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2017
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long
M. Doidge
P. Love
Liverpool | S. Jones
R. Fay
J. Bland
Manchester | A. Forti
R. Frank
A. McNab
Sheffield | E. Korolkova
Total |  | 0 | 0 | 0 | 0 | 0 | 0
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | 0.5 | 0.5 | 0.5
Manchester | A. Forti |  |  |  | 1 | 1 | 1

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q2
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | C7 Migration New Vos enabled. More IPv6 testing Vacation Season | Majority of the cluster moved to C7 NA62 and skatelescope rolled out IPv6 testing methodology perfected Everyone is feeling refreshed |  |  | Still need to leave some kit on SL6 for non-atlas Vos. Still no greenlight to dualstack everything Reduced manhours this quarter.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Still need a new SE headnode – current one out of warranty. Need new CE as well. NFS server struggling under load (same risks as last quarter, C7 migration took a lot of effort)) |  |  | Not showing its age since updated, will set up test SE next quarter. Looking at HTCondor Need to fix stagein/out scripts.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | C7 upgrade |  |  | 30/9/17 |  | Moved and adjusted to C7
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | New CE, to allow for containerisation strategies. Large scale tarball update. Dualstack SE, or I'll eat my hat |  |  | 23/12/2017 |  | New CE New tarballs End of the v6 saga at Lancaster.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q3
Reported by | S Jones, J Bland, R Fay
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Routines Talks, Docs Server Room Move | Routine sys admin (SSL Firewall interference, kernel updates, re-benchmarking, removal of state Vos: camont, cdf, d0, esr, magic, neiss. Complete move to UMD, Create Centos7 builds for 3 architectures, DPM pool updated to Centos7 DPM 1.9) Slides prepared to WLCG Accounting Task Force to show how to do round trip, black box testing of APEL system. Wrote doc on GridPP wiki to demonstrate Centos7 Worker Node Adoption using Puppet3/Hiera. Wrote puppet3/Hiera modules for Centos 7 worker node adoption without Yaim. Completed move to new room, aircon, power, network, hardware, etc. |  | None to speak of Will present at 19th Oct WLCG/CERN meeting. None. But we do need guidance on adoption of new tech, cloud, containers, Vms, also storage systems and protocols. What is a full generic site? Requirements, please. In the runup, there was much reduced throughput. I will attempt to maximise throughput for next quarter to make up. This happened due to flaky aircon, and outage time for move, and on top we had big ssl problems due to external contractor and firewall. It's all over now, though.
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | Ipv6 Medium sized site Network redundancy, lack of |  | Need to work with external supplier (CSD). Link works, but too slow for real use. Plotting course as “medium sized site.” We lack network stack redundancy. Some of our kit is out of warranty. A failure would lead to some outage; no funds to improve this situation.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Continue adoption of Ipv6, documentation Continue adoption of Centos7 Continue GridPP5 HW purchases Progress on new cooling from facilities Convert site to Puppet 3 Plans to continue with Tom Whyntie's user guide VAC Superslot/Multicore tests |  | '30/09/2017 '30/09/2017 '30/09/2017 '30/09/2017 '30/09/2017 '30/09/2017 '30/09/2017 |  | Prepared but link too slow to go live. Prepared but too little traffic to go live. Slipped, CPU next All done In progress, will take years. Slipped Slipped
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Continue adoption of Ipv6, documentation Continue adoption of Centos7 Continue GridPP5 HW purchases Convert site to Puppet 3 Plans to continue with Tom Whyntie's user guide VAC Superslot/Multicore tests Research usefulness of Condor/Singularity, document baseline Develop Account Black Box Testing |  | '30/12/2017 '30/12/2017 '30/12/2017 '30/12/2017 '30/12/2017 '30/12/2017 '30/12/2017 '30/12/2017 |  | Faster link needed from central services More traffic needed from Vos Spec for service node and CPU by XMAS Ongoing. Will take years. I'll look at it if there is a call for it. By XMAS Hot topic. Look at it. I'll do it if there is a call for it.

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q3
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | sl7 was installed on one mode which is currently under test. Storage accounting script is installed. Routine sysadmin work.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Local sysadmin who was helping with GridPP servers left. The post is advertised for the seconf time. University currently doesn't support ipv6. ipv6 has been disabled on the University border (support issues from the University provider). |  |  | University answer for enabling ipv6 is that this will require money. The question is still under discussion.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | one node is now running sl7. Under test. Storage accounting script is installed. |  |  | 30 September 2017
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Install arc ce. Connect sl7 nodes to condor cluster. |  |  | 2017-12-30
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
atlas cloud support work
Other outputs and Knowledge |  |  | Date |  | Notes