## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q4 2017 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 161% | 223% | 224.7% | 151% | 151% | 153.7% | 195% | 219% | 215.9% | 154% | 154% | 153.9% | 200.1%
.x.2 | % of promised (by that time) CPU available | 100% | 227% | 227% | 226.6% | 213% | 213% | 213% | 214% | 181% | 175.2% | 210% | 210% | 210.2% | 203.8%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 96% | 92% | 93% | 100% | 85% | 100% | 98% | 100% | 100% | 73% | 84% | 73% | 91.5%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 86% | 95% | 93% | 100% | 100% | 100% | 98% | 100% | 100% | 74% | 84% | 77% | 92.5%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 62% | 65% | 71.87% | 73% | 35% | 91.54% | 98% | 131% | 147.5% | 89% | 88% | 100.7% | 102.2%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 53% | 57% | 65.26% | 63% | 32% | 82.47% | 87% | 119% | 128% | 82% | 58% | 90.24% | 90.67%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html |  |  | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2017
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | umd4 | 10Gb/s | 10Gb/s | DPM |  | Site | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total |  | Site | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Liverpool | Umd3/4 | Umd3/4 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 22622624 | 21695198 | 20634963 | 64952785 |  | Lancaster | 24218390 | 23582853 | 23734293 | 71535536
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 12331715 | 12922831 | 13331016 | 38585562 |  | Liverpool | 13349763 | 14361818 | 15114616 | 42826197
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 33705056 | 32897117 | 33594533 | 100196706 |  | Manchester | 38505153 | 37579934 | 39332644 | 115417731
[7 empty] | Sheffield | 5951573 | 7704323 | 6927755 | 20583651 |  | Sheffield | 6626550 | 8510455 | 7831845 | 22968850
[7 empty] | Total CPU hrs | 68659395 | 67515146 | 67560512 | 203735053 |  | Total | 82699856 | 84035060 | 86013398 | 252748314
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2017/1/2017/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 46080 | 3074 | 20332 | 1368 | 226.6% | 224.7% | 40.23% | 36.26% | 64952785 | 28.96% | 2160 | 99532800 | 65.26% | 71.87%
Liverpool | 21660 | 1425 | 10169 | 927 | 213% | 153.7% | 18.91% | 16.81% | 38585562 | 17.2% | 2160 | 46785600 | 82.47% | 91.54%
Manchester | 36233 | 3448 | 20685 | 1597 | 175.2% | 215.9% | 31.64% | 40.67% | 100196706 | 44.67% | 2160 | 78263280 | 128% | 147.5%
Sheffield | 10560 | 531 | 5024 | 345 | 210.2% | 153.9% | 9.22% | 6.263% | 20583651 | 9.176% | 2160 | 22809600 | 90.24% | 100.7%
Totals | 114533 | 8478 | 56210 | 4237 | 203.8% | 200.1% | 100% | 100% | 224318704 | 100% | 2160 | 247391280 | 90.67% | 102.2%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 46080 | 3074 | NA | Lancaster
Liverpool | 2018 | 21660 | 1425 | NA | Liverpool
Manchester | 3592 | 36233 | 3448 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 9610 | 114533 | 8478 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2017
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cernatschool | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hyperk.org | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | moedal | na48 | na62 | neiss | ops | pheno | planck | vo.skatelescope.eu | snoplus | solidexperiment.org | vo.sixt.cern.ch | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 |  | 0 | 1 | 0 | 1 | 0 |  | 1 | 1 |  |  | 1 |  |  | 1 |  | 16
Liverpool | 1 | 1 |  | 1 | 1 |  | 0 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 35
Manchester | 1 | 1 |  | 1 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 23
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 0 | 1 | 1 | 0 |  |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 0 | 1 |  | 18
Total | 3 | 4 | 0 | 3 | 1 | 1 | 0 | 0 |  | 3 | 4 | 1 | 1 | 1 | 2 | 1 |  | 2 | 4 | 2 | 2 |  | 2 | 4 | 1 |  | 2 | 1 | 1 | 1 | 1 |  | 4 | 3 |  | 3 | 4 |  | 1 | 4 | 2 | 2 | 4 |  | 92
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1800 | 0 | 17 | 1 | 1818 | 0.9351% | 0.9901%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3970.24 | 0.57 | 179 | 8.47 | 4266.46 | 4.196% | 4.407%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2017
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | bar: GridPP Funded Month 1 to GridPP Funded Month 3
M. Doidge | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| P. Love | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
Liverpool | S. Jones | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| R. Fay | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
| J. Bland | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Manchester | A. Forti | bar: GridPP Funded Month 1 to GridPP Funded Month 3
R. Frank | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| A. McNab | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Sheffield | E. Korolkova | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
Total |  | 5.5 | 5.5 | 5.5 | 1.8 | 1.8 | 1.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | EGI Funded Month 1: 0.5; EGI Funded Month 2: 0.5; EGI Funded Month 3: 0.5
Manchester | A. Forti | bar: Unfunded Month 1 to Unfunded Month 3

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q4
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | IPv6 Xcache SOC Tarball | DPM now all dual stacked Installed and started Xcache work Prepared for and engaged in workshop Started new tarball |  |  | A few hiccups, but fixed and documented. Deployment stalled None Hit some unexpected issues.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Still a bit too much SL6 at the site, need to migrate more to Centos7 There a few more services on nodes that are out of warranty then I would like. |  |  | Testing more C7 upgrades Either move more services to the central VM cluster or buy more hardware in the next purchase.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | IPv6 DPM Xcache Groundwork SOC Bro/MISP ground work |  |  | 22/12/17 |  | Beat deadline Engaged In xcache work Engaged in soc work
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | xcache testing Misp/bro investigated further Centos 7 builds tested for everything IPv6 testing Tarball infrastructure overhaul |  |  | 2018-03-30 |  | Help on CHEP paper Build on SOC work Ready to move to all C7 Measurements for other sites Easier tarball rollout.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q4
Reported by | S Jones, J Bland, R Fay
Progress over last Quarter
Site | Work area | Successes |  | Problems/Issues
Liverpool | Grid Admin Routine work Documentation | More migration to CentOS7 (storage, service nodes) Extra VO support (LOFAR,SKA, LZ commissioning) UMD4 tests and production CentOS7 ARC CE + redundancy Bouncycastle Bugs (GGUS 132205) Tighter HTCondor security lcg-CA, HEPOS_libs, space tokens, CentOS7 firewall, Certificate renewal, CVEs CVE-2017-1000-253 (kernel update) CVE-2017-7184 (unpriv user namespace) Docs for Accounting Audit, maintenance of approved VOs doc, defined suite of Puppet modules for ARC/HTCondor C7 adoption documentation, github. |  | None – it's ongoing None None Needs test by another site, also not in prod yet. None – fixed None – good baseline found No problems for routine work Puppet modules need testing to see if solution is general.
Note:To get multiple lines per box use Alt-Return
Institute or area specific risks
Site | Risk |  | Mitigating Action
Liverpool | Ipv6 Medium sized site Network redundancy, lack of |  | Need to work with external supplier (CSD). Link works, but too slow for real use. Discussions still ongoing, esp. funding. Plotting course as “medium sized site.” We lack network stack redundancy. Some of our kit is out of warranty. A failure would lead to some outage; no funds to improve this situation.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Continue adoption of Ipv6, documentation Continue adoption of Centos7 Continue GridPP5 HW purchases Convert site to Puppet 3 VAC Superslot/Multicore tests Research usefulness of Condor/Singularity, document baseline |  | '30/12/2017 '30/12/2017 '30/12/2017 '30/12/2017 '30/12/2017 '30/12/2017 |  | Delayed; funding questions. see above. Now delayed – Spectre/Meltdown Now delayed – Spectre/Meltdown Ongoing. Will take years. Hot topic. Look at it next Q. Hot topic. Look at it next Q.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  | Due Date |  | Metric/Output
Liverpool | Adoption of Ipv6, documentation Adoption of Centos7 GridPP5 HW purchases Convert site to Puppet 3 VAC Superslot/Multicore tests Research usefulness of Condor/Singularity, document baseline Test modules to implement ARC/CE HTCondor on CentOS Definitive fix for Spectre/Meltdown on all CPUs |  | '31/03/2018 '31/03/2018 '31/03/2018 '31/03/2018 '31/03/2018 '31/03/2018 '31/03/2018 '31/03/2018 |  | +ve outcome on funding questions No SL6 nodes left Delayed by Spectre/Meltdown Will take years VAC multicore operational Ability to implement Other site needed to show usefulness Fix installed

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 17Q4
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | Cleaning dpm storage with various scripts. Argus server and arc ce have been reinstalled as Centos7. Work on installation of wns with puppet. Routine sysadmin work. |  |  | This results in Q4 were affected by the problem with lcg-CA 1.88-1-patch. The recommendation on tb-support jobs didn't work straight away in Sheffield. Only 50% of jobs were authenticated.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | Local sysadmin who was helping with GridPP servers left. The post is advertised for the third time in December. University currently doesn't support ipv6. |  |  | University answer for enabling ipv6 is that this will require money. The question is still under discussion.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Cleaning dpm storage with various scripts. Argus server and arc ce have been reinstalled as Centos7. Work on installation of wns with puppet. |  |  | 30 December 2017
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Continue work on installation of wns with puppet and moving servers to sl7. |  |  | 2018-03-31
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
atlas cloud support work
Other outputs and Knowledge |  |  | Date |  | Notes