## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q4 2017 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 114.9% | 114.9% | 114.9% | 72.92% | 72.92% | 72.92% | 147.2% | 134.5% | 134.5% | 186.7% | 186.7% | 186.7% | 189.4% | 189.4% | 189.4% | 155.6% | 155.6% | 155.6% | 146.2% | 145.5% | 145.5%
.x.2 | % of promised (by that time) CPU available | 100% | 232.2% | 232.2% | 232.2% | 402.1% | 366.5% | 366.5% | 212.8% | 301% | 328.2% | 338.7% | 338.7% | 338.7% | 272.6% | 272.6% | 272.6% | 1522% | 1522% | 1522% | 299.8% | 302.3% | 304.2%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 84.24% | 80% | 88.7% | 98.3% | 98% | 98.6% | 99.1% | 100% | 97.9% | 99.97% | 99.97% | 98.07% | 72.75% | 96% | 99.79% | 45.8% | 90% | 89.8% | 83.36% | 94% | 95.48%
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 85.69% | 80% | 88.7% | 98.3% | 100% | 100% | 99.18% | 100% | 97.9% | 99.97% | 99.97% | 98.07% | 74.53% | 99% | 99.79% | 45.8% | 90% | 89.8% | 83.91% | 94.83% | 95.71%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 74.24% | 45.35% | 53.58% | 17.31% | 39.49% | 44.92% | 114% | 84.52% | 87.86% | 88.79% | 84.29% | 83.33% | 80.92% | 83.78% | 86.08% | 50.42% | 81.74% | 68.93% | 73.58% | 73.11% | 75.29%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 61.58% | 37.41% | 46.6% | 14.48% | 30.4% | 39.61% | 78.41% | 70.65% | 76.02% | 52.83% | 52.83% | 51.68% | 63.29% | 63.35% | 61.7% | 41.8% | 63.25% | 44.38% | 53.69% | 53.67% | 54.8%
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html
summarised here | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q4 2017
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total |  | Site | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 3886723.2815 | 6365298.01 | 7235372.4191 | 17487393.7106 |  | Birmingham | 4398069.2237 | 7336566.5312 | 8368422.4459 | 20103058.2008
Cambridge | UMD 4/SL6 or C7 | UMD 4/SL6 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.0 |  | Bristol | 3906055.1346 | 6692750.2035 | 2295816.3839 | 12894621.722 |  | Bristol | 4262404.7976 | 7809073.5127 | 2552745.044 | 14624223.3543
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.8.11.1 |  | Cambridge | 5088740.4951 | 4949441.6788 | 5336570.8455 | 15374753.0194 |  | Cambridge | 5869100.0697 | 5685863.0515 | 6215305.5188 | 17770268.64
RALPP | UMD3/4 | UMD3 |  | 10Gb/s | 10Gb/s | Dcache 2.13.51 |  | Oxford | 16877412.7382 | 16317895.9472 | 15093775.407 | 33632519 |  | Oxford | 18608521.7687 | 18297251.8932 | 17325392.259 | 54231165.9209
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 20538051.6527 | 19975771.7779 | 22562271.2778 | 63076094.7084 |  | RALPP | 29652275.4559 | 28669688.2141 | 29681297.088 | 88003260.758
[8 empty] | Sussex | 1778636.0948 | 1556992.5618 | 2135659.7237 | 5471288.3803 |  | Sussex | 2813521.0858 | 2332533.2994 | 3353019.7173 | 8499074.1025
[8 empty] | Total CPU hrs | 52075619.3969 | 55858150.1792 | 54659466.057 | 162593235.6331 |  | Total | 65603892.4014 | 70130976.5021 | 67496182.073 | 203231050.9765
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | efficiency
Birmingham | 16994 | 920 | 7319 | 801 | 232.2% | 114.9% | 13.9% | 17.02% | 17487393.7106 | 11.82% | 2208 | 37522752 | 46.6% | 53.58% | 86.99%
Bristol | 14744 | 560 | 4023 | 768 | 366.5% | 72.92% | 12.06% | 10.36% | 12894621.722 | 8.716% | 2208 | 32554752 | 39.61% | 44.92% | 88.17%
Cambridge | 9160 | 265 | 2791 | 197 | 328.2% | 134.5% | 7.493% | 4.903% | 15374753.0194 | 10.39% | 2208 | 20225280 | 76.02% | 87.86% | 86.52%
Oxford | 29473 | 980 | 8701 | 525 | 338.7% | 186.7% | 24.11% | 18.13% | 33632519 | 22.73% | 2208 | 65076384 | 51.68% | 83.33% | 62.02%
RALPP | 46300 | 2610 | 16985 | 1378 | 272.6% | 189.4% | 37.87% | 48.29% | 63076094.7084 | 42.64% | 2208 | 102230400 | 61.7% | 86.08% | 71.67%
Sussex | 5584 | 70 | 367 | 45 | 1522% | 155.6% | 4.568% | 1.295% | 5471288.3803 | 3.698% | 2208 | 12329472 | 44.38% | 68.93% | 64.38%
Totals | 122255 | 5405 | 40186 | 3714 | 304.2% | 145.5% | 100% | 100% | 147936670.5407 | 100% | 2208 | 269939040 | 54.8% | 75.29% | 72.79%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken |  | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Birmingham |  | 0 |  |  | Birmingham | 22433 | 980
Bristol |  | 0 |  |  | Bristol | 9607 | 0
Cambridge |  | 0 |  |  | Cambridge | 5940 | 293
Oxford |  | 0 |  |  | Oxford | 26240 | 940
RALPP |  | 0 |  |  | RALPP | 42840 | 3079
Sussex |  | 0 |  |  | Sussex | 2006 | 83
Totals |  | 0 | 0 | 0
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D30: gronbech: Sussex may have promised 2000 by email.?
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q4 2017
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 12
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 0 | 1 | 1 | [6 empty] | 5
[46 empty] | 0 | 0
[46 empty] | 0 | 0
Total | 5 | 6 | 0 | 2 | 3 | 3 | 1 | 1 | 2 | 5 | 6 | 1 | 2 | 2 | 0 | 3 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 2 | 2 | 2 | 1 | 0 | 0 | 4 | 1 | 1 | 6 | 3 | 1 | 0 | 0 | 1 | 3 | 6 | 1 | 0 | 2 | 0 | 0 | 4 | 102
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
Birmingham | 446 | 215 | 0.11 | 0.1 | 0.28 | 0.01 | 0 | 0 | 0 | 0.001 | 0.01 |  | 0 | 0 | 0 | 0.02 | 0 | 0.16 | 0.03 |  | 0.51 | 0 | 0.05 |  |  | 0 | 0 | 0 | 0 | 1.21 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 663.531 | 16.97% | 0.3738%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 9.826% | 0.001822%
Cambridge | 0 | 230.8 | 0 | 0 | 0.096 | 0.024 | 0 | 0 | 0 | 0 | 0.004 |  | 0 | 0 | 0 | 0 | 0 | 0.208 | 0 |  | 0 | 0 | 0.441 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231.573 | 5.924% | 0.1434%
Oxford | 0 | 704 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.049 | 0 | 0.0035 | 0.036 |  | 0.004 | 0 | 0.0038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033 | 0 | 0 | 0 | 0 | 7.38 | 0.018 | 0.016 | 1.5 | 32.13 | 0 | 0 | 0.02285 | 746.9091 | 19.11% | 5.609%
RALPP | 0 | 662 | 2 | 1.1 | 0 | 0 | 0 | 0 | 0 | 842 | 0.27 | 0 | 0 | 0.14 | 0 | 0.08 | 0 | 0 | 0.03 |  | 1.8 | 0 | 305 |  | 0 | 21 | 0.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0.7 | 0 | 0 | 0 | 0.65 | 1837.42 | 47% | 1.547%
Sussex |  | 44.626 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [9 empty] | 45.636 | 1.167% | 2.213%
Total | 446 | 1856.426 | 2.11 | 1.2 | 0.376 | 0.058 | 0 | 0 | 0 | 1227.111 | 0.341 | 0 | 0.049 | 0.73 | 0 | 0.149 | 0 | 0.3715 | 0.096 | 0 | 2.314 | 0 | 305.4968 | 0 | 0 | 21 | 0.59 | 0 | 0 | 1.21 | 0 | 0 | 0 | 0.083 | 0 | 0 | 1 | 0 | 7.38 | 0.018 | 0.046 | 2.2 | 32.13 | 0 | 0 | 0.69285 | 3909.1781 | 100% | 1.897%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q4 2017
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | 0.5 | 0.5 | 0.5
Bristol | Winnie Lacesso |  |  |  | 0.2 | 0.2 | 0.2
Luke Kreczko
Cambridge
| John Hill |  |  |  | 0.5 | 0.5 | 0.5
Oxford
| Vip Davda | 0.5 | 0.5 | 0.5
| Kashif Mohammad | 0.5 | 0.5 | 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris |  |  |  | 0.1 | 0.1 | 0.1
| Leo Rojas |  |  |  | 0.4 | 0.4 | 0.4
Total |  | 2.1 | 2.1 | 2.1 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q4 2017
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Transfer to VAC is now complete. Only two nodes powered by CREAM/Torque for SAM tests and these are planned to be shifted soon as well. Completed install of an EOS instance with two storage boxes for ALICE which is now under testing. Still some stability issues to work out but working well. Have made progress in getting IPv6 addresses from the University in order to start testing dual stack. Upgraded the gird site link to 20Gb/s. |  | No major issues this quarter.
Bristol | Only VERY brief Site outage to move Bristol LCG & DICE hardware within HPC machine room to consolidate in one locale (vs being split all over the room) upcoming replacement for main LCG/DICE switch will be paid for by IT Services :) New switches will have SDN capabilities if GridPP is interested new GPU development node opened to first testers |  | . Severe site staff shortage .. IT Networks has lost interest in deploying perfsonar, back to us
Cambridge | DPM upgraded to 1.9.0 (legacy mode). Migration to VAC ~80% complete. Added NA62 VO to VAC. HEP_OSlibs updated to 1.1.2. cvmfs upgraded to 2.4.4 |  | How to move A/R tests to VAC? Trust Anchors 1.88 update caused some disruption.
Oxford | New CPU ordered. BRO and MISP installed. CentOS7 ARC CE installed with two C& WNs. (t2ce00) Testing underway prior to migration of more WNs.
RALPP | Orders placed for additional storage and CPU Firewall bypass link upgraded from 2x10 (active-passive) to 2x20 Argus nodes reinstalled as C7 |  | New PerfSONAR node still not working, blocking issue on deploying IPv6
Sussex | Last quarter availability figures are the best on recent 12 months, we just have a couple of incidents due to some general HPC issues but otherwise we are currently running a stable number of multi-core jobs. We are checking 2 old 64-core nodes to decide if they should be decomissioned so we are currently running nearly 100 multicore jobs instead of 140. We solved the issue that prevented us to run dirac test jobs. It was a conflict on our CE which somehow had some bdii-site code running when it is only a bdii-resource node, after getting rid of bdii-site packages and reinstalling the bdii-resource packages, dirac test jobs started to run fine. This bdii conflict fix, also made it possible to properly published our site capacity on RBUS, since the dbii conflict was preventing us to publish any of the SubClusters. Now this is working fine too. |  | Xrootd server was recreated from scratch from a vanilla SL6 install, since the old provisioning system provoked some repo incompatibilities (repos installed where basically out of date) and the final image did not support our LustreFS. Now the xrootd service is starting fine on the new server so we are waiting from ITS to open the ports on the central firewall to test it. I'm still collecting information to perform the service nodes migration to a different existent VM physical host machine.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern. |  | Recruitment ongoing at Sussex.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Purchase new hardware with GridPP Allocation |  | 31/09/2017 |  | Order placed
Bristol: First deployment of kubernetes |  | 2017-12-31 |  | Fail mainly due to severe site staff shortage & needing help from outside (e.g. Andrew Lahiff)
Bristol: Roll out new IPv4 and IPv6 network to bypass university firewall |  | 12/31/2017 |  | Probably even higher SE bandwidth? Fail mainly due to Severe site staff shortage & lack of interest from IT Networks
Bristol: Work together with IT services to deploy new perfsonar hosts |  | 12/31/2017 |  | hosts up + running Fail mainly due to Severe site staff shortage & lack of interest from IT Networks
Bristol: Add support for LZ, lsst, & DUNE Vos |  | 2017-07-31 |  | pass tests for these VOs. (Success as of 05/07/2017)
Bristol: LCG & hdfs nodes will physically consolidate from being scattered amongst 6 racks in HPC MachineRoom, to 3 adjacent. We may be able to shutdown & swiftly move & rerack nodes in batches so no major outage; planning in progress. |  | 2017-07-31 |  | all Bristol LCG & hdfs nodes up + running in new racks/location
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Deploy IPv6 to Storage Gateways |  | 2018-03-31
RALPP: Deploy New Hardware |  | 2018-03-31
RALPP: Upgrade site-bdii to C7 |  | 2018-03-31
RALPP: Add support for additional Vos |  | 2018-03-31
Bristol: First deployment of kubernetes |  | 2019-12-31 |  | Run HTCondor and Apache Spark on kubernetes
Bristol: SL7 WN in production (for compute - they already do HDFS |  | 2018-04-01 |  | SL7 WN running jobs
Bristol: New IPv6 perfsonar hosts |  | 2018-04-01 |  | hosts up + running
Bristol: DICE Phase5 +5 10Gb-NIC WN = 34-36 jobslots/ea, 40TB disk(20TB net)/ea |  | 2018-04-01 |  | hardware arrived & budgets spent!
Bristol: New network gear installed & configured |  | 2018-04-01 |  | hardware arrived & all machines migrated
Sussex |  | 2017-08-31 |  | XrootD front end
Sussex |  | 31/09/2017 |  | Migration of service nodes into a new virtual machine host server
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop