## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q118 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 305.8% | 305.8% | 305.8% | 281.5% | 281.5% | 388.2% | 233.5% | 352.1% | 352.1% | 151.9% | 151.9% | 151.9% |  |  |  | 232.7% | 272.3% | 305.2%
.x.2 | % of promised (by that time) CPU available | 100% | 363.3% | 363.3% | 363.3% | 275.9% | 275.9% | 275.9% | 375.1% | 375.1% | 375.1% | 450.5% | 450.5% | 450.5% |  |  |  | 339.2% | 339.2% | 339.2%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 99% | 100% | 100% | 99% | 87% | 87% | 100% | 96% | 96% |  |  |  | 99.5% | 95.75% | 95.75% | QMUL down
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 100% | 99% | 100% | 100% | 99% | 87% | 87% | 100% | 96% | 96% |  |  |  | 99.5% | 95.75% | 95.75% | QMUL down
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 57.91% | 79.4% | 73.97% | 88.36% | 84.07% | 87.42% | 85.13% | 81.14% | 82.89% | 98.38% | 94.97% | 205% |  |  |  | 84.23% | 85.15% | 109.3%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 41.47% | 54.92% | 57.54% | 81.25% | 71.03% | 74.26% | 85.13% | 81.14% | 82.89% | 84.49% | 78.09% | 52.88% |  |  |  | 75.13% | 71.94% | 68.64%
.x.3/.4
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q118
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2018 Jan | 2018 Feb | 2018 Mar | Total |  |  | 2018 Jan | 2018 Feb | 2018 Mar | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 17741502.1351 | 13681142.5797 | 12078513.9513 | 43501159 |  | UKI-LT2-Brunel | 23109822.1106 | 17921564.8103 | 14891053.0448 | 55922440
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 32036255.2168 | 28649016.0157 | 36290294.8296 | 96975566 |  | UKI-LT2-IC-HEP | 38080719.1689 | 35714443.7368 | 40364275.5085 | 114159438
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 25419421.9118 | 28322162.7515 | 27480404.998 | 81221990 |  | UKI-LT2-QMUL | 25419406.2842 | 28322168.044 | 27480049.7311 | 81221624
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 9779464.7776 | 16578553.3216 | 17047353.9514 | 43405372 |  | UKI-LT2-RHUL | 28108715.2741 | 120212552.8419 | 19953009.837 | 168274278
[8 empty] | UKI-LT2-UCL-HEP | 820728.7106 | 606278.7431 | 810730.591 | 2237738 |  | UKI-LT2-UCL-HEP | 877147.7359 | 784397.9526 | 1056335.2866 | 2717881
[8 empty] | Total | 85797373 | 87837153 | 93707298 | 267341824 |  | Total | 115595811 | 202955127 | 103744723 | 422295661
[8 empty] | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normcpu/SITE/DATE/2017/10/2017/12/all/localinfrajobs/ | [5 empty] | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normelap_processors/SITE/DATE/2017/10/2017/12/all/onlyinfrajobs/
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1400 | 9632.812 | 457.8006 | 363.3% | 305.8% | 19.57% | 10.77% | 43501159 | 16.41% | 2160 | 75600000 | 57.54% | 73.97% | 77.79%
UKI-LT2-IC-HEP | 60456 | 5100 | 21915.766 | 1313.8219 | 275.9% | 388.2% | 33.81% | 39.23% | 96975566 | 36.58% | 2160 | 130584960 | 74.26% | 87.42% | 84.95%
UKI-LT2-QMUL | 45363 | 5001 | 12094.921 | 1420.211 | 375.1% | 352.1% | 25.37% | 38.47% | 81221990 | 30.64% | 2160 | 97984080 | 82.89% | 82.89% | 100% | Slurm accounting problem whereby CPU time = wall time
UKI-LT2-RHUL | 38000 | 1500 | 8434.349 | 987.6466 | 450.5% | 151.9% | 21.25% | 11.54% | 43405372 | 16.37% | 2160 | 82080000 | 52.88% | 205% | 25.79% | RHUL accounting problem
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 178819 | 13001 | 52714.598 | 4260.48 | 339.2% | 305.2% | 100% | 100% | 265104087 | 100% | 2160 | 386249040 | 68.64% | 109.3% | 63.31%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | rebus | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 4673 | 55842 | 1399
UKI-LT2-IC-HEP | 5718 | 56664 | 4988
UKI-LT2-QMUL | 4248 | 46797 | 5029
UKI-LT2-RHUL | 3824 | 38312 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 197615 | 12876
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q118
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cepc | cernatschool.org | comet.j-parc.jp | cms | dteam | dune | dzero | enmr.eu | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | icecube | ilc | ipv6.hepix.org | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | neiss.org.uk | ops | pheno | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.gear.cern.ch | vo.helio-vo.eu | vo.landslides.mossaic.org |  | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 16
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 20
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 22
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 17
Total | 0 | 4 | 4 | 2 | 0 | 1 | 3 | 1 | 4 | 4 | 4 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 3 | 1 | 4 | 0 | 4 | 3 | 3 | 4 | 1 | 0 | 4 | 4 | 4 | 1 | 0 | 0 | 4 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | 75
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | lsst | cernatschool.org | solidexperiment.org | vo.moedal.org | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.278 |  | 0.385 |  |  |  | 0.072 | 967 |  | 31 | 0.017 | 0.002 |  |  |  |  | 1.491 | [5 empty] | 0.544 | 0.007 |  |  |  |  | 0.202 | [6 empty] | 0.018 |  | 0 |  |  | 0 |  |  | 1001.016 | 10.66% | 0.3013%
UKI-LT2-IC-HEP |  | 28.3 | 0 |  | 0 |  | 0 | 2473.067 |  | 9.761 |  |  |  |  | 289.005 |  |  |  | 0 | [15 empty] | 36.652 |  |  | 320 |  |  | 169.765 |  | 71.125 | 3397.675 | 36.18% | 18.42%
UKI-LT2-QMUL |  | 132 | 0.809 |  |  | 0 |  | 3.3 |  | 3500 | 0.052 |  |  |  | 199 |  | 0.673 | 0.0068 |  |  |  | 0.016 | 0.069 | 0.011 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 11 |  |  |  | 0 | 0.109 | 0.073 | 0 | 0.042 |  | 3847.185 | 40.97% | 3.766%
UKI-LT2-RHUL | 0 |  | 0.5 |  |  |  |  | 1.621 |  | 1142 | 0.015 | 0.001 |  |  |  |  | 0.19 | [5 empty] | 0.006 | 0.014 | [6 empty] | 0.009 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 1144.356 | 12.19% | 0.06423%
Total | 0.278 | 160.3 | 1.694 | 0 | 0 | 0 | 0.072 | 3444.988 | 0 | 4682.761 | 0.084 | 0.003 | 0 | 0 | 488.005 | 0 | 2.354 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.619 | 0.032 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.009 | 0 | 0.019 | 11 | 36.652 | 0.018 | 0 | 320 | 0.109 | 0.073 | 169.765 | 0.042 | 71.125 | 9390.232 | 100% | 8.248%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q118
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.85 | 0.85 | 0.85 | 0.15 | 0.15 | 0.15
| Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
| P. Hobson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| B.Green/Tom | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 6.9 | 6.9 | 6.9 | 1.85 | 1.85 | 1.85

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q118
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel
UKI-LT2-IC-HEP | 170 TB Solid data already on site. Taking part in LZ Mock Data Challenge2 - data being copied to NSERC.
UKI-LT2-QMUL | New storage has been filled up by ATLAS. Testing our storage frontend (se03 /storm). Brought new Dell R440 compute servers (Intel Gold 5118, 48 HT cores, 192 GB RAM) Gave talk at Pre GDB on "QMULs GPUs on the grid". Have set up a number of Centos 7 development nodes for system services and worker node. Continued development of our new deployment system. We can now have a resilient (2 node) solution which can redeploy itself as well as basic sl6/centos7 nodes. Working on ansible playbooks and migration of core services (dhcp/dns/nis/ntp...) to these nodes. Attended remotely the atlas site jamboree at cern. Begun investigation of possible provision of hadoop / spark services via the grid. Submitted abstract to chep2018 about running hadoop/spark at a wlcg grid site contributed to abstract by hepix ipv6 working group to chep2018 about ipv6 deployment
UKI-LT2-RHUL | New equipment under testing.
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes