## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q1 2018 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 114.9% | 114.9% | 114.9% | 72.92% | 72.92% | 72.92% | 134.5% | 134.5% | 134.5% | 186.7% | 186.7% | 186.7% | 189.4% | 189.4% | 189.4% | 155.6% | 155.6% | 155.6% | 145.5% | 145.5% | 145.5%
.x.2 | % of promised (by that time) CPU available | 100% | 232.2% | 232.2% | 232.2% | 366.5% | 366.5% | 366.5% | 301% | 328.2% | 328.2% | 338.7% | 384.2% | 384.2% | 272.6% | 272.6% | 272.6% | 1522% | 1522% | 1522% | 302.3% | 314.1% | 314.1%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 80% | 88.7% | 96.34% | 98% | 98.6% | 99.58% | 100% | 97.9% | 99.86% | 99.97% | 98.07% | 91.42% | 96% | 99.79% | 98.18% | 90% | 89.8% | 87.63% | 94% | 95.48% | 95.5%
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 80% | 88.7% | 96.63% | 100% | 100% | 100% | 100% | 97.9% | 99.86% | 99.97% | 98.07% | 93.75% | 99% | 99.79% | 99.79% | 90% | 89.8% | 87.63% | 94.83% | 95.71% | 96.28%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 45.35% | 53.58% | 51.54% | 39.49% | 44.92% | 32.26% | 84.52% | 87.86% | 90.26% | 84.29% | 73.47% | 69.93% | 83.78% | 86.08% | 75.56% | 81.74% | 68.93% | 71.37% | 73.11% | 72.93% | 66.66%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 37.41% | 46.6% | 42.44% | 30.4% | 39.61% | 25.07% | 70.65% | 76.02% | 78.66% | 52.83% | 45.56% | 62.3% | 63.35% | 61.7% | 54.46% | 63.25% | 44.38% | 56.96% | 53.67% | 53.08% | 53.35%
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html
summarised here | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2018
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2018-01-01 | 2018-02-01 | 2018-03-01 | Total |  | Site | 2018-01-01 | 2018-02-01 | 2018-03-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 5917870.0872 | 5231741.0321 | 4427800.142 | 15577411 |  | Birmingham | 7327145.3769 | 6696943.2109 | 4895790.0368 | 18919878.6246
Cambridge | UMD 4/SL6 or C7 | UMD 4/SL6 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.0 |  | Bristol | 2958312.5999 | 1727364.2772 | 3298929.9654 | 7984607 |  | Bristol | 3747074.1817 | 2688726.589 | 3839015.2519 | 10274816.0226
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.2 |  | Cambridge | 5449013.8017 | 5063405.1873 | 5051198.221 | 15563617 |  | Cambridge | 6310396.2066 | 5914297.9527 | 5633707.779 | 17858401.9383
RALPP | UMD3/4 | UMD3 |  | 10Gb/s | 10Gb/s | Dcache 2.13.51 |  | Oxford | 15696192.8809 | 13625877.6895 | 15666952.8491 | 44989023 |  | Oxford | 17459496.6687 | 16163580.4877 | 16873090.1574 | 50496167.3138
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 18039139.7054 | 19341033.3252 | 17083072.5255 | 54463246 |  | RALPP | 25787749.1221 | 26176321.6535 | 23597864.9971 | 75561935.7727
[8 empty] | Sussex | 2166471.4555 | 2317187.7947 | 2386478.3203 | 6870138 |  | Sussex | 3345556.7655 | 2627339.7064 | 2634967.55 | 8607864.0219
[8 empty] | Total CPU hrs | 50227000.5306 | 47306609.306 | 47914432.0233 | 145448041.8599 |  | Total | 63977418.3215 | 60267209.6002 | 57474435.7722 | 181719063.6939
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | efficiency
Birmingham | 16994 | 920 | 7319 | 801 | 232.2% | 114.9% | 13.46% | 17.02% | 15577411 | 10.71% | 2160 | 36707040 | 42.44% | 51.54% | 82.33%
Bristol | 14744 | 560 | 4023 | 768 | 366.5% | 72.92% | 11.68% | 10.36% | 7984607 | 5.49% | 2160 | 31847040 | 25.07% | 32.26% | 77.71%
Cambridge | 9160 | 265 | 2791 | 197 | 328.2% | 134.5% | 7.258% | 4.903% | 15563617 | 10.7% | 2160 | 19785600 | 78.66% | 90.26% | 87.15%
Oxford | 33432 | 980 | 8701 | 525 | 384.2% | 186.7% | 26.49% | 18.13% | 44989023 | 30.93% | 2160 | 72213120 | 62.3% | 69.93% | 89.09%
RALPP | 46300 | 2610 | 16985 | 1378 | 272.6% | 189.4% | 36.68% | 48.29% | 54463246 | 37.45% | 2160 | 100008000 | 54.46% | 75.56% | 72.08%
Sussex | 5584 | 70 | 367 | 45 | 1522% | 155.6% | 4.424% | 1.295% | 6870138 | 4.723% | 2160 | 12061440 | 56.96% | 71.37% | 79.81%
Totals | 126214 | 5405 | 40186 | 3714 | 314.1% | 145.5% | 100% | 100% | 145448042 | 100% | 2160 | 272622240 | 53.35% | 66.66% | 80.04%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken |  | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Birmingham |  | 0 |  |  | Birmingham | 22433 | 980
Bristol |  | 0 |  |  | Bristol | 9607 | 0
Cambridge |  | 0 |  |  | Cambridge | 5940 | 293
Oxford |  | 0 |  |  | Oxford | 26240 | 940
RALPP |  | 0 |  |  | RALPP | 42840 | 3079
Sussex |  | 0 |  |  | Sussex | 2006 | 83
Totals |  | 0 | 0 | 0
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D30: gronbech: Sussex may have promised 2000 by email.?
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2018
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 12
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 21
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 0 | 1 | 1 | [6 empty] | 5
[46 empty] | 0 | 0
[46 empty] | 0 | 0
Total | 5 | 6 | 0 | 2 | 3 | 3 | 1 | 1 | 2 | 5 | 6 | 1 | 2 | 2 | 0 | 3 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 2 | 2 | 2 | 1 | 0 | 0 | 4 | 1 | 1 | 6 | 3 | 1 | 0 | 0 | 1 | 3 | 6 | 1 | 0 | 2 | 0 | 0 | 4 | 102
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
Birmingham | 103.5 | 227.6 | 0.11 | 0.1 | 0.28 | 0.01 | 0 | 0 | 0 | 0.001 | 0.01 |  | 0 | 0 | 0 | 0.02 | 0 | 0.16 | 0.03 |  | 0.51 | 0 | 0.05 |  |  | 0 | 0 | 0 | 0 | 1.37 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 333.791 | 9.653% | 0.7909%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 11.11% | 0.001822%
Cambridge | 0 | 219.8 | 0 | 0 | 0.096 | 0.024 | 0 | 0 | 0 | 0 | 0.004 |  | 0 | 0 | 0 | 0 | 0 | 0.208 | 0 |  | 0 | 0 | 0.441 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.573 | 6.378% | 0.1505%
Oxford | 0 | 704 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.049 | 0 | 0.0035 | 0.036 |  | 0.004 | 0 | 0.0038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033 | 0 | 0 | 0 | 0 | 7.38 | 0.018 | 0.016 | 1.5 | 32.13 | 0 | 0 | 0.02285 | 746.9091 | 21.6% | 5.609%
RALPP | 0 | 572 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 786 | 0.25 | 0 | 0 | 0.14 | 0 | 0.08 | 0 | 0 | 0.03 |  | 1.6 | 0 | 331 |  | 0 | 31 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0.7 | 0 | 0 | 0 | 0.65 | 1727.06 | 49.94% | 2.204%
Sussex |  | 44.626 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [9 empty] | 45.636 | 1.32% | 2.213%
Total | 103.5 | 1768.026 | 2.11 | 1.1 | 0.376 | 0.058 | 0 | 0 | 0 | 1171.111 | 0.321 | 0 | 0.049 | 0.73 | 0 | 0.149 | 0 | 0.3715 | 0.096 | 0 | 2.114 | 0 | 331.4968 | 0 | 0 | 31 | 0.55 | 0 | 0 | 1.37 | 0 | 0 | 0 | 0.083 | 0 | 0 | 1 | 0 | 7.38 | 0.018 | 0.046 | 2.2 | 32.13 | 0 | 0 | 0.69285 | 3458.0781 | 100% | 2.427%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2018
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | 0.5 | 0.5 | 0.5
Bristol | Winnie Lacesso |  |  |  | 0.2 | 0.2 | 0.2
Luke Kreczko
Cambridge
| John Hill |  |  |  | 0.5 | 0.5 | 0.5
Oxford
| Vip Davda | 0.5 | 0.5 | 0.5
| Kashif Mohammad | 0.5 | 0.5 | 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris |  |  |  | 0.1 | 0.1 | 0.1
| Leo Rojas |  |  |  | 0.4 | 0.4 | 0.4
Total |  | 2.1 | 2.1 | 2.1 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q1 2018
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Finished commissioning EOS for ALICE who are now using that exclusively. In the process of decommissioning the old XRootD storage and transferring it. Have made progress in setting up EOS for ATLAS use. Made good progress on rearranging/consolidating the server room to improve air flow. Have got IPv6 addresses from IT and will be testing dual stack very soon. |  | Had power and aircon issues which took us down for a few days in total.
Bristol | SL7 PerfSONAR BW in production but it turns out to be on a network on which ITServices won't enable IPv6. Replacements for main LCG/DICE switch arrived but IT Services is N weeks behind in deploying :-/ New switches will have SDN capabilities if GridPP is interested 5 new 40TB (20TB net/ea) Hadoop/HDFS wn ordered & arrived, not in production yet Previous 2 new WN had 10GB BaseT(copper) NICs replace with SFP+ |  | Site staff shortage not improving :[ Need to move PerfSONAR host to other network or choose other hardware already on that network & need PerfSONAR LAT New (relativly) superheavyduty Dell GridFTP I/O server logging hardware errors =:o
Cambridge | Reinstall UI with officially-released CentOS 7 version. All remaining WNs moved to VAC, except for small number of old servers which will be decommissioned. SE and pool nodes upgraded to DPM 1.9.2/xrootd 4.8.1.Reinstall perfSonar 4.0.2 on CentOS 7. |  | Still need to understand if and how to move SAM tests to VAC.
Oxford | Installed Dell 6420 'Twin squared' Intel 5115 based worker nodes. (~10.1.18) DPM upgraded to 1.9.2, solved long standing webdav access.(Jan 2018) Oxford Networking replace the router/switch connecting Oxford to JANET, which improved single threaded transfer tests dramatically. (24.1.18) |  | A/C issues in February caused reduced capcity on Sunday 25th Feb and 1st March. Decommissioned the Oxford VAC site.
RALPP | New PerfSONAR Node reistalled from Image, is now working, next step is to bring IPv6 to it. IPv6 now set up as far as Tier 2 Router
Sussex | Last quarter availability figures are the best on recent 12 months, we just have a couple of incidents due to some general HPC issues but otherwise we are currently running a stable number of multi-core jobs. We are checking 2 old 64-core nodes to decide if they should be decomissioned so we are currently running nearly 100 multicore jobs instead of 140. We solved the issue that prevented us to run dirac test jobs. It was a conflict on our CE which somehow had some bdii-site code running when it is only a bdii-resource node, after getting rid of bdii-site packages and reinstalling the bdii-resource packages, dirac test jobs started to run fine. This bdii conflict fix, also made it possible to properly published our site capacity on RBUS, since the dbii conflict was preventing us to publish any of the SubClusters. Now this is working fine too. |  | Xrootd server was recreated from scratch from a vanilla SL6 install, since the old provisioning system provoked some repo incompatibilities (repos installed where basically out of date) and the final image did not support our LustreFS. Now the xrootd service is starting fine on the new server so we are waiting from ITS to open the ports on the central firewall to test it. I'm still collecting information to perform the service nodes migration to a different existent VM physical host machine.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern. |  | Recruitment ongoing at Sussex.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Purchase new hardware with GridPP Allocation |  | 31/09/2017 |  | Hardware arrived
Bristol: First deployment of kubernetes |  | 2018-04-01 |  | Fail mainly due to severe site staff shortage & needing help from outside (e.g. Andrew Lahiff)
Bristol: SL7 WN in production (for compute - they already do HDFS |  | 2018-04-01 |  | Fail mainly due to severe site staff shortage & fail-build issues with stacki-sl7, trying to do complicated with docker/singularity etc
Bristol: New IPv6 perfsonar hosts |  | 2018-04-01 |  | .5Fail (only new BW host) because network not & will not be IPv6-enabled
Bristol: DICE Phase5 +5 10Gb-NIC WN = 34-36 jobslots/ea, 40TB disk(20TB net)/ea |  | 2018-04-01 |  | SUCCESS hardware arrived & budgets spent!
Bristol: New network gear installed & configured |  | 2018-04-01 |  | Fail due to waiting on overstretched IT Networks
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Deploy IPv6 to Storage Gateways |  | 2018-03-31 |  | Ongoing - IPv6 at T2 Router
RALPP: Deploy New Hardware |  | 2018-03-31 |  | Ongoing - Hardware Delivered 25/3/18
RALPP: Upgrade site-bdii to C7 |  | 2018-03-31 |  | Ongoing
RALPP: Add support for additional Vos |  | 2018-03-31 |  | Ongoing
Bristol: First deployment of kubernetes |  | 2018-01-07 |  | Run HTCondor and Apache Spark on kubernetes
Bristol: SL7 WN in production (for compute - they already do HDFS |  | 2018-01-07 |  | SL7 WN running jobs
Bristol: New IPv6 perfsonar hosts |  | 2018-01-07 |  | hosts up + running
Bristol: DICE Phase5 +5 10Gb-NIC WN = 34-36 jobslots/ea, 40TB disk(20TB net)/ea in production |  | 2018-01-07 |  | Net +100TB storage & 5 new 10GB SL7 WN running jobs
Bristol: New network gear installed & configured |  |  |  | hardware arrived & all machines migrated
Sussex |  | 2017-08-31 |  | XrootD front end
Sussex |  | 31/09/2017 |  | Migration of service nodes into a new virtual machine host server
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop