## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | ATLAS |  |  | Close to target
Year | 2017 |  |  | Not OK
Reported by | Roger Jones |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Q416 | Q117 | Q217 | Q317 | Q417 | Comment Q116 | Comment Q216 | Comment Q316 | Comment Q416 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417
1.5.1 | Tier 1 -Required hardware deployed |  | Roger Jones | Requested share, dymanic
1.5.2 | Tier 1 - Job success rates from ATLAS dashboard |  | Roger Jones | 0.95 | 0.983 | 0.991 | 0.997 | 0.974 | 0.949 | 0.978 | 0.939 | 0.938
1.5.3 | Tier 1 - Data availability from ATLAS dashboard |  | Roger Jones | 0.98 | 0.965 | 0.957 | 0.973 | 0.976 | 0.968 | 0.915 | 0.948 | 0.95 |  |  |  |  | This just fails the metric because the echo service is included and has lower efficiency |  |  | Problems with Castor
1.5.4 | Tier 1 - Data acceptance from Tier-0/1/2 - ATLAS SAM tests |  | Roger Jones | 0.98 | 0.986 | 0.993 | 0.999 | 0.973 | 0.968 | 0.98 | 0.96 | 0.95 |  |  |  | Some brokeroff periods |  |  | New data source from ATLAS; pulled down by transfers to ECHO | Broker-off periods for PANDA queue merger
1.5.5 | Tier 1 - Data loss |  | Roger Jones | 0.01 | [14 empty] | Significant loss from ECHO | Data loss from Castor
2.1.1 | Tier 2 - Requested disk space deployed |  | Roger Jones | Requested share, dynamic
2.1.2 | Tier 2 - Production job success rates |  | Roger Jones | 0.95 | 0.915 | 0.958 | 0.969 | 0.964 | 0.938 | 0.99 | 0.925 | 0.943 | [7 empty] | Numbers pulled down fro ScotGrid by Durham having a sub 90% rate
2.1.3 | Tier 2 - Data availability from the ATLAS dashboard |  | Roger Jones | 0.95 | 0.933 | 0.93 | 0.954 | 0.929 | 0.941 | 0.963 | 0.955 | 0.972
2.1.4 | Tier 2 - Data acceptance |  | Roger Jones | 0.95 | 0.952 | 0.958 | 0.976 | 0.974 | 0.971 | 0.96 | 0.91 | 0.965 | [6 empty] | This is pulled down by a low data acceptance in SouthGrid; (Oxford)
2.1.5 | Tier 2 - Data loss |  | Roger Jones | 0.05 | [9 empty] | There was a significant irretrievable data loss at Glasgow due to a RAID card failure | An excellent quarter in terms of data loss - literally half a dozen, all of which were recovered.
2.1.6 | Tier 2 - ATLAS Available slots |  | Roger Jones | Requested share, dynamic
2.1.7 | Tier 2 - Atlas job success in production |  | Roger Jones |  |  |  |  | 0.964 |  |  | 0.925 | 0.943
2.1.8 | Tier 2 - ATLAS job success rate in user analysis |  | Roger Jones | 0.95 | 0.941 | 0.93 | 0.969 | 0.916 | 0.922 | 0.92 | 0.926 | 0.956 | This is pulled dpwn by Sussex and Birmingham (65%and 82% availability respectively) | This is considerably depressed by problems at RALPP (72% success rate) | Birmingham and Sussex reamin low. ECDF is also below 90% | ECDF had some analysis loss because of a problem in the ATLAS Jobmover. | Problems at Lancaster (where misconfigured jobs requested too much RAM) and Oxford for short periods | This is artificailly low because of a large number of miscomnfigured user jobs with very high memory requiremetns sent to one site.Hammercloud confirmed the site was not at fault | Still lwo because of misconfigured jobs to lancs and RHUL
Note on B16: gronbech: site only metric from PANDA dashboard
Note on B18: gronbech: via the Steve Lloyd page folded with the available storage (Peter Love page)
Note on B19: gronbech: Cedric's page

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | ATLAS |  |  | Overdue
Year | 2017 |  |  | Not yet due
Reported by | Roger Jones |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
A5.6 | Report to PMB on delivery during the year | Roger Jones | 2016-12-01 | 2016-12-01 | OC Docs for Nov + PG Review SS
A5.7 | Report to PMB on delivery during the year | Roger Jones | 2017-12-01 | 2018-02-02 | OC Docs for Nov + PG Review SS
A5.8 | Report to PMB on delivery during the year | Roger Jones | 2018-12-01
A5.9 | Report to PMB on delivery during the year | Roger Jones | 2019-12-01

## Manpower Q1 2017
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1 | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q2 2017
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1 | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q3 2017
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1 | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q4 2017
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1 | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q216
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2016
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Project managing new disk only storage at RAL Echo. IPv6 deployment planning - For both ATLAS and WLCG in general. Arranging summer placements (5 proposed, 3 arranged). Attended ATLAS software week as well as site Jamboree at CERN. Also addressed ALICE long term stoarge issues at RAL and operational issues such as lost tape-based data at RAL and RHUL data lossed during migration. |  | - Echo project management - S3 / Event service development/testing - IPv6 only CPU deployment strategy - ADC review (I was one of the reviewers) - Various squid/Frontier monitoring improvements - Attended ADC TIM and CHEP days at CERN, as well as CVMFS workshop at RAL. - LocalGroupDisk management including requesting improvements from Rucio developers.
Operations | Generally good performance in T2s, but some T3 or near T3 sites (Sussex, Bham) pull the averages down. The T1 was having increasing networking issues. |  | Generally good performance at T2s, though some isses at RALPP. There are growing concerns over the absence of dedicated T1 manager; the workload is being spread over the team, to the detriment of development activities, which may have a downstream impact on operations.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DC14 production |  | Sliding (external delay) |  | Smooth operations, feedback on new systems

## Narrative Q316
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2016
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Alastair has been working on the ipV6 only CPU plan for WLCG and ATLAS, and proejct managing the Echo aprt of the Ceph plan. He also supervised summer students on Ceph. |  | The majority of his time is currently on Tier 1 issues, not specificially ATLAS. It would help if a clear plan was in place for the Tier 1 responsibilities, with roles filled, so the ATLAS specific work can also be planned in a coherent fashion.
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q416
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2016
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | IP v6 migration. Attended CHEP. But mainly worked on ECHO |  | It is good that the exepriment contact drive so many of the T1 developments, but it woujdl help if they set the direction and more effort from the rest of the team took it forward, leaving more time for the experiment links to look at the experiment side.
Operations | Attended and presentat at CHEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q117
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2017
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Worked mainly on the echo installation; the remaining time was on ipv6 and Frontier issues
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q217
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2017
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | - Echo was a very large percentage of his work (as it entered production this quarter). - Quite a bit of work on was done on IPv6 stuff at the Tier 1. - He contributed to DynaFed and testing storage on Microsoft Azure. - WLCG Workshop in Manchester (He gave presentation on both Object Stores and IPv6 [tutorial]) - He attended ATLAS Software week in Valencia and did related work on Object Stores for the Event Service - He has been contributing to the WLCG data steering group, especially with respect to storage accounting. - Also did some work to help setup LIGO on S3. |  | While it is not a problem, and genrally useful to ATLAS, the level of non-ATLAS specific effort is high and could become a problem if ATLAS problems arise.
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q317
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2017
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | August was taken with holiday and paternity leave. Object store benchmarking for ATLAS; presentation and preparation for pre-GDB on object stores. Project management for Echo; project management training.
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q417
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2017
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Echo Project management, ipv6 deployment, some work on Object Stores for ATLAS, large scale CVMFS+DynaFed
Operations | Good work on data recovery after Castor losses |  | Castor data loss, some more minor Echo problems. Alastair had a period of illneess
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
CAP | 2011-
DPHEP Management group | 2012-
Other outputs and Knowledge | Date | Notes