## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | CMS |  |  | Close to target
Year | 2017 |  |  | Not OK
Reported by | Dave Colling |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q316 | Q416 | Q117 | Q217 | Comment Q3 | Comment Q4 | Comment Q117 | Comment Q217
1.6.1 | Data Transfer quality | PhEDEx | Dave Colling | As needed by CMS | OK | OK | OK | OK | This will generally be OK but will flagged as not OK if a backlog builds up.
1.6.2 | Timely and efficient availability and use of resources at RAL T1 |  | Dave Colling |  | OK | OK | Not ideal – worst cpu effeciency of any T1 in CMS. Best is ~90% whereas RAL is below 70%. Work in progress | Not ideal, worst CPU efficiency (~65%) of any CMS T1 (other than T1-RU-JINR and we don’t in their league) | CMS usage was capped during this period, however those available resources were efficientyly available.. There were also job efficiency issues but these were of CMS’ making. |  | There are investigations in place as to why the CMS use of the T1 has not been as efficient as at other T1 centres. Previously this was put down to multicore pilot jobs and one particular workflow. However further scratching has shown that these are only a small part of the effect and so searches are being carried out. | See comments in main report.
1.6.3 | Data Loss at Tier-1 |  | Dave Colling |  | OK | OK | OK | OK | This will generally be OK but will flagged as not OK if custodial data is lost.
1.6.4 | Site availability at the Tier-1 | 90% | Dave Colling | 97% | 99% | OK | 90% for April, which is below 97% target, but still OK. | Not ideal, worst reliability and availabilty of all CMS T1s (around 90% averaged over the quarter) |  |  |  | See comments in main report.
1.6.5 | Data availability via AAA |  | Dave Colling |  | Almost | OK | OK | OK | Had some problems during this period. This is being worked upon.
1.6.6 | CMS Fraction of Tier-1 work carried out at RAL |  | Dave Colling | 8% |  |  | 7.9% | 8.2% | Not Great | Between 6.8% and 13% depending on how measured
2.2.1 | Transfer rates to the UK Tier 2s |  | Dave Colling |  |  | OK | OK | OK
2.2.2 | Site availability at the Tier-2s |  | Dave Colling | 80% | 77% - Bristol, 98% RALPP, 99% Brunel, 100% Imperial | Bristol 90%, RALPP ~93%, Imperial 100%, Brunel 95% | Bristol 93%, RALPP78%, Brunel 98%, Imperial 100% | Bristol 96%, RALPP 87%, Brunel 99%, Imperial 100% |  |  |  | These numbers are a by eye average over 3 monthly reports
2.2.3 | Site readiness at the Tier-2s |  | Dave Colling | 80% | 79% - Bristol, 98% RALPP, 89% Brunel, 100% Imperial | Bristol 93%, RALPP 89%, Brunel 100%, Imperial 100% | Bristol 93%, RALPP78%, Brunel 98%, Imperial 100% | Bristol 96%, RALPP 87%, Brunel 99%, Imperial 100% |  |  |  | These numbers are a by eye average over 3 monthly reports
2.2.4 | Unique data loss at Tier-2s |  | Dave Colling |  | OK | OK | OK | OK | This is generally OK unless data is lost.
2.2.5 | Failed analysis jobs |  | Dave Colling |  | 30% on average across all UK sites | 35% | 30% | 38% | This seems high but is not abnormal. It appears that about 1/3 of the failures are down as site failure. I don’t really know what a good target is here have marked as OK for now. This will evolve. | not good
2.2.6 | Failed production jobs |  | Dave Colling |  | 32% | 12% failed, 10% unknown | 11% | 8% | This varies greatly from site to site. The efficiency (1-fail rate) is ~85% for Imperial at one end and about 35% at Brunel.
2.2.7 | T2 sites provide an appropriate level of resource to CMS |  | Dave Colling |  | OK | 6% or 7% depending on how mentioned |  | 4.5% | Yes |  |  | Actually 4.5%
2.2.8 | AAA data transfer performance |  | Dave Colling |  | OK | OK | OK | Good | Worked very well | Just fine |  | Have linked all UK data and installed UK re-director

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | CMS |  |  | Overdue
Year | 2017 |  |  | Not yet due
Reported by | Dave Colling |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
1.6.9 | Report to PMB on delivery during the year | Dave Colling | 2016-12-01 | 2016-12-01 | OC Docs | OC Docs plus experiment review SS
1.6.10 | Report to PMB on delivery during the year | Dave Colling | 2017-12-01 |  | OC Docs
1.6.11 | Report to PMB on delivery during the year | Dave Colling | 2018-12-01 |  | OC Docs
1.6.12 | Report to PMB on delivery during the year | Dave Colling | 2019-12-01 |  | OC Docs

## Manpower Q2 2016
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q3 2016
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q4 2016
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q1 2017
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Manpower Q2 2017
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Narrative Q2 2016
GridPP Quarterly Report
Area | CMS
Year | 2016
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Lots of cloud stuff
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q3 2016
GridPP Quarterly Report
Area | CMS
Year | 2016
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Lots of cloud stuff and some container stuff
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q4 2016
GridPP Quarterly Report
Area | CMS
Year | 2016
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Andrew was very effective this quarter, especially interesting was his work running CMSjobs on different cloud infrastructures.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q1 2017
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Andrew left CMS (although still contributes(. A replacement is being sought.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q2 2017
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.