## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q217 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 616% | 781% | 889.5% | 210% | 249% | 249.1% | 176% | 176% | 240.1% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 253.8%
.x.2 | % of promised (by that time) CPU available | 100% | 2589% | 2589% | 3365% | 215% | 215% | 215% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 655.4%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 99% | 98.9% | 100% | 87% | 84% | 100% | 90% | 90.12% | [9 empty] | 100% | 99% | 99%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 99% | 98.9% | 100% | 90% | 84% | 100% | 91% | 90.56% | [9 empty] | 100% | 99% | 99%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 71% | 91% | 80.38% | 38% | 63% | 79.92% | 73% | 82% | 75.19% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 69% | 68% | 77.57%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 70% | 91% | 80.39% | 34% | 55% | 74.01% | 55% | 62% | 62.71% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 52% | 59% | 70.42%
ECDF: Availablity low due to problems with ARGO site monitoring (-1% availability). Dashboard issues are covered in GGUS #126349 and #128294
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q217
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2017-04-01 | 2017-05-01 | 2017-06-01 | Total |  | Site | 2017-04-01 | 2017-05-01 | 2017-06-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 23096880 | 28661928 | 28231217 | 79990025 |  | DURHAM | 23075137 | 28693788 | 28207658 | 79976583
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 7756985 | 4664014 | 3742333 | 16163332 |  | ECDF | 8511645 | 4981668 | 3962121 | 17455434
[8 empty] | GLASGOW | 23550427 | 30884804 | 32730598 | 87165829 |  | GLASGOW | 31309132 | 36236808 | 36963886 | 104509826
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 54404292 | 64210746 | 64704148 | 183319186 |  | Total | 62895914 | 69912264 | 69133665 | 201941843
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2016) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 1354 | 39 | 3365% | 889.5% | 38.22% | 6.223% | 79990025 | 43.63% | 2184 | 99503040 | 80.39% | 80.38%
ECDF | 10000 | 1345.339 | 4652 | 540 | 215% | 249.1% | 8.389% | 24.13% | 16163332 | 8.817% | 2184 | 21840000 | 74.01% | 79.92%
GLASGOW | 63643 | 3882 | 12181 | 1617 | 522.5% | 240.1% | 53.39% | 69.64% | 87165829 | 47.55% | 2184 | 138996312 | 62.71% | 75.19%
Totals | 119203 | 5574.239 | 18187 | 2196 | 655.4% | 253.8% | 100% | 100% | 183319186 | 100% | 2184 | 260339352 | 70.42% | 77.57%
Please check the figures in the Yellow
| MoU figures taken from 2016 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q217
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q217
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Oliver Smith | 0 | 0 | 0 | 0 | 0 | 0
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | R. Currie | 0 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 3 | 3.5 | 3.5 | 0.5 | 0.5 | 0.5
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q217
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Additional node hardware installed. Efforts to maximise rack space due to restrictions on physical space available. We have begun migrating our service nodes to SL7, we have completed the BDII, ARGUS, a test CE and a DPM disk pool server. |  | Small loss of files due to issue during disk drain. Hardware failure caused loss of monitoring and some logging for two days.
ECDF | Hiring of new GridPP data management post. (Will add something more here) |  | Opportunistic use on shared cluster has not been as effective as in Q117
GLASGOW | Migrated ARGUS to CentOS7/VM, installation and commisioning of new tranche HW. |  | Accounting issue identified with VAC nodes, a bug cause multi-core jobs to be accounted at 8x their actual HEPSPEC value
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Unclear performance impact on using of RDF disk in production environment. Temporary loss of resident storage expertise due to Marcus Ebert leaving |  | Working with RDF team to understand any unexpected outages and performance considerations. Rob Currie documenting and covering site storage operations
Glasgow: Air Condition/power issues leading to damaged equipment |  | Working with E&B to supply new data facility, now scheduled for Aug 2017
Durham: DISK! Our local VO home space disk server has chewed up and spat out a couple of disks meaning it was showing some performance issues; along with said server deciding to RAID scrub while it was undergoing a ZFS resilver. |  | Asked the server to play nicely as well as giving it nice shiney new disks and disabling RAID verify/scrub for the (single disk) arrays. There was no noticable impact on the cluster.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Continue deployment of pakiti for UK NGI Security Team |  | 2017-06-30 |  | In progress; test service being developed
Glasgow: Deploy internal CA |  | 2017-06-30 |  | Superseded by use of existing services: completed
Glasgow: Deploy internal elasticsearch cluster |  | 2017-06-30 |  | Priority changed to establishing new virtualisation platform (oVirt)
Durham: Trial Docker/Containers |  | 2017-06-30 |  | Trial continues, but project on hold due to staff member loss
Durham: Install new nodes |  | 2017-06-30 |  | Nodes installed, HS06 increased
ECDF: Openstack migration |  | 2017-06-30 |  | Stalled. Current openstack solution is still working fine but some issues remain with wider deployment that need resolving
ECDF: Singularity evaluation on Eddie3 and Tier-2 HPC |  | 2017-08-30 |  | Work ongoing. Some discussion with Archer and Cirrus administrators
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Deploy oVirt virtualisation platform |  | 2017-09-30
ECDF: MISP content sharing |  | 2017-09-30 |  | No progress made so far but still intention to help with UK work
ECDF: Ainsible based deployment of ARC and/or DPM(legacy) |  | 2017-08-30
Durham: Migrate remaining grid services to SL7 (excluding nodes) |  | 2017-08-30
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Marcus Ebert (and replacement) 50% LUSC DAC Team.
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
HEPSYSMAN (WLCG Workshop security session) |  | 2017-06-15 |  | David Crooks
HEPSYSMAN (Glasgow Site Report) |  | 2017-06-15 |  | David Crooks
WLCG Workshop (Security & Trust) |  | 2017-06-19 |  | David Crooks (convener)
HEPSYSMAN talks on setting up HV at Edinburgh and site summary |  | 13,15/6/2017 |  | Rob Currie
Organisation of 2nd ATLAS merge request tutorial, CERN |  | 2017-04-20 |  | Andrew Washbrook
Organisation of 2nd Intel/Openlab code optimisation workshop, CERN |  | 3-5/5/2017 |  | Andrew Washbrook
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Traceability & Isolation WG |  | Present |  | David Crooks
WLCG SOC Working Group |  | Present |  | co-lead by David Crooks
EGI Software Vulnerability Group |  | Present |  | David Crooks
UK NGI Security Team |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A