## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q317 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW | [11 empty] | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 616% | 781% | 221% | 210% | 249% | 243.7% | 176% | 176% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 2589% | 2589% | 270.6% | 215% | 215% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 256%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 99% | 99% | 98.9% | 87% | 84% | 91.85% | 90% | 99% | 99.61% | [9 empty] | 100% | 99% | 96.79%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 99% | 99% | 98.9% | 90% | 84% | 91.85% | 91% | 99% | 99.61% | [9 empty] | 100% | 99% | 96.79%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 71% | 91% | 79.54% | 38% | 63% | 46.33% | 73% | 82% | 108.3% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 69% | 68% | 92.1%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 70% | 91% | 79.75% | 34% | 55% | 47.4% | 55% | 62% | 90.47% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 52% | 59% | 82.76%
ECDF: Availablity low due to problems with ARGO site monitoring (-1% availability). Dashboard issues are covered in GGUS #126349 and #128294
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q317
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2017-07-01 | 2017-08-01 | 2017-09-01 | Total |  | Site | 2017-07-01 | 2017-08-01 | 2017-09-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 27284787 | 28731407 | 24207403 | 80223597 |  | DURHAM | 27232977 | 28687284 | 24092103 | 80012364
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 3678233 | 3488625 | 3299035 | 10465893 |  | ECDF | 4117018 | 2692367 | 3420106 | 10229491
[8 empty] | GLASGOW | 70337875 | 30090124 | 26704643 | 127132642 |  | GLASGOW | 78584436 | 38255061 | 35326561 | 152166058
[12 empty] | 0 | [5 empty] | 0
[12 empty] | 0 | [5 empty] | 0
[12 empty] | 0 | [5 empty] | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 101300895 | 62310156 | 54211081 | 217822132 |  | Total | 109934431 | 69634712 | 62838770 | 242407913
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 38.22% | 6.223% | 80223597 | 36.83% | 2208 | 100596480 | 79.75% | 79.54%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 8.389% | 24.13% | 10465893 | 4.805% | 2208 | 22080000 | 47.4% | 46.33%
GLASGOW | 63643 | 3882 | 22034 | 1987 | 288.8% | 195.4% | 53.39% | 69.64% | 127132642 | 58.37% | 2208 | 140523744 | 90.47% | 108.3%
Totals | 119203 | 5574.239 | 46556 | 2696 | 256% | 206.8% | 100% | 100% | 217822132 | 100% | 2208 | 263200224 | 82.76% | 92.1%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q317
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q317
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | R. Currie | 0 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 3 | 3.5 | 3.5 | 0.5 | 0.5 | 0.5
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q317
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Various services have been migrated to SL7. After power issues (See issues) the cluster is back to correct performance. |  | Power Issues within the datacentre caused a complete unexpected power cut to the cluster. Power was restored but only 50-60% of the nodes were available due to a hardware failure of a network switch. Network switch repaired which restored the cluster to the correct availablity, capacity and performance. Oliver Smith left the team and so there's only one systems admin for both the Cluster and the Local group.
ECDF | Teng Li joined the team in our joint GridPP data management / LSST post. Finished deploying test dpm instance for Atlas use (now being used by dynafed developers @ CERN) Migrated production systems back to Hypervisors. |  | Opportunistic use on shared cluster has not been as effective as in Q1 and Q2 17 in part due to scheduling issue of jobs to our new openstack resources. Aim to scale up our cloud resources over the quarter. Deploying instances of dpm can be tricky esp as moving to Centos7. Mitigated by writing detailed notes and preparing ainsible playbooks which are documented. Past performance problems with Hypervisors have been mitigated and the redeployment has been documented. Minor risk as still on ZFS 0.7.0 but can be mitiagated with a software update during an intervention.
GLASGOW | Deployed containerised Worker Nodes and successfully ran ATLAS Multicore payloads. Upgrade storage for Bro installation to use remote storage. Deployed new instance of MISP. |  | Problems with Disk configuration for LHCb left us unavailable for part of this quarter impacting our overall availabilty and reliability.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Unclear performance impact on using of RDF disk in production environment. Lack of control of the computing cluster can expose fragile parts of grid MW. Older out of warranty storage starting to fail over time. |  | Met with RDF team and will have greater visibility into outage schedule. Will insulate storage access through new DPM service to avoid outage contagion for the rest of the site. Good communication with Research Services at Edinburgh to plan for and reduce impact of potential changes to site/scheduler. Have increased redundancy at cost of space and regenerated older ZFS pools to reduce risk of data loss.
Glasgow: Air Condition/power issues leading to damaged equipment |  | Working with E&B to supply new data facility, now scheduled for Aug 2017
Durham: Only a single system admin. |  | Updating site documentation and offline password list incase of any unforseen circumstances.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Deploy oVirt virtualisation platform |  | 2017-09-30 |  | First phase installation complete and in production
ECDF: MISP content sharing |  | 2017-09-30 |  | No progress made so far but still intention to help with UK work
ECDF: Ainsible based deployment of ARC and/or DPM(legacy) |  | 2017-08-30 |  | No progress yet, have prototype storage-node/generic grid-middleware playbook which will be expanded to deploy additional dpm head/storage nodes for site including for RDF storage use.
ECDF: Test DPM deployment |  | 2017-08-30 |  | Ongoing/Finished with the dpm being advertised to Atlas.
Durham: Migrate remaining grid services to SL7 (excluding nodes) |  | 2017-08-30 |  | Ongoing, only a few services left to migrate.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Deploy development elasticsearch instance |  | 2017-12-31 |  | Reporting at Scotgrid Technical Meeting
ECDF: Openstack migration |  | 2017-12-31 |  | Stalled. Current openstack solution is still working fine but wider deployment method still being tested (including Cloudscheduler)
ECDF: Singularity evaluation on Eddie3 and Tier-2 HPC |  | 2017-12-31 |  | Work ongoing. Have access to Cirrus and example containers from ATLAS
ECDF: Initial testing of Atlas with RDF storage |  | 2017-12-31 |  | Deploying RDF for atlas to test system performance ahead of expanding RDF quota to 750Tb. This will effect how we intend to manage exposing 750Tb on 1 filesystem to ATLAS
ECDF: Investigation and testing of XRootD Caching |  | 2017-12-31 |  | Will build a XRootD caching test-bed on top of Openstack WNs, to see if everything works properly and how is the performance
ECDF: Ainsible deployment of DPM |  | 2017-12-31 |  | Will expand grid-middleware playbook to deploy DPM storage/head nodes on VM and test servers
Durham: Migrate remaining grid services to SL7 (excluding nodes) |  | 2017-12-31 |  | All services will be on SL7 with no noticable downtime/issues.
Durham: Second System Admin |  | 2017-12-31 |  | There will be another person.
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team.
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
Further Funding (eg external grants) |  | Date |  | Notes
N/A
Destination of ex staff and recruitment issues |  | Date |  | Notes
Oliver Smith leaving for Gibraltar and William Hill |  | 2017-08-28 |  | Durham supported by Adam Boutcher
Dissemination events |  | Date |  | Notes
CERN IT Technical Forum, Manchester Workshop report, Security & Trust (slide preparation/given by proxy) |  | 2017-07-07 |  | David Crooks
GDB, Manchester Workshop report, Security & Trust (slide preparation/given by proxy) |  | 2017-07-12 |  | David Crooks
"Continuous software quality analysis for the ATLAS experiment", 18th International Workshop on Advanced Computing and Analysis Techniques in Physics Research (ACAT 2017), Seattle, USA |  | 2017-08-22 |  | Andrew Washbrook
"Continuous software quality analysis for the ATLAS experiment", Workshop on Sustainable Software for Science: Practice and Experiences (WSSSPE5.1) Manchester, UK |  | 2017-09-06 |  | Andrew Washbrook
A container model for resource provision at a WLCG Tier-2 (ACAT 2017), Seattle, USA |  | 21-25/8/2017 |  | Gareth Roy
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Traceability & Isolation WG |  | Present |  | David Crooks
WLCG SOC Working Group |  | Present |  | co-lead by David Crooks
EGI Software Vulnerability Group |  | Present |  | David Crooks
UK NGI Security Team |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A