## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q417 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 616% | 781% | 221% | 210% | 249% | 243.7% | 176% | 176% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 2589% | 2589% | 270.6% | 215% | 215% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 256%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 99% | 99% | 100% | 84% | 92% | 91.85% | 90% | 100% | 99.61% | [9 empty] | 99% | 99% | 97.15%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 99% | 99% | 100% | 84% | 92% | 91.85% | 91% | 100% | 99.61% | [9 empty] | 99% | 99% | 97.15%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 71% | 91% | 81.98% | 38% | 63% | 43.79% | 73% | 82% | 74.96% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 69% | 68% | 76.71%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 70% | 91% | 82.06% | 34% | 55% | 41.68% | 55% | 62% | 50.81% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 52% | 59% | 61.99%
ECDF: Availablity low due to problems with ARGO site monitoring (-1% availability). Dashboard issues are covered in GGUS #126349 and #128294
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q417
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total |  | Site | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 29614630 | 27601524 | 25334283 | 82550437 |  | DURHAM | 29585877 | 27585546 | 25301330 | 82472753
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 3310543 | 3229750 | 2661773 | 9202066 |  | ECDF | 3447809 | 3347659 | 2872743 | 9668211
[8 empty] | GLASGOW | 22698172 | 24724967 | 23980664 | 71403803 |  | GLASGOW | 34160996 | 36726108 | 34453692 | 105340796
[8 empty] | ECDF-CS [1,2] |  | 533000 | 1937000 | 2470000 |  | ECDF-CS [1,2] |  | 1271000 | 3161000 | 4432000
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 55623345 | 56089241 | 53913720 | 165626306 |  | Total | 67194682 | 68930313 | 65788765 | 201913760
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 38.22% | 6.223% | 82550437 | 50.6% | 2208 | 100596480 | 82.06% | 81.98%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 8.389% | 24.13% | 9202066 | 5.64% | 2208 | 22080000 | 41.68% | 43.79%
GLASGOW | 63643 | 3882 | 22034 | 1987 | 288.8% | 195.4% | 53.39% | 69.64% | 71403803 | 43.76% | 2208 | 140523744 | 50.81% | 74.96%
Totals | 119203 | 5574.239 | 46556 | 2696 | 256% | 206.8% | 100% | 100% | 163156306 | 100% | 2208 | 263200224 | 61.99% | 76.71%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
[1] New Cloud scheduler service run on ECDF openstack (~400 cores). In future this will be integrated into a single ECDF resource.
[2] Values are not available in EGI accounting at present. CPU and walltime data are available at https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CondorHeprcAccounting and https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CernAccounting

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q417
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q417
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Durham | Paul Clark | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | R. Currie | 0 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 3 | 3.5 | 3.5 | 0.5 | 0.5 | 0.5
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q417
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Onboarded a new member of staff (Paul Clark). |  | Job Session directory that is used by CE2, CE3 and CE4 was at 100% usage due to poorly written jobs which caused a brief failure of those CE's. This was resolved by liasing with the user to develop better code/jobs.
ECDF | Deployment of Cloud Scheduler on our Eddie Openstack allocation. Now continually running ATLAS jobs on 25 VMs (400 cores) |  | Scheduling issues remain for getting workload run on non-GridPP ringfenced cluster nodes. Time required to maintain older storage servers with failing drives has been reduced after some minor investigations and change in policy to check disks remotely before visiting ACF to replace drive in production.
GLASGOW | Initial meeting of the governance board regarding construction of Data Centre at Glasgow. Construction to commence Q1-2018. |  | Loss of data due to failure of Disk041 during the period between Christmas and New Years. Data reported lost to Atlas.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Operational continuity concerns with upcoming machine room server move. Out of warranty network switch |  | Regular meetings with University Research Services to formulate smooth machine room change. Request for new switch equipment pending
Glasgow: Air Condition/power issues leading to damaged equipment |  | New Data Centre commences construction in Jan 2018
Durham: Only a single system admin with Grid knowledge. |  | Training up other admin.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Deploy development elasticsearch instance |  | 2017-12-31 |  | Completed: development instance deployed to test secure access
ECDF: Openstack migration |  | 2017-12-31 |  | Ongoing: Cloud scheduler work is complete. Now looking to wind down SL6 cloud instances and increase number of VMs
ECDF: Singularity evaluation on Eddie3 and Tier-2 HPC |  | 2017-12-31 |  | Ongoing: demonstrated use of Singularity on Cirrus (HPC). Not clear if same can be done on Tier-2 cluster due to dependency on legacy batch system.
ECDF: Initial testing of Atlas with RDF storage |  | 2017-12-31 |  | Ongoing: ATLAS not keen on multi-SE at a single site. Focus on exposing RDF to other communities and potentially raise storage available on main cluster to atlas.
ECDF: Investigation and testing of XRootD Caching |  | 2017-12-31 |  | Completed; We have investigated XRootD proxy cache, deployed a XRootD proxy cache test-bed server and had some initial studies and tests on it.
ECDF: Ainsible deployment of DPM |  | 2017-12-31 |  | Ongoing: Still persuing a pure DPM ainsible playbook with a view to deploying dpm 1.10 with it soon once it's in testing.
Durham: Migrate remaining grid services to SL7 (excluding nodes) |  | 2017-12-31 |  | Ongoing; Unable to migrate the remaining services without causing major downtime and/or do not have alternative hardware at the moment to progress sealessly.
Durham: Second System Admin |  | 2017-12-31 |  | Completed; We now have Paul Clark.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Deploy development MISP/Bro integration |  | 2017-03-31 |  | ISGC presentation
Durham: Researching and Developing an OpenShift Origin Cluster to investigate it's viability in the GRID environment. |  | 2017-03-31 |  | A working test environment that can then be developed on futher.
Durham: Research, Develop and eventually deploy a shared Fail2Ban System |  | 2017-03-31 |  | A working shared Fail2Ban system, with a guide on how to replicate.
Durham: 10Gb/s Network Connectivity *Optimistic Date* |  | 2017-03-31 |  | We will have a faster internet connection.
ECDF: Deploying and testing XCache server |  | 2017-03-31 |  | We will work with XRootD and AGIS developers to put XCache server into production and have performance studies.
ECDF: HPC performance evaluation |  | 2017-03-31 |  | Validate ATLAS workload on Cirrus and run scaling tests to compare performance with Archer (container-based solution should be better performance)
ECDF: Documentation Drive |  | 2017-03-31 |  | Full review of site configuration and best practices based on existing material contained in site Gitlab wiki
ECDF: Deploy DPM testing instance for WLCG |  | 2017-03-31 |  | Provide a DPM service which is available for deployment testing which will be used to test 1.10 at the site.
ECDF: ZFS performance studies |  | 2017-03-31 |  | On the back of performance studies looking at the impact of spectre/meltdown fixes on ZFS systems collect information on best practices for testing ZFS performance and enhance monitoring to look for bottlenecks.
ECDF: Openstack Service |  | 2017-03-31 |  | Scale up VMs for cloud scheduler and wind down SL6 queue
EVAL Notes
Publications |  | Date |  | Notes
David Crooks and Liviu Vâlsan, "WLCG Security Operations Centres Working Group" |  | 2017-12-06 |  | Published in Proceedings of Science, volume 293
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team.
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
Further Funding (eg external grants) |  | Date |  | Notes
Microsoft RSE Cloud Computing Award |  | 2017-12-01 |  | (Andrew Washbrook) 1 year travel money + Microsoft Azure compute site for PaaS development
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
GDB, SOC Workshop Full Announcement |  | 2017-11-08 |  | David Crooks
University of Glasgow CoSE Networking: Threat Intelligence Sharing |  | 2017-11-30 |  | David Crooks
WLCG SOC WG Workshop |  | 11,12/12/2017 |  | David Crooks
GDB, SOC Workshop Summary |  | 2017-12-13 |  | David Crooks
Software Quality Update |  | 2017-12-13 |  | Andrew Washbrook
LHCb Trigger/Operations Update |  | 2017-11-17 |  | Robert Currie
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Traceability WG [was Traceability & Isolation] |  | Present |  | David Crooks
WLCG SOC Working Group |  | Present |  | co-lead by David Crooks
EGI Software Vulnerability Group |  | Present |  | David Crooks
UK NGI Security Team |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A