## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q218 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 305.8% | 305.8% | 305.8% | 281.5% | 388.2% | 388.2% | 352.1% | 352.1% | 352.1% | 151.9% | 151.9% | 131.6% |  |  |  | 272.3% | 305.2% | 300.5%
.x.2 | % of promised (by that time) CPU available | 100% | 363.3% | 363.3% | 363.3% | 275.9% | 275.9% | 275.9% | 375.1% | 375.1% | 375.1% | 450.5% | 450.5% | 604.7% |  |  |  | 339.2% | 339.2% | 363.9%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 97% | 100% | 100% | 99% | 87% | 87% | 99% | 96% | 96% | 94% |  |  |  | 95.75% | 95.75% | 97.25% | QMUL and RHUL low
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 97% | 100% | 100% | 100% | 87% | 87% | 99% | 96% | 96% | 94% |  |  |  | 95.75% | 95.75% | 97.5% | QMUL and RHUL low
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 79.4% | 73.97% | 77.99% | 84.07% | 87.42% | 87.21% | 81.14% | 82.89% | 75.55% | 94.97% | 205% | 63.14% |  |  |  | 85.15% | 109.3% | 76.82%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 54.92% | 57.54% | 54.22% | 71.03% | 74.26% | 74.74% | 81.14% | 82.89% | 75.55% | 78.09% | 52.88% | 53.82% |  |  |  | 71.94% | 68.64% | 65.63%
.x.3/.4
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q218
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2018 Apr | 2018 May | 2018 Jun | Total |  |  | 2018 Apr | 2018 May | 2018 Jun | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 6249681.0944 | 16770197.0627 | 18425733.3756 | 41445612 |  | UKI-LT2-Brunel | 7845987.3661 | 23635178.5058 | 28132852.0813 | 59614018
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 34080368.2553 | 32229440.2679 | 32378494.7402 | 98688303 |  | UKI-LT2-IC-HEP | 39230930.9578 | 37373927.3636 | 38543523.481 | 115148382
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 22009681.4357 | 26093722.8933 | 26745272.0948 | 74848676 |  | UKI-LT2-QMUL | 22009411.7096 | 26093722.9911 | 26745271.0402 | 74848406
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 22641788.2063 | 16359866.327 | 20944788.2578 | 59946443 |  | UKI-LT2-RHUL | 26481464.9079 | 20418209.3809 | 23425825.4694 | 70325500
[8 empty] | UKI-LT2-UCL-HEP | 777793.7685 | 740954.1033 | 149756.3078 | 1668504 |  | UKI-LT2-UCL-HEP | 867217.8087 | 817585.1977 | 203586.409 | 1888389
[8 empty] | Total | 85759313 | 92194181 | 98644045 | 276597538 |  | Total | 96435013 | 108338623 | 117051058 | 321824695
[8 empty] | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normcpu/SITE/DATE/2017/10/2017/12/all/localinfrajobs/ | [5 empty] | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normelap_processors/SITE/DATE/2017/10/2017/12/all/onlyinfrajobs/
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1400 | 9632.812 | 457.8006 | 363.3% | 305.8% | 18.25% | 10.94% | 41445612 | 15.08% | 2184 | 76440000 | 54.22% | 77.99% | 69.52%
UKI-LT2-IC-HEP | 60456 | 5100 | 21915.766 | 1313.8219 | 275.9% | 388.2% | 31.52% | 39.84% | 98688303 | 35.9% | 2184 | 132035904 | 74.74% | 87.21% | 85.71%
UKI-LT2-QMUL | 45363 | 5001 | 12094.921 | 1420.211 | 375.1% | 352.1% | 23.65% | 39.07% | 74848676 | 27.22% | 2184 | 99072792 | 75.55% | 75.55% | 100% | Slurm accounting problem whereby CPU time = wall time
UKI-LT2-RHUL | 51000 | 1300 | 8434.349 | 987.6466 | 604.7% | 131.6% | 26.59% | 10.16% | 59946443 | 21.8% | 2184 | 111384000 | 53.82% | 63.14% | 85.24%
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 191819 | 12801 | 52714.598 | 4260.48 | 363.9% | 300.5% | 100% | 100% | 274929034 | 100% | 2184 | 418932696 | 65.63% | 76.82% | 85.95%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | rebus | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 5852 | 69931 | 1399
UKI-LT2-IC-HEP | 5718 | 56664 | 4965
UKI-LT2-QMUL | 4248 | 46797 | 5031
UKI-LT2-RHUL | 4624 | 48121 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 221513 | 12855
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q218
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cepc | cernatschool.org | comet.j-parc.jp | cms | dteam | dune | dzero | enmr.eu | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | icecube | ilc | ipv6.hepix.org | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | neiss.org.uk | ops | pheno | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.gear.cern.ch | vo.helio-vo.eu | vo.landslides.mossaic.org | skatelescope.eu | vo.londongrid.ac.uk |  | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 16
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 21
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 23
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 17
Total | 0 | 4 | 4 | 2 | 0 | 1 | 3 | 1 | 4 | 4 | 4 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 3 | 1 | 4 | 0 | 4 | 3 | 3 | 4 | 1 | 0 | 4 | 4 | 4 | 1 | 0 | 0 | 4 | 0 |  | 0 | 0 | 0 | 2 | 0 |  | 1 | 1 | 77
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | lsst | cernatschool.org | solidexperiment.org | vo.moedal.org | skatelescope.eu | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.278 |  | 0.388 |  |  |  | 10.601 | 888 |  | 33.469 | 0.017 | 0.002 |  |  |  |  | 1.491 | [5 empty] | 0.557 | 0.01 |  |  |  |  | 0.202 | [6 empty] | 0.018 |  | 0 |  |  | 0 |  |  |  | 935.033 | 9.671% | 1.451%
UKI-LT2-IC-HEP |  | 28.831 | 0 |  | 0 |  | 0 | 2610.062 |  | 9.761 |  |  |  |  | 336.47 |  |  |  | 0 | [15 empty] | 36.652 |  |  | 346.716 |  |  | 213.543 |  |  | 66.874 | 3648.909 | 37.74% | 18.98%
UKI-LT2-QMUL |  | 133 | 0.849 |  |  | 0 |  | 3.3 |  | 3500 | 0.052 |  |  |  | 178 |  | 0.673 | 0.0068 |  |  |  | 0.016 | 0.069 | 0.014 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 11 |  |  |  | 0 | 0.265 | 0.073 | 0 | 0.068 | 0.068 |  | 3827.478 | 39.59% | 3.819%
UKI-LT2-RHUL | 0 |  | 0.5 |  |  |  |  | 1.6 |  | 1255 | 0.015 | 0.002 |  |  |  |  | 0.19 | [5 empty] | 0.006 | 0.018 | [6 empty] | 0.009 | 0 | [5 empty] | 0 |  |  | 0 |  |  |  | 1257.34 | 13% | 0.05885%
Total | 0.278 | 161.831 | 1.737 | 0 | 0 | 0 | 10.601 | 3502.962 | 0 | 4798.23 | 0.084 | 0.004 | 0 | 0 | 514.47 | 0 | 2.354 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.632 | 0.042 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.009 | 0 | 0.019 | 11 | 36.652 | 0.018 | 0 | 346.716 | 0.265 | 0.073 | 213.543 | 0.068 | 0.068 | 66.874 | 9668.76 | 100% | 8.823%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q218
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.85 | 0.85 | 0.85 | 0.15 | 0.15 | 0.15
| Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
| P. Hobson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Govind Songara | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| B.Green/Tom | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 6.4 | 6.4 | 6.4 | 1.95 | 1.95 | 1.95

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q218
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | Implemetation of QUIC protocol. The target is to port it to iperf3 and maybe some grid tool, like gfal-copy.
UKI-LT2-IC-HEP
UKI-LT2-QMUL | Deployed 3 new AMD compute nodes (HPE DL385, CPU=AMD EPYC 7351/ 256GB RAM). Brought new racks (APC AR3300) and PDUs (Eaton eswb05 24ac) to replace failing PDUs. Continued development of our new deployment system, we now have most dhcp services have moved over and a kickstart server (cobbler) both backed by our own bespoke site database. the server can deploy basic centos 7 nodes. Work on ansible playbooks ongoing. Developed a proof of concept to do Hadoop and Spark workloads (using magpie, https://github.com/LLNL/magpie) on our cluster via grid submission for poster presentation at CHEP2018. Tested new version of StoRM (1.11.13) for wlcg roll out.
UKI-LT2-RHUL | - GridPP funded FTE dropped from 1.0 to 0.5 at start of April - Hardware purchase from Dell: 10x C6420, dual Xeon Gold 6148, (80 hyper-cores), 9.6 kHS06 total. - Intermittent problems with time sync on SE causing storage failures, and some worker nodes. Tomcat often gets stuck on CEs - Several disk failures in old (5yo+) storage nodes which did not impact operations or data - ATLASLOCALGROUPDISK became full at the end of June and was increased. - IPV6 awaiting solution to DNS
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes