## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q2 2018 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 225% | 225% | 224.7% | 154% | 154% | 153.7% | 216% | 216% | 215.9% | 154% | 154% | 153.9% | 200.1%
.x.2 | % of promised (by that time) CPU available | 100% | 227% | 193% | 192.6% | 213% | 262% | 262.2% | 175% | 175% | 175.2% | 210% | 210% | 210.2% | 200.4%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 93% | 99% | 96% | 100% | 95% | 100% | 100% | 96% | 98% | 73% | 85% | 98% | 98%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 93% | 99% | 96% | 100% | 100% | 100% | 100% | 100% | 98% | 77% | 86% | 98% | 98%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 72% | 71% | 69.62% | 92% | 79% | 78.74% | 147% | 122% | 199.1% | 101% | 105% | 92.46% | 115.6%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 65% | 63% | 59.04% | 82% | 72% | 58.03% | 128% | 106% | 172.7% | 90% | 92% | 85.72% | 97.86%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html |  |  | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2018
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | umd4 | 10Gb/s | 10Gb/s | DPM |  | Site | 2018-04-01 | 2018-05-01 | 2018-06-01 | Total |  | Site | 2018-04-01 | 2018-05-01 | 2018-06-01 | Total
Liverpool | Umd4 | umd4 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 16584641 | 15216547 | 18701266 | 50502454 |  | Lancaster | 19888431 | 18560508 | 21108171 | 59557110
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 17174485 | 16608813 | 12070 | 33795368 |  | Liverpool | 17174485 | 16608813 | 12070055 | 45853353
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 40359045 | 46472628 | 49816198 | 136647871 |  | Manchester | 47767787 | 54121559 | 55674750 | 157564096
[7 empty] | Sheffield | 8590155 | 6586066 | 4593944 | 19770165 |  | Sheffield | 9243128 | 7109935 | 4970951 | 21324014
[7 empty] | Total CPU hrs | 74118171 | 78297988 | 68529534 | 220945693 |  | Total | 94073831 | 96400815 | 93823927 | 284298573
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2018/1/2018/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 39168 | 3074 | 20332 | 1368 | 192.6% | 224.7% | 34.78% | 36.26% | 50502454 | 20.98% | 2184 | 85542912 | 59.04% | 69.62%
Liverpool | 26664 | 1425 | 10169 | 927 | 262.2% | 153.7% | 23.68% | 16.81% | 33795368 | 14.04% | 2184 | 58234176 | 58.03% | 78.74%
Manchester | 36233 | 3448 | 20685 | 1597 | 175.2% | 215.9% | 32.17% | 40.67% | 136647871 | 56.77% | 2184 | 79132872 | 172.7% | 199.1%
Sheffield | 10560 | 531 | 5024 | 345 | 210.2% | 153.9% | 9.376% | 6.263% | 19770165 | 8.213% | 2184 | 23063040 | 85.72% | 92.46%
Totals | 112625 | 8478 | 56210 | 4237 | 200.4% | 200.1% | 100% | 100% | 240715858 | 100% | 2184 | 245973000 | 97.86% | 115.6%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 2720 | 39168 | 3074 | NA | Lancaster
Liverpool | 2498 | 26634 | 1425 | NA | Liverpool
Manchester | 6280 | 67179 | 4229 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 12298 | 143541 | 9259 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2018
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cernatschool | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hyperk.org | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | moedal | na48 | na62 | neiss | ops | pheno | planck | vo.skatelescope.eu | snoplus | solidexperiment.org | vo.sixt.cern.ch | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 |  | 0 | 1 | 0 | 1 | 0 |  | 1 | 1 |  |  | 1 |  |  | 1 |  | 16
Liverpool | 1 | 1 |  | 1 | 1 |  | 0 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 35
Manchester | 1 | 1 |  | 1 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 23
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 0 | 1 | 1 | 0 |  |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 0 | 1 |  | 18
Total | 3 | 4 | 0 | 3 | 1 | 1 | 0 | 0 |  | 3 | 4 | 1 | 1 | 1 | 2 | 1 |  | 2 | 4 | 2 | 2 |  | 2 | 4 | 1 |  | 2 | 1 | 1 | 1 | 1 |  | 4 | 3 |  | 3 | 4 |  | 1 | 4 | 2 | 2 | 4 |  | 92
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1800 | 0 | 17 | 1 | 1818 | 0.9351% | 0.9901%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3970.24 | 0.57 | 179 | 8.47 | 4266.46 | 4.196% | 4.407%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q2 2018
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | 1 | 1 | 1
| M. Doidge | 1 | 1 | 1
| P. Love |  |  |  | 0.3 | 0.3 | 0.3
Liverpool | S. Jones | 1 | 1 | 1
| R. Fay |  |  |  | 0.5 | 0.5 | 0.5
| J. Bland |  |  |  | 0.5 | 0.5 | 0.5
Manchester | A. Forti | 1 | 1 | 1
| R. Frank | 1 | 1 | 1
| A. McNab |  |  |  | 0.5 | 0.5 | 0.5
Sheffield | E. Korolkova | 0.5 | 0.5 | 0.5
Total |  | 5.5 | 5.5 | 5.5 | 1.8 | 1.8 | 1.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | 0.5 | 0.5 | 0.5
Manchester | A. Forti |  |  |  | 1 | 1 | 1

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q2
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Fire fighting and general faffing Expansion in deployment tools (ansible) Engagement in activities within GridPP and beyond | Fires fought, reliability metrics didn't take too much of a hit. More ansible roles and tools. Participation at HEPSYSMAN, WLCG SOC workshop. |  |  | Not much progress on projects this quarter. None. None.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Out of warranty dpm headnode that's starting to creek. |  |  | Move headnode to virtual infrastructure.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | New purchasing framework in place. MISP deployment Dual-stacking last few services |  |  | 30/6/18 |  | Easier purchasing of future kit MISP can be put to use Fully dual stacked site in reach.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | C7 DPM on new/virtual hardware Explore xcache and dune Expand job slots using local hardware Increase Dune etc workloads. |  |  | 2018-09-30 |  | More stable and up to date DPM Easier dune running? More jobs slots! More jobs from the “other” Vos.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q2
Reported by | Ste Jones
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Liverpool | Security New HW Migration Routine VOs DevOps support / workarounds Conferences/talks/reports IPv6 | CVE2018-1111 (dhclient) 3 x Quad Wns, 1 x DPM Headnode, New build (config control) server. Puppet 3 (complete) Updates to UMD4 (complete), Updates to C75 (Argus, BDII, DPM, ARC/Condor…), VAC3, CA and host certs, kernels, general upgrades, DUNE collaboration, review of small VO priorities, xfs→ext4, DPM 600 sec timeout work, VAC timeout work, VAC APEL work, HepSysMan (site report and ARGUS Hackathon) GridPP40 (C7 migration and manual C7 build), |  |  | VAC shows timeouts on some C7 systems. Under investigation. Delayed due to other pressing matters
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Liverpool | Deadlock issues have cropped up on our VAC nodes using the CentOS7.x systems. No definitive fix for Spectre/Meltdown on all CPUs |  |  | Doing various tests to narrow down the issue. May temporarily roll back to SL6 until resolved. Industry wide issue. Can only monitor and react.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Adoption of Ipv6, documentation Adoption of Centos7 GridPP5 HW purchases Convert site to Puppet 3 VAC Superslot/Multicore tests Research usefulness of Condor/Singularity, document baseline Test modules to implement ARC/CE HTCondor on CentOS Definitive fix for Spectre/Meltdown on all CPUs |  |  | 30/06/2018 30/06/2018 30/06/2018 30/06/2018 30/06/2018 30/06/2018 30/06/2018 30/06/2018 |  | External partners not ready (politics). Complete. Complete. Complete. Deferred for now (triage) Deferred for now (triage) Complete. External partners not ready (technical).
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Adoption of Ipv6, documentation VAC Superslot/Multicore tests Research usefulness of Condor/Singularity, document baseline Definitive fix for Spectre/Meltdown on all CPUs Find reason for VAC/C7 deadlock. Roll out RPMs for new LZ VOMS The Big Tidy Up |  |  | 30/09/2018 30/09/2018 30/09/2018 30/09/2018 30/09/2018 31/07/2018 30/09/2018 |  | Some servers on IPv6 VAC runs mcore Singularity install and runs External partners ready (technical). Fewer or zero instances. Installed and running. All lose ends neat and tidy…
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Assisting with Accounting SIG.
Other outputs and Knowledge |  |  | Date |  | Notes