## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q2 2018 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 114.9% | 114.9% | 156.2% | 72.92% | 72.92% | 178.3% | 134.5% | 134.5% | 140.2% | 186.7% | 186.7% | 191.4% | 189.4% | 189.4% | 170.1% | 155.6% | 155.6% | 189.2% | 145.5% | 145.5% | 169.1%
.x.2 | % of promised (by that time) CPU available | 100% | 232.2% | 232.2% | 248.4% | 366.5% | 366.5% | 218.9% | 328.2% | 328.2% | 308.6% | 384.2% | 384.2% | 240.4% | 272.6% | 272.6% | 239.5% | 1522% | 1522% | 206.5% | 314.1% | 314.1% | 240.6%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 88.7% | 96.34% | 96.51% | 98.6% | 99.58% | 91.15% | 97.9% | 99.86% | 99.79% | 98.07% | 91.42% | 95.39% | 99.79% | 98.18% | 99.33% | 89.8% | 87.63% | 90.91% | 95.48% | 95.5% | 95.51%
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 88.7% | 96.63% | 96.51% | 100% | 100% | 97.36% | 97.9% | 99.86% | 99.79% | 98.07% | 93.75% | 95.39% | 99.79% | 99.79% | 99.33% | 89.8% | 87.63% | 91.22% | 95.71% | 96.28% | 96.6%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 53.58% | 51.54% | 48.92% | 44.92% | 32.26% | 33.52% | 87.86% | 90.26% | 97.18% | 73.47% | 69.93% | 65.14% | 86.08% | 75.56% | 56.58% | 68.93% | 71.37% | 69.21% | 72.93% | 66.66% | 58.26%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 46.6% | 42.44% | 35.3% | 39.61% | 25.07% | 25.07% | 76.02% | 78.66% | 80.27% | 45.56% | 62.3% | 61.62% | 61.7% | 54.46% | 53.86% | 44.38% | 56.96% | 56.33% | 53.08% | 53.35% | 51.57%
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html
summarised here | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2018
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2018-04-01 | 2018-05-01 | 2018-06-01 | Total |  | Site | 2018-04-01 | 2018-05-01 | 2018-06-01 | Total
Birmingham | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | EMI-3 | EMI 3 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 4028905.1724 | 7070753.0878 | 8016679.5264 | 15577411 |  | Birmingham | 4767180.5921 | 7941114.7121 | 8882155.4215 | 21590450.7257
Cambridge | UMD 4/SL6 or C7 | UMD 4/SL6 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.0 |  | Bristol | 1375593.9738 | 2637059.2542 | 3057172.4363 | 7984607 |  | Bristol | 3233538.118 | 3444046.6386 | 3998866.4389 | 10676451.1955
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.2 |  | Cambridge | 5528897.5638 | 5970674.7734 | 5630246.5429 | 15563617 |  | Cambridge | 6188620.2276 | 6522844.8461 | 6132020.2442 | 18843485.3179
RALPP | UMD3/4 | UMD3 |  | 10Gb/s | 10Gb/s | Dcache 2.13.51 |  | Oxford | 14490662.1068 | 15269368.8868 | 13814125.9312 | 44989023 |  | Oxford | 15971712.3799 | 16284269.5428 | 15302978.1469 | 47558960.0696
Sussex | EMI2 | EMI3 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 18592150.784 | 21050186.655 | 5110756.3241 | 54463246 |  | RALPP | 25543841.2634 | 25306886.407 | 6360066.0153 | 57210793.6857
[8 empty] | Sussex | 2577089.8897 | 2599894.6401 | 2543052.1884 | 6870138 |  | Sussex | 2763082.1401 | 2866502.2 | 2811415.9539 | 8441000.294
[8 empty] | Total CPU hrs | 46593299.4905 | 54597937.2973 | 38172032.9493 | 139363269.7371 |  | Total | 58467974.7211 | 62365664.3466 | 43487502.2207 | 164321141.2884
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2018) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | job efficiency
Birmingham | 20206 | 1340 | 8136 | 858 | 248.4% | 156.2% | 15.65% | 23% | 15577411 | 10.71% | 2184 | 44129904 | 35.3% | 48.92% | 72.15%
Bristol | 14744 | 560 | 6735 | 314 | 218.9% | 178.3% | 11.42% | 9.614% | 7984607 | 5.49% | 2160 | 31847040 | 25.07% | 33.52% | 74.79%
Cambridge | 8878 | 265 | 2877 | 189 | 308.6% | 140.2% | 6.874% | 4.549% | 15563617 | 10.7% | 2184 | 19389552 | 80.27% | 97.18% | 82.59%
Oxford | 33432 | 980 | 13905 | 512 | 240.4% | 191.4% | 25.89% | 16.82% | 44989023 | 30.93% | 2184 | 73015488 | 61.62% | 65.14% | 94.6%
RALPP | 46300 | 2610 | 19329 | 1534 | 239.5% | 170.1% | 35.85% | 44.81% | 54463246 | 37.45% | 2184 | 101119200 | 53.86% | 56.58% | 95.2%
Sussex | 5584 | 70 | 2704 | 37 | 206.5% | 189.2% | 4.324% | 1.202% | 6870138 | 4.723% | 2184 | 12195456 | 56.33% | 69.21% | 81.39%
Totals | 129144 | 5825 | 53686 | 3444 | 240.6% | 169.1% | 100% | 100% | 145448042 | 100% | 2184 | 282050496 | 51.57% | 58.26% | 88.51%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | GSTAT Broken |  | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Birmingham |  | 0 |  |  | Birmingham | 22433 | 980
Bristol |  | 0 |  |  | Bristol | 9607 | 0
Cambridge |  | 0 |  |  | Cambridge | 5940 | 293
Oxford |  | 0 |  |  | Oxford | 26240 | 940
RALPP |  | 0 |  |  | RALPP | 42840 | 3079
Sussex |  | 0 |  |  | Sussex | 2006 | 83
Totals |  | 0 | 0 | 0
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
Note on D30: gronbech: Sussex may have promised 2000 by email.?
Note on D41: gronbech: Figure correct as at 30/6/2014. 80TB extra storage added 3/7/2014. Also 8TB old storage removed 9/7/2014
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2018
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 14
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 23
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 0 | 1 | 1 | [7 empty] | 5
[47 empty] | 0 | 0
[47 empty] | 0 | 0
Total | 5 | 6 | 0 | 2 | 3 | 3 | 1 | 1 | 2 | 5 | 6 | 2 | 2 | 2 | 0 | 3 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 3 | 3 | 2 | 1 | 0 | 0 | 4 | 1 | 1 | 6 | 3 | 1 | 0 | 0 | 1 | 3 | 6 | 1 | 1 | 0 | 2 | 0 | 0 | 4 | 106
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
Birmingham | 85 | 208 | 0.11 | 0.1 | 0.28 | 0.01 | 0 | 0 | 0 | 0.001 | 0.01 |  | 0 | 0 | 0 | 0.02 | 0 | 0.16 | 0.03 |  | 0.51 | 0 | 0.05 |  |  | 0 | 0 | 0 | 0 | 1.37 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.02 | 295.691 | 8.099% | 0.8928%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 10.52% | 0.001822%
Cambridge | 0 | 207.5 | 0 | 0 | 0.096 | 0.024 | 0 | 0 | 0 | 0 | 0.004 |  | 0 | 0 | 0 | 0 | 0 | 0.208 | 0 |  | 0 | 0 | 0.451 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.039 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 208.322 | 5.706% | 0.1781%
Oxford | 0 | 704 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.049 | 0 | 0.0035 | 0.036 |  | 0.004 | 0 | 0.0038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033 | 0 | 0 | 0 | 0 | 2.98 | 0.018 |  | 0.016 | 1.5 | 32.13 | 0 | 0 | 0.02285 | 742.5091 | 20.34% | 5.05%
RALPP | 0 | 640 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 947 | 0.25 | 0 | 0 | 0.14 | 0 | 0.08 | 0 | 0 | 0.03 |  | 1.6 | 0 | 314 |  | 30 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.03 | 0.7 | 1.7 | 0 | 0 | 0.65 | 1974.76 | 54.09% | 3.735%
Sussex |  | 44.626 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [10 empty] | 45.636 | 1.25% | 2.213%
Total | 85 | 1804.126 | 2.11 | 1.1 | 0.376 | 0.058 | 0 | 0 | 0 | 1332.111 | 0.321 | 0 | 0.049 | 0.73 | 0 | 0.149 | 0 | 0.3715 | 0.096 | 0 | 2.114 | 0 | 314.5068 | 0 | 30 | 35 | 0.55 | 0 | 0 | 1.37 | 0 | 0 | 0 | 0.083 | 0 | 0 | 1 | 0.039 | 2.98 | 0.018 | 0 | 0.046 | 2.2 | 33.83 | 0 | 0 | 0.69285 | 3651.0271 | 100% | 3.158%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2018
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
Bristol | Winnie Lacesso | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
Luke Kreczko
Cambridge
| John Hill | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Oxford
| Vip Davda | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| Kashif Mohammad | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| Leo Rojas | Unfunded Month 1: 0.4; Unfunded Month 2: 0.4; Unfunded Month 3: 0.4
Total |  | 2 | 2 | 2 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q2 2018
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Fully decommissioned ALICE xrootd storage and moved it over to EOS. ATLAS are almost ready to have use EOS in production. Completed the server room rearrangement/recabling. Got IPv6 working on gateway and perf sonar, now waiting on central IT to allow IPv6 DNS assignments. |  | An aircon failure has meant we have been running for on very few workers for 2 months. This should be fixed very soon.
Bristol | SL7 PerfSONAR BW in production but it turns out to be on a network on which ITServices won't enable IPv6. Replacements for main LCG/DICE switch installed less 1 48-port 1Gbps switch to move last of non-10GB DICE WN off old switch :-/ Phase 4 of 11 new WN had 1Gb NIC replace with 10GB SFP+ NICs |  | Site staff shortage not improving :[ Need to move PerfSONAR host to other network or choose other hardware already on that network & need PerfSONAR LAT New (relativly) superheavyduty Dell GridFTP I/O server logging hardware errors =:o Staff shortage in IT Networks delaying install of last needed switch to finally move off old switch Not all WN have iDRAC subnet enabled yet & no subnet security yet on new switch! =:o 5 new 40TB (20TB net/ea) Hadoop/HDFS wn not in production yet (staff shortage) One earlier Phase WN dead, can't seem to revive DICE WN disks aging = more disk errors = require more frequent hadoop maintenance :[
Cambridge | VAC now upgraded to v3.0.1 on CS7. Re-benchmarked WNs at the same time. skatelescope.eu now can use multicore on VAC. Increase control_idle_timeout to 7200 (from 600) to help with gridftp transfers. |  | Still need to understand if and how to move SAM tests to VAC. Instabilities with VAC3 on CS7 (especially with singlecore factories) to be understood.
Oxford | Added support for the DUNE and solid VO's.
RALPP | IPv6 Added to the PerfSONAR node, IPv6 works though the node now has problems storing results Problems with GridFTP on hosts with IPv4 and IPv6 on different interfaces means we need to rethink out deployment plan. New plan now going through change control 560TB new disk deployed, 380TB old DIsk retired 12 New WNs (192 slots@11.39 = ~6.5kHS06) installed as C7 Queues to be added next Quarter.
Sussex | Last quarter availability figures are the best on recent 12 months, we just have a couple of incidents due to some general HPC issues but otherwise we are currently running a stable number of multi-core jobs. We are checking 2 old 64-core nodes to decide if they should be decomissioned so we are currently running nearly 100 multicore jobs instead of 140. We solved the issue that prevented us to run dirac test jobs. It was a conflict on our CE which somehow had some bdii-site code running when it is only a bdii-resource node, after getting rid of bdii-site packages and reinstalling the bdii-resource packages, dirac test jobs started to run fine. This bdii conflict fix, also made it possible to properly published our site capacity on RBUS, since the dbii conflict was preventing us to publish any of the SubClusters. Now this is working fine too. |  | Xrootd server was recreated from scratch from a vanilla SL6 install, since the old provisioning system provoked some repo incompatibilities (repos installed where basically out of date) and the final image did not support our LustreFS. Now the xrootd service is starting fine on the new server so we are waiting from ITS to open the ports on the central firewall to test it. I'm still collecting information to perform the service nodes migration to a different existent VM physical host machine.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol: First deployment of kubernetes |  | 2018-07-01 |  | Partly/limited implemented
Bristol: SL7 WN in production (for compute - they already do HDFS |  | 2018-07-01 |  | limited access for local users - grid soon
Bristol: New IPv6 perfsonar hosts |  | 2018-07-01 |  | .5Fail (only new BW host) because network not & will not be IPv6-enabled
Bristol: DICE Phase5 +5 10Gb-NIC WN = 34-36 jobslots/ea, 40TB disk(20TB net)/ea IN PRODUCTION |  | 2018-07-01 |  | Defered due to stacki-sl7 complications
Bristol: New network gear installed & configured |  | 2018-07-01 |  | Partial success, major new network components installed+config'd (with serious teething problems!)
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Deploy IPv6 to Storage Gateways |  | 2018-03-31 |  | Ongoing - IPv6 at T2 Router
RALPP: Deploy New Hardware |  | 2018-03-31 |  | Ongoing - Hardware Delivered 25/3/18
RALPP: Upgrade site-bdii to C7 |  | 2018-03-31 |  | Ongoing
RALPP: Add support for additional Vos |  | 2018-03-31 |  | Ongoing
Bristol: Upgrade to HTCondor 8.6 |  | 2018-12-31 |  | SL7 container jobs (via jobrouter)
Bristol: New IPv6 perfsonar hosts |  | 2018-01-12 |  | hosts up + running
Bristol: Completion of task = network gear installed & configured |  | 2018-07-12 |  | All hardware arrived & configured (including security!) & all machines migrated
Sussex |  | 2017-08-31 |  | XrootD front end
Sussex |  | 31/09/2017 |  | Migration of service nodes into a new virtual machine host server
EVAL Notes
Publications |  | Date |  | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine |  | 2012-10-15 |  | Followed from an interview with Pete Gronbech (Project Manager)
Collaborations |  | Date |  | Notes
CAMONT |  |  |  | Cambridge/Birmingham?
VoxTox/Accel-RT |  | starting 09/12 |  | Cambridge - investigating GRID techniques
Neurogrid |  | Aug-sep 2012 |  | Completed setup of the VO. Still need to help them start using it.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Santanu Das - Cambridge Sys Admin |  | 2012-05-24 |  | Left to work for DataPipe, but then moved to the Financial Times.
Dissemmination events |  | Date |  | Notes
Particle Physics Masterclass |  | 12-13/3/12 |  | P. Gronbech gave GridPP talk at Oxford
|  | 18-19/4/13 |  | P. Gronbech gave GridPP talk at Oxford
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes
Pete Gronbech |  | 2013-12-06 |  | GridPP talk at the IATUL Workshop