## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q318 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 305.8% | 305.8% | 305.8% | 388.2% | 388.2% | 388.2% | 352.1% | 352.1% | 352.1% | 151.9% | 131.6% | 131.6% |  |  |  | 305.2% | 300.5% | 300.5%
.x.2 | % of promised (by that time) CPU available | 100% | 363.3% | 363.3% | 363.3% | 275.9% | 275.9% | 275.9% | 375.1% | 375.1% | 375.1% | 450.5% | 604.7% | 604.7% |  |  |  | 339.2% | 363.9% | 363.9%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 97% | 100% | 100% | 99% | 97% | 87% | 99% | 87% | 96% | 94% | 100% |  |  |  | 95.75% | 97.25% | 96% | QMUL low
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 97% | 100% | 100% | 100% | 100% | 87% | 99% | 91% | 96% | 94% | 100% |  |  |  | 95.75% | 97.5% | 97.75% | QMUL low
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 73.97% | 77.99% | 101.6% | 87.42% | 87.21% | 80.35% | 82.89% | 75.55% | 32.66% | 205% | 63.14% | 135.8% |  |  |  | 109.3% | 76.82% | 87.92% | RHUL high
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 57.54% | 54.22% | 64.27% | 74.26% | 74.74% | 62.97% | 82.89% | 75.55% | 28.34% | 52.88% | 53.82% | 75.14% |  |  |  | 68.64% | 65.63% | 58.25%
.x.3/.4
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q318
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2018 Jul | 2018 Aug | 2018 Sep | Total |  |  | 2018 Jul | 2018 Aug | 2018 Sep | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 17019913.1407 | 15113202.974 | 17533564.3482 | 49666680 |  | UKI-LT2-Brunel | 26080910.7429 | 25738108.7501 | 26681643.6308 | 78500663
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 27861162.3958 | 28197886.5458 | 27995660.0891 | 84054709 |  | UKI-LT2-IC-HEP | 33705562.9996 | 37338783.8739 | 36215481.3458 | 107259828
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 14805621.3978 | 2850206.9901 | 10729798.8551 | 28385627 |  | UKI-LT2-QMUL | 14805613.19 | 2850225.4331 | 15060224.2227 | 32716063
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 28894262.718 | 28432801.7636 | 27285775.5219 | 84612840 |  | UKI-LT2-RHUL | 33510738.4564 | 84343749.4009 | 35039544.3028 | 152894032
[8 empty] | UKI-LT2-UCL-HEP | 318406.0663 | 315602.9744 | 308938.3006 | 942947 |  | UKI-LT2-UCL-HEP | 338821.5312 | 338905.4911 | 332642.0911 | 1010369
[8 empty] | Total | 88899366 | 74909701 | 83853737 | 247662804 |  | Total | 108441647 | 150609773 | 113329536 | 372380955
[8 empty] | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normcpu/SITE/DATE/2017/10/2017/12/all/localinfrajobs/ | [5 empty] | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normelap_processors/SITE/DATE/2017/10/2017/12/all/onlyinfrajobs/
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1400 | 9632.812 | 457.8006 | 363.3% | 305.8% | 18.25% | 10.94% | 49666680 | 20.13% | 2208 | 77280000 | 64.27% | 101.6% | 63.27%
UKI-LT2-IC-HEP | 60456 | 5100 | 21915.766 | 1313.8219 | 275.9% | 388.2% | 31.52% | 39.84% | 84054709 | 34.07% | 2208 | 133486848 | 62.97% | 80.35% | 78.37%
UKI-LT2-QMUL | 45363 | 5001 | 12094.921 | 1420.211 | 375.1% | 352.1% | 23.65% | 39.07% | 28385627 | 11.51% | 2208 | 100161504 | 28.34% | 32.66% | 86.76% | Slurm accounting problem whereby CPU time equals wall time fixed in September
UKI-LT2-RHUL | 51000 | 1300 | 8434.349 | 987.6466 | 604.7% | 131.6% | 26.59% | 10.16% | 84612840 | 34.3% | 2208 | 112608000 | 75.14% | 135.8% | 55.34% | Very large wall-clock figures, being investigated
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 191819 | 12801 | 52714.598 | 4260.48 | 363.9% | 300.5% | 100% | 100% | 246719856 | 100% | 2208 | 423536352 | 58.25% | 87.92% | 66.51%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | rebus | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 5867 | 70110 | 1377
UKI-LT2-IC-HEP | 5718 | 56664 | 4965
UKI-LT2-QMUL | 3992 | 44575 | 5031
UKI-LT2-RHUL | 4624 | 48121 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 219470 | 12833
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q318
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cepc | cernatschool.org | comet.j-parc.jp | cms | dteam | dune | dzero | enmr.eu | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | icecube | ilc | ipv6.hepix.org | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | neiss.org.uk | ops | pheno | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.gear.cern.ch | vo.helio-vo.eu | vo.landslides.mossaic.org | skatelescope.eu | vo.londongrid.ac.uk |  | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 16
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 21
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 23
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 17
Total | 0 | 4 | 4 | 2 | 0 | 1 | 3 | 1 | 4 | 4 | 4 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 3 | 1 | 4 | 0 | 4 | 3 | 3 | 4 | 1 | 0 | 4 | 4 | 4 | 1 | 0 | 0 | 4 | 0 |  | 0 | 0 | 0 | 2 | 0 |  | 1 | 1 | 77
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | lsst | cernatschool.org | solidexperiment.org | vo.moedal.org | skatelescope.eu | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.278 |  | 0.411 |  |  |  | 10.601 | 894 |  | 29 | 0.017 | 0.002 |  |  |  |  | 1.491 | [5 empty] | 0.557 | 0.01 |  |  |  |  | 0.202 | [6 empty] | 0.018 |  | 0 |  |  | 0 |  |  |  | 936.587 | 9.615% | 1.451%
UKI-LT2-IC-HEP |  | 29 | 0 |  | 0 |  | 0 | 2598.004 |  | 9.761 |  |  |  |  | 344 |  |  |  | 0 | [15 empty] | 36.652 |  |  | 351 |  |  | 181 |  |  | 67.692 | 3617.109 | 37.13% | 18.39%
UKI-LT2-QMUL |  | 133 | 0.859 |  |  | 0 |  | 3.3 |  | 3600 | 0.052 |  |  |  | 180 |  | 0.673 | 0.0068 |  |  |  | 0.016 | 0.069 | 0.015 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 11 |  |  |  | 0 | 0.265 | 0.073 | 0 | 0.069 | 0.083 |  | 3929.505 | 40.34% | 3.721%
UKI-LT2-RHUL | 0 |  | 0.5 |  |  |  |  | 1.6 |  | 1255 | 0.015 | 0.002 |  |  |  |  | 0.19 | [5 empty] | 0.006 | 0.018 | [6 empty] | 0.009 | 0 | [5 empty] | 0 |  |  | 0 |  |  |  | 1257.34 | 12.91% | 0.05885%
Total | 0.278 | 162 | 1.77 | 0 | 0 | 0 | 10.601 | 3496.904 | 0 | 4893.761 | 0.084 | 0.004 | 0 | 0 | 524 | 0 | 2.354 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.632 | 0.043 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.009 | 0 | 0.019 | 11 | 36.652 | 0.018 | 0 | 351 | 0.265 | 0.073 | 181 | 0.069 | 0.083 | 67.692 | 9740.541 | 100% | 8.479%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q318
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.5 | 0.5 | 0.5 | 0.15 | 0.15 | 0.15 | Have not been updated
| Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
| P. Hobson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Antonio Perez Fernandez | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| B.Green/Tom | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 6.05 | 6.05 | 6.05 | 1.95 | 1.95 | 1.95

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q318
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel
UKI-LT2-IC-HEP
UKI-LT2-QMUL | Major issues with cooling and two planned power outages limited operations over the summer. Two new cooling units have been installed and commissioned replacing two broken units. The building where the Cluster is located now has an additional power supply. Leave over the summer also limited development work. Attended CHEP2018 and presented a poster at CHEP Redeployed two racks of kit into new racks with new PDUs. Redeployed all worker nodes on SL6.10 due to Lustre compatibility issues with Spectra and Meltdown patches.
UKI-LT2-RHUL | Couple of problems with ntpd and httpd services. IPV6 awaiting solution to DNS
UKI-LT2-UCL-HEP | Updated perfSONAR host OS to Centos7 and perfSONAR version > 4.1. Progess on IPv6 roll-out: "We have requested an allocation of IPv6 addresses, and should be ready to proceed in a few weeks' time."
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes